## Raw Data
[10 empty] | FTE's | [12 empty] | System Impact
Project Name | Type | Anchor | Status | RYG Indicator | Start Date | End Date | Revised Start | Revised End | Budget | jan/12 | fev/12 | 40969 | abr/12 | mai/12 | jun/12 | jul/12 | ago/12 | set/12 | out/12 | nov/12 | dez/12 | TOTAL | BSCS | OFS | Single | Maestro | SFA | SFO | CRIVO | Gemco | MIT | Synchro | Network | Datacenter | Security | Voice | EUC | Others | TOTAL | Dependencies
3G Anatel KPI | 3G | Yes | In execution | On Track | Mar/12 | R8 - Oct/12 |  |  | 946096.2518 | 0 | 7.4188 | 11.8397 | 6.3557 | 6.3202 | 6.2503 | 6.9376 | 6.9762 | 2.7088 | 2.7396 | 2.7552 | 2.7711 | 63.0731 |  |  | X | [13 empty] | 1 | No Dependencies
3G BI/DW (MIT) | 3G | Yes | In execution | On Track | Dec/11 | R7 - Jul/12 |  | R - Oct/12 | 1293531.303 | 0 | 21.4622 | 10.6099 | 10.5503 | 10.4913 | 10.3754 | 11.3417 | 11.4047 | 0 | 0 | 0 | 0 | 86.2354 | [8 empty] | X | [7 empty] | 1 | Oracle 11G BD01 + ASM
3G Bill Checkout | 3G | Yes | In execution | On Track | TBD | TBD |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | 0 | PENDING DATA
^ DELETE ABOVE EXAMPLES

## Planning Flow
[5 empty] | Step 1 | Step 2 | Step 3 |  |  | Step 4 |  |  | Step 5 |  |  | Step 6
Project Name | 3G? | Anchor? | Status | Baseline Release | Anchors & Constraints | Project Status | System Impacts | Proposed Release | Dependencies | Resource Loading | Target Release | Dependencies | Risk Normalization | Target Release | Dependencies | IT Validation | Business Validation
3G Anatel KPI | 3G | Yes | On Track | 08 - Oct/12 | Anchor | On Track | Major Candidate | 12 - Major - 02/13 | No Dependencies |  |  |  | No Change | 12 - Major - 02/13 | No Dependencies
3G BI/DW (MIT) | 3G | Yes | On Track | 05 - Jul/12 | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 | Oracle 11G BD01 + ASM |  |  |  | No Change | 09 - Major - 11/12 | Oracle 11G BD01 + ASM
3G Bill Checkout | 3G | Yes | On Track | 0 - TBD | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 | PENDING DATA |  |  |  | No Change | 09 - Major - 11/12 | PENDING DATA
^ DELETE ABOVE EXAMPLES

## Release Cadence
PROPOSED RELEASE NAMES / TYPE
# | Release Name | Type | Target Date | Name / Theme | Capabilities Impacted
01 | 01 - Major - 03/12 | Major | 2012-03-15
02 | 02 - Minor - 04/12 | Minor | 2012-04-15
03 | 03 - Fix - 05/12 | Fix | 2012-05-15
04 | 04 - - 06/12 |  | 2012-06-15
05 | 05 - - 07/12 |  | 2012-07-15
06 | 06 - - 08/12 |  | 2012-08-15
07 | 07 - - 09/12 |  | 2012-09-15
08 | 08 - - 10/12 |  | 2012-10-15
09 | 09 - - 11/12 |  | 2012-11-15
10 | 10 - - 12/12 |  | 2012-12-15
11 | 11 - - 01/13 |  | 2013-01-15
12 | 12 - - 02/13 |  | 2013-02-15
13 | 13 - - 03/13 |  | 2013-03-15
14 | 14 - - 04/13 |  | 2013-04-15
15 | 15 - - 05/13 |  | 2013-05-15
16 | 16 - - 06/13 |  | 2013-06-15
17 | 17 - - 07/13 |  | 2013-07-15
18 | 18 - - 08/13 |  | 2013-08-15
19 | 19 - - 09/13 |  | 2013-09-15
20 | 20 - - 10/13 |  | 2013-10-15
21 | 21 - - 11/13 |  | 2013-11-15

## Data Staging_Systems
|  | Step 1 | Step 2 | Step 3 |  | Systems Impact
Project Name | Baseline Release | Anchors & Constraints | Project Status | System Impacts | Proposed Release | System 1 | System 2 | System 3 | System 4 | System 5 | System 6 | System 7 | System 8 | System 9 | System 10 | Others | TOTAL | Dependencies
3G Anatel KPI | 08 - Oct/12 | Anchor | On Track | Major Candidate | 12 - Major - 02/13 | 0 | 0 | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | No Dependencies
3G BI/DW (MIT) | 05 - Jul/12 | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | X | 0 | 0 | 1 | Oracle 11G BD01 + ASM
3G Bill Checkout | 0 - TBD | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PENDING DATA
^ DELETE ABOVE EXAMPLES
[6 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3

## Data Staging_Resources
[11 empty] | Minor | Minor | [6 empty] | Major
|  | Step 1 | Step 2 | Step 3 |  | Step 4 |  |  | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2012 | 2013 | 2013 | 2013
Project Name | Baseline Release | Anchors & Constraints | Project Status | System Impacts | Proposed Release | Resource Loading | Target Release | Dependencies | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Dependencies
3G Anatel KPI | 08 - Oct/12 | Anchor | On Track | Major Candidate | 12 - Major - 02/13 |  |  |  | 0 | 7.4188 | 11.8397 | 6.3557 | 6.3202 | 6.2503 | 6.9376 | 6.9762 | 2.7088 | 2.7396 | 2.7552 |  |  |  |  | No Dependencies
3G BI/DW (MIT) | 05 - Jul/12 | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 |  |  |  | 0 | 21.4622 | 10.6099 | 10.5503 | 10.4913 | 10.3754 | 11.3417 | 11.4047 | 0 | 0 | 0 |  |  |  |  | Oracle 11G BD01 + ASM
3G Bill Checkout | 0 - TBD | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | PENDING DATA
^ DELETE ABOVE EXAMPLES
[8 empty] | TOTALS | 0 | 28.881 | 22.4496 | 16.9059 | 16.8115 | 16.6257 | 18.2793 | 18.3808 | 2.7088 | 2.7396 | 2.7552 | 0 | 0 | 0 | 0
BASELINE
Note on G3: 1) Project Status: Push out resources for Projects “At Risk” or “Behind” in a way that builds on the target cadence structure formed from steps 1-3. 2) Move resources to minimize system impact while maintaining the release cadence formed from steps 1-3. 3) Move non-anchors that haven’t been resource loaded already into releases to optimize resource loading

## Data Staging_Risk
[11 empty] | 1 | 1 | 1 | 1 | WEIGHT
[11 empty] | 1000000 | 30 | 2 | 1 | UPPER LIMIT
|  | Step 1 | Step 2 | Step 3 |  | Step 4 |  | Step 5 |  |  | 250000 | 20 | 1 | 0 | LOWER LIMIT
Project Name | Baseline Release | Anchors & Constraints | Project Status | System Impacts | Proposed Release | Resource Loading | Target Release | Risk Normalization | Target Release | Dependencies | Budget | FTE's | System Impact | Dependencies | TOTAL RISK SCORE
3G Anatel KPI | 08 - Oct/12 | Anchor | On Track | Major Candidate | 12 - Major - 02/13 | 0 | 0 |  | 12 - Major - 02/13 |  | 946096.2518 | 63.0731 | 1 | 1 | 12
3G BI/DW (MIT) | 05 - Jul/12 | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 | 0 | 0 |  | 09 - Major - 11/12 |  | 1293531.303 | 86.2354 | 1 | 1 | 14 | Row Labels | Sum of TOTAL RISK SCORE
3G Bill Checkout | 0 - TBD | Anchor | On Track | Minor Candidate | 09 - Major - 11/12 | 0 | 0 |  | 09 - Major - 11/12 |  | 0 | 0 | 0 |  | 6 | 09 - Major - 11/12 | 20
^ DELETE ABOVE EXAMPLES | [15 empty] | 12 - Major - 02/13 | 12
One for each Release
Placeholder | One for each Release |  |  |  | One for each Release |  | One for each Release |  | One for each Release | [6 empty] | (blank)
^ Use to ensure inclusion in pivot | [15 empty] | Grand Total | 32
Note on G4: 1) Project Status: Push out resources for Projects “At Risk” or “Behind” in a way that builds on the target cadence structure formed from steps 1-3. 2) Move resources to minimize system impact while maintaining the release cadence formed from steps 1-3. 3) Move non-anchors that haven’t been resource loaded already into releases to optimize resource loading