## Overview
Project Information
Customer | Model N Project Manager
Project Name (Open Air Name) | Model N MD / Executive Sponsor
Estimated Start | Customer Project Manager(s)
Estimated Finish | Customer Project Sponsor(s)
Estimated Duration | Project Methodology
Contract Terms (e.g. T&M) | Model N Version
Services Budget | Application Scope (Modules)
Expenses Budget | Project Repository Link
Industry (e.g. Med Device) | Other Info
Project Objective

## Status
Project Information
Project | Planned Go-Live Date |  | Update Date
Overall Project Status |  | 1 | Current Phase | total value | 7
7 Keys Status (limit length of input to 3-5 concise points) |  |  | Planned Action for Red / Yellow Items (status) | overall project | 1
Stakeholders |  | 1
Business Benefits |  | 1
Work & Schedule |  | 1
Team |  | 1
Scope |  | 1
Risks |  | 1
Budget & Delivery Org Benefits |  | 1
Note on A3: Input a concise, executive level summary of the status of the project
Note on E3: Ensure you fill out a gate review form, links can be found on Milestones tab
Note on A5: Are project communications timely and appropriate? Are the Business and IT teams actively involved?
Note on D5: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track)
Note on A6: Are business benefits for project clearly understood? Are benefits on track to be realized?
Note on D6: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track)
Note on A7: Is the project schedule clear and understood by team? Is the project schedule on track and realistic?
Note on D7: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track)
Note on A8: Is the right size steam in place to achieve project objectives? Are the right skills available to deliver project? Is team morale high?
Note on D8: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track
Note on A9: Are change control processes well defined and effective? Is scope clear and known to project teams? Are any/all recent changes to scope going through change control process?
Note on D9: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track)
Note on A10: Are risks properly evaluated and mitigation plans established? Are issue & risk logs are actively managed?
Note on D10: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track)
Note on A11: - Will the project help the delivery organization’s reputation? - Is the project financiall healthy and collections are current? - Will the project help team members’ careers? - Will the project contribute to the organization’s knowledge and lessons learned?
Note on D11: Red - Off track; Immediate corrective action required (corrective action plan is off track) Yellow - Heading off track; corrective action needed to get back on track Green - On Track; stay the course (corrective action plan agreed and on track)

## Milestones
Milestones | Original Due Date | Current Planned Due Date | Owner | % Complete | Status | Comments
Project Handover
Project Kickoff
Sample Data Collected
Inception Gate Review
Workshops Complete
Use Cases/FDS Complete
Full Breadth Data Load
Dev. Environment Setup
Elaboration Gate Review
Build and Configure System
Full Breadth and Depth Data Load
Full Contract Data Load
Test Scripts/Plan Complete
QA & Perf Env Setup
Dry Run Complete
Construction Gate Review
Mock Conversion 1
Mock Conversion 2
Mock Conversion 3
SIT 1
SIT 2
SIT 3
Performance
UAT
Verificaiton Gate Review
End User Training Complete
Go-Live
Transition to Support Complete
Hyper Care Complete
Project Debrief Complete
Transition Gate Review

## Contacts
Role | Customer / MODEL N | First Name | Last Name | Work # | Mobile # | Email
Project Sponsor | Customer
Project Manager (SPOC) | Customer
Business owner | Customer
Business SME(s) | Customer
ERP System Team | Customer
Build and Release Engineer | Customer
Integration / Conversion Technical Lead | Customer
Data Migration/ Conversion Lead | Customer
Integration / Conversion Developers | Customer
Organizational Change Lead | Customer
Training Lead | Customer
Testing Lead | Customer
Testers | Customer
Project Sponsor / Managing Director | MODEL N
Project Manager | MODEL N
Business Analyst (s) | MODEL N
Solution Architect | MODEL N
Technical Lead / Architect | MODEL N
Application Developer | MODEL N
Dataflow Developer | MODEL N
Report Developer | MODEL N
Deployment Engineer | MODEL N
COE Quality Lead | MODEL N

## RAID
Type | Description | Date Identified | Current Status | Priority | Due Date | Complete Date | Mitigation Plan / Next Steps | Owner | Requires Escalation

## Gantt
Gantt Chart | time axis 2014-01-01 to 2014-11-12
Build Plan
Inception | bar: 2014-01-01 to 2014-01-22
Initiate Program Strategy | bar: 2014-01-01 to 2014-01-08
Create Program Vision | bar: 2014-01-08 to 2014-01-15
Gather Sample Data | bar: 2014-01-08 to 2014-01-22
Elaboration | bar: 2014-01-29 to 2014-04-23
Confirm Solution Design
Confirm Technical Design
Load & Assess Full Data
Train Project Team
Construction | bar: 2014-04-30 to 2014-06-11
Build & Dry Run Solution
Conduct Mock Conversion
Prepare for Testing
Verification | bar: 2014-06-18 to 2014-09-17
SIT 1
SIT 2
SIT 3
Performance Testing
User Acceptance Testing
Transition | bar: 2014-09-24 to 2014-11-12
Train End Users
System Go-Live
Execute Hyper-care

## Product Backlog (hidden)
Story ID | Release | Epic (Key Business Process) | Sprint | Points (1-Low to 5 - High) | Story Name | Story Description | Conditions of Satisfaction / Definition of Done | Design | Definition of Done | Scrum Team Members Responsible | Integration Tests | Integration Testing Outcome | Regression Tests | Regressoin Testing Outcome | Performance Tests | Performance Testing Outcome | System Tests | System Testing Outcome | Date of Acceptance by Customer
EXAMPLE 1005 | EXAMPLE 1 | 1. Master Data Integration | EXAMPLE 1 | EXAMPLE 5 | EXAMPLE Multi Currency: Create quote in various currencies | EXAMPLE As a sales rep, I want to be able to select a currency from a list of currencies during the quote creation, so I can quote for my customers who are located in various countries in my region. | EXAMPLE 1. Sales rep located in country A creates a new quote for an account located in country B • Sales rep creates oppty for account • Sales rep creates a new quote • System copies account into quote header • Sales rep enters contact 2. Sales rep selects currency other than his default currency • Sales rep sees the default currency maintained for his user • Sales rep can select from a list of currencies 3. Sales rep adds products to the quote • Sales rep sees list prices for product in the selected currency • Sales rep adds product to the quote • System displays the products in the quote header currency | Design Document: Functional Design - Section 1 & Technical Design: Section 2 | EXAMPLE Functionality accepted by product owner No outstanding bugs Test cases are documented Design is completed |  | Integration Tests |  | Regression Testing |  | Performance Testing |  | System Testing

## Delv Tracker
Phase | Org Owner | Work stream | Author / Owner | Deliverable | Description | Assumptions | Dependencies | Status | % Complete | Planned Submission Date | Actual Submittal
All Phases | Model N | Management |  | Project Plan | This is updated throughout all phases of project. Development/Refinement of project schedule for all phases. Will contain detailed tasks for next phase of project, based on learning of this phase |  |  |  | 100% | 2014-01-01
All Phases | Model N | Management |  | Weekly Status Reports | This is updated throughout all phases of project. Status report includes activities for each team member, planned activities for following week, and open issues/risks
Inception | <Customer> | Organization |  | Project Charter | A document that provides roles and responsibilities, outlines the project objectives, identifies the main stakeholders, and defines the authority of the project manager
Inception | <Customer> | Functional |  | System Requirements Specification | Documentation of business requirements and known functional gaps, to be used as input into the workshops
Inception | <Customer> | Technical |  | System Context Diagram | A high level diagram of Model N that defines the boundary between Model N and its environment, showing the entities that interact with it.
Inception | <Customer> | Data |  | Representative Data Sets | Data set of contracts, policies and master data that provide a compressive view of in scope processes
Inception | <Customer> | Organization |  | Stakeholder Management Matrix | Tool used to identify the individuals or groups that are likely to be affected by the Model N solution, and sorting them according to their impact solution will have on them
Elaboration | Model N | Functional |  | Functional Design Specifications | Functional design specifications that outline the system design
Elaboration | Model N | Technical |  | Preliminary Hardware Sizing | Preliminary Hardware sizing specification to be used for procuring development, QA, Performance & production environments (depending on lead time of production equipment and project duration, this can be delayed, Model N recommends delaying until Verification if lead time allows)
Elaboration | <Customer> | Organization |  | Organizational Change Management Plan | Defines potential changes in process, technology, and organization. And describes approach for aligning process and organizational changes with new Model N- enabled solution architecture. Lastly, it identifies appropriate training needs for the project
Elaboration | <Customer> | Management |  | Cut-over plan | High-level cutover plan that describes how old systems will be retired as Model N is turned on. Includes deployment dates per country, deployment activities, and support plan during Hypercare
Elaboration | <Customer> | Data |  | Data Interface & Conversion Design | Development of Data Conversion and Integration Plan identifying sequence of data conversion and method of load, and identifying plan for ongoing interfaces. Outlines plan for mock and final data conversions.
Elaboration | <Customer> | Management |  | Testing Strategy | Documentation of testing approach and criteria for acceptance. Documentation of validated testing requirements, if necessary. And documentation of User Acceptance Testing strategy
Elaboration | <Customer> | Technical |  | Development Environment Setup | Setup and support environments required for project development activities. Setup and support covers the installation of servers, 3rd party software, database, and deployment of the Model N build. It does not cover the configuration of the Model N software.
Elaboration | <Customer> | Data |  | Full Data Set | Provide full breadth dataset (full coverage of all master data, transaction data and contracts)
Construction | <Customer> | Functional |  | System, Integration, Performance and UAT Test Plans | Detailed test plan outlining dependencies, expected results, execution owners and priority for each test script
Construction | <Customer> | Data |  | Conversion Summary Report | Report summarizing the mock conversions, including detailed load timings
Construction | Model N | Technical |  | Model N Application Builds | Completion of configuration and unit testing of Common functional configurations and dataflow. Model N will provide builds throughout this phase (and verification as necessary) in support of rapid iterative development and testing approach.
Construction | <Customer> | Technical |  | Legacy System Data and Interface Programs | Completion of coding and unit testing of source data extract programs and data transport programs
Construction | <Customer> | Functional |  | SOP Development | Development of an SOP for each function/process and any manual processes that are added or changed due to the Model N implementation.
Construction | <Customer> | Technical |  | Testing, Data Migration, and Performance Environments | Setup and support multiple environments required for project activities. Setup and support covers the installation of servers, 3rd party software, database, and deployment of the Model N build. It does not cover the configuration of the Model N software.
Construction | Model N | Management |  | Support Plan | Detailed support plan for hyper-care and on-going support, including help desk and support for any customizations required
Construction | <Customer> | Functional |  | Test scripts | Scripts will provide detailed steps required to test the requirements outlined in inception in Model N and external systems
Verification | <Customer> | Functional |  | Test Execution Summary Reports | Results of Execution of all testing
Verification | <Customer> | Organization |  | End User Training Plan and Materials | Finalize End User training materials, including finalization of all SOPs
Verification | <Customer> | Management |  | Finalize System Cut-over Plan | Refined and more detailed System Cut-over Plan outlining how existing systems will be retired and Model N will be turned “on”, including detailed steps and ownership of each step.
Transition | Model N | Organization |  | Knowledge Transfer Plan | Complete knowledge transfer for business users, support staff, and trainers. Items and knowledge to be transferred will be identified and managed like a project plan with due dates and people assignments
Transition | <Customer> | Technical |  | Final Data Migration | Final Data Conversion Summary Report
Transition | <Customer> | Technical |  | Model N Deployment to Production | Executed System Cut-over Plan including the migration of the database, code, and configurations to production. Verification of system for readiness
Transition | Model N | Functional |  | Provide Hyper-Care support | Provide hyper-care support to users of system. At conclusion of period, transition solution to Model N customer support, including transition to support checklist

## FDS Tracker
Work-stream | FDS Name | FDS Content | Author | Status | Planned Submittal | Actual Submital | Approver | Approval Status | Planned Sign-Off Date | Actual Sign-Off Date

## Test Scr. Tracker
Customer FDS | Customer Requirement ID | Customer Requirement | Requirement Owner | Model N Use Case ID | Model N Use Case | Model N Scenario ID | Model N Scenario | Model N Test Case | Model N Test Script ID | Planned Mapping Date | Functional / BA Owner | Script Mapping Status | Planned I & ER Date | Inputs & Expected Results Owner | I & ER Status | Planned ATS Configured Date | ATS Configuror | Script Configuration Status

## Price Type Tracker
Price Types | Elaboration | [8 empty] | Construction | [9 empty] | Verification |  |  |  |  | Transition
| Requirement Gathering Status | Gap Analysis | Workshop Date | Design | [5 empty] | Configuration | [7 empty] | Off Line Model |  | SIT1 |  | SIT2 Full Data | SIT3 | UAT | PROD
|  |  |  | Data Source (MN) | Formula (MN) | Filter (HP) | Result Column (MN) | Validation (MN) | Overall (%) | Data Source | Formula | Filter | CB & DD (MN) | Result Column | Validation | Overall | Delivered Date | UI | Query/ Filter | Number Matching (Partial Data) | Test Script (Full Data)
Monthly AMP
Quarterly AMP
BP Initial
BP Restated
ASP
Quarterly NFAMP
Annual NFAMP
T/P NFAMP
Annual FCP
Quarterly FCP
Temporary/Provisional FCP
TriCare
PHS
Legend
| In Progress | Completed | Not Applicable | Not Started

## Blank Tracker
Item | Detail | Owner | Status | Plan Date

## Wksp Gantt
Workshop |  | COE SA | BA | Workshop Duration (Hrs) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
Master Data | bar: W1 to W3
| Manage Customer | Eric K | Neeraj Ambika | 6 | bar: W1
| Manage GPO Membership | Eric K | Neeraj Ambika | 3 | bar: W1
| Manage Plan Membership | Kristina | Neeraj | 3 | bar: W1
| Manage Product | Bill Watts, Watson IT, Business, Eric K, Jesse | Neeraj Gowri | 6 | bar: W1
| Manage Market Baskets | Kristina | Neeraj | 3 | bar: W2
| Manage Formulary | Kristina | Neeraj | 3 | bar: W2
| Manage Price List Price List Approval Route | Bill Watts, Watson IT, Business, Eric K, Jesse | Neeraj Gowri | 3 | bar: W2
| Manage Price Floor | Eric K | Neeraj | 3 | bar: W3
| Manage User Groups/Roles | Eric K, Jesse, Kristina | Neeraj Gowri | 3 | bar: W3
Contracts and Pricing (PBC) | bar: W4 to W8
| Contract Creation/Maintenance | Eric K | Neeraj | 6 | bar: W4
| Pricing Strategy (Contract Mapping) | Eric K | Neeraj | 6 | bar: W4 to W5
| Compliance Strategy (Contract Mapping) | Eric K | Neeraj | 6 | bar: W4 to W5
| Manage Contract Eligiblity | Eric K | Neeraj | 6 | bar: W4 to W5
| Commercial Contract Approvals | Eric K | Neeraj | 3 | bar: W6 to W7
| Mass Updates | Eric K | Neeraj | 3 | bar: W6 to W7
| Price Resolution | Eric K | Neeraj | 3 | bar: W8
| Contract Reporting | Eric K | Neeraj | 2 | bar: W8
Utilization Based Contracting (MCO) | bar: W6 to W8
| Contract Creation/Maintenance | Kristina | Neeraj | 6 | bar: W6
| Contract Mapping | Kristina | Neeraj | 20 | bar: W7 to W8
| Manage MCO Contract Elibility | Kristina | Neeraj | 4 | bar: W8
| MCO Contract Approvals | Kristina | Neeraj | 2 | bar: W8
Rebate Strategies | bar: W8 to W12
| Review representative contracts | Eric K | Neeraj | 9 | bar: W8 to W10
| Define PBC Strategies per contract | Eric K | Neeraj | 40 | bar: W9 to W10
| Define PBC Strategies per contract | Eric K | Neeraj | 40 | bar: W11 to W12
| Prototype | Eric K | Neeraj | 40 | bar: W12
Commercial Rebate Processing | bar: W11 to W13
| Loading/Validating Utilization Lines | Kristina | Neeraj | 4 | bar: W11
| MCO Rebate Calculation and Payment Processing | Kristina | Neeraj | 6 | bar: W11 to W12
| MCO Rebate Payment Approvals | Kristina | Neeraj | incl in 85 | bar: W12
| MCO Operational Reports | Kristina | Neeraj | 6 | bar: W13
ScriptValidate | bar: W14 to W15
Government Pricing | bar: W6 to W12
| Manage Product Linkage, Maintain GP Product Attributes | Jesse | Gowri | 4 | bar: W6; W11
Activate Price Type (Policy Review)
| - MAMP - QAMP | Jesse | Gowri | 4 | bar: W7 to W8; W12
| - BP | Jesse | Gowri | 2 | bar: W8
| - PHS | Jesse | Gowri | 1 | bar: W8
| - ASP | Jesse | Gowri | 3 | bar: W9
| - QNFAMP - ANFAMP - TNFAMP - FCP (s) | Jesse | Gowri | 4 | bar: W7; W9
| Calculate Workbook - MAMP, QAMP - BP - PHS - ASP - QNFAMP, ANFAMP, TNFAMP - FCP (s) | Jesse | Gowri | 4 | bar: W10
| File Workbook View Dashboards and GP Reports | Jesse | Gowri | 2 | bar: W10
FSS Compliance and DRM | bar: W13
| Configure & Activate FSS Policy (Policy Mapping) | Jesse | Gowri | 2 | bar: W13
| Review and Analyze FSS Price Points | Jesse | Gowri | 2 | bar: W13
| Process Notifications and approve RFM Activate FSS Price List FSS Operational Reports | Jesse | Gowri | 3 | bar: W13
Medicaid | bar: W14
| Create Program | Jesse | Gowri | bar: W14
| Manage Medicaid Policies Manage Pricing Manage Medicaid Rates Medicaid Customer | Jesse | Gowri | 4 | bar: W14
| Process Medicaid Claims Process and Request Medicaid Payment Maintain Reimbursement Info Medicaid Operational Reports | Jesse | Gowri | 4 | bar: W14
RMI | bar: W15
| Price Impact | Jesse | Gowri | 4 | bar: W15
| MCO Impact |  |  | 4 | bar: W15
Technical Workshops
Founcdational Technical Workshops
| Environments, Infrastructure and Performance | Praney | Bill/Suresh | 3 | bar: W1
| System Landscape/Integration Approach -1 | Bill | Suresh | 3 | bar: W1
| System Landscape/Integration Approach - 2 | Bill | Suresh | 3 | bar: W2
| Model N Build and Release Process | Bill | Suresh | 3 | bar: W2
| Data Conversion Strategy - 6 sessions | Bill | Suresh | 10 | W3: 1,2; W6: 3,4; W7: 5,6; W10: 7,8; W11: 9,10
| Batch Processing | Bill | Suresh | 3 | bar: W4
| Reporting Architecture (RME, PI, DW) | Bill/Jim | Suresh | 3 | bar: W12
| RMI Architecture |  |  | 3 | bar: W13
| RMI Deployment Planning |  |  | 3 | bar: W14
| Archival Strategy | Bill/Jim | Suresh | 3 | bar: W15
Interface Mapping Workshops Schedule | bar: W4 to W10
Master Data and Contract Management | bar: W4
| Customers and Legal Entity Hierarchy | Bill | Suresh | 3 | bar: W4
| Products, Competitor Products | Bill | Suresh | 3 | bar: W4
| Market Baskets, Formulary | Bill | Suresh | 3 | bar: W5
| Price Lists | Bill | Suresh | 3 | bar: W5
| Membership Roster | Bill | Suresh | 2 | bar: W5
Institutional (PBC) | bar: W6 to W10
| Direct Sales | Bill | Suresh | 2 | bar: W7; W9 to W10
| Indirect Sales | Bill | Suresh | 2 | bar: W7; W9 to W10
| Custom Sales | Bill | Suresh | 2 | bar: W7; W9 to W10
| Real Time Pricing? | Bill | Suresh | 2 | bar: W6; W9 to W10
| Chargeback Payment Request | Bill | Suresh | 2 | bar: W8 to W10
| PBC Rebate Payment Request | Bill | Suresh | 2 | bar: W8 to W10
| Admin Fee Rebate Payment Request | Bill | Suresh | 2 | bar: W8 to W10
| Chargeback Payment Confirmation | Bill | Suresh | 2 | bar: W9 to W10
| PBC Rebate Payment Confirmation | Bill | Suresh | 2 | bar: W9 to W10
| Admin Fee Rebate Payment Confirmation | Bill | Suresh | 2 | bar: W9 to W10
| Bid Awards (EDI 845) | Bill | Suresh | 2 | bar: W9 to W10
| Chargeback Reconciliation (EDI 849) | Bill | Suresh | 2 | bar: W9 to W10
Managed Care (UBC) | bar: W9 to W10
| Managed Care (UBC) Utilization | Bill | Suresh | 2 | bar: W9
| UBC Rebate Payment Request | Bill | Suresh | 2 | bar: W9
| UBC Rebate Payment Confirmation | Bill | Suresh | 2 | bar: W10
| National Market Share | Bill | Suresh | 2 | bar: W10
Conversion Mapping Workshops Schedule | bar: W9 to W16
Master Data and Contract Management | bar: W9 to W11
| Customers and Legal Entity Hierarchy | Bill | Suresh | 3 | bar: W9
| Products, Competitor Products | Bill | Suresh | 3 | bar: W9
| Market Baskets, Formulary | Bill | Suresh | 3 | bar: W10
| Price Lists | Bill | Suresh | 3 | bar: W10
| Membership Roster | Bill | Suresh | 2 | bar: W11
| Membership Roster | Bill | Suresh | 2 | bar: W11
Institutional (PBC) | bar: W11
| Direct Sales | Bill | Suresh | 2 | bar: W11
| Indirect Sales | Bill | Suresh | 2 | bar: W11
| Custom Sales | Bill | Suresh | 2 | bar: W11
Managed Care (UBC) | bar: W12 to W13
| Book of Business/Plans | Bill | Suresh | 2 | bar: W12
| Managed Care (UBC) Utilization | Bill | Suresh | 2 | bar: W13
| National Market Share | Bill | Suresh | 2 | bar: W13
Medicaid | bar: W14
| Medicaid Programs conversion | Bill | Suresh | 2 | bar: W14
| Medicaid Claims Conversion | Bill | Suresh | 2 | bar: W14
| URA Conversion | Bill | Suresh | 2 | bar: W14
Government Pricing | bar: W15
| Government Price Lists conversion | Bill | Suresh | 2 | bar: W15
| Product Attributes for GP | Bill | Suresh | 2 | bar: W15
| GP Conversion considerations - Rebate Types, etc | Bill | Suresh | 2 | bar: W15
Admininstration Workshops | bar: W16
| Users, roles, groups - detailed | Bill | Suresh | 2 | bar: W16
| LDAP/Single Sign on, password validations, etc | Bill | Suresh | 2 | bar: W16

## Int. Matrix
| <Cust> / Model N Integration Development & Testing |  |  |  |  | Legend |  | Green | Complete |  | Mock Conversions
[6 empty] | White | Not Started | Red | Past Due |  | Mock 0: Design Prototype |  | Mock 2: Full Breadth Data for SIT
[6 empty] | Blue | In Progress | Gray | N/A |  | Mock 1: Partial Data Test |  | Mock 3: Full Volume for Performance Test/UAT
|  |  | Documentation |  |  | Mock 0 |  |  |  | Mock 1 |  |  |  | Mock 2 |  |  |  | Mock 3 |  |  |  | Mock 4 (UAT Run) |  |  |  | Action Items
| Data Flow / Integration Activity | Source System | MN Interface Layout | MN TDS | <Cust> TDS | Model N Interfaces Ready | Extract & Transform | Load | Data Reconciliation/UI Test | Model N Interfaces Ready | Extract & Transform | Load | Data Reconciliation/UI Test | Model N Interfaces Ready | Extract & Transform | Load | Data Reconciliation/UI Test | Model N Interfaces Ready | Extract & Transform | Load | Data Reconciliation/UI Test | Model N Interfaces Ready | Extract & Transform | Load | Data Reconciliation/UI Test | Action Item | Owner | Date Due
| Responsibility |  | Model N | Model N | <Cust> | Model N | <Cust> | Model N | <Cust> | Model N | <Cust> | Model N | <Cust> | Model N | <Cust> | <Cust>/Model N | <Cust> | Model N | <Cust> | <Cust> | <Cust> | Model N | <Cust> | <Cust> | <Cust>
# | Master Data/Contracts |  |  |  |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends:
1 | Customer
| Conversion - Direct Customer | SAP
| Conversion - Indirect Customer | SAP
| Ongoing - Direct Customer | SAP
| Ongoing - Indirect Customer | SAP
2 | Legal Entity Hierarchy (LEH)
| Conversion | SAP
| Ongoing | SAP
3 | Products
| Conversion | SAP
| Ongoing | SAP
4 | Unit of Measure conversion
| Conversion | SAP
| Ongoing | SAP
5 | Competitor Products
| Conversion | Business
| Ongoing | Business
6 | Price Lists
| Conversion | SAP
| Ongoing | SAP
7 | Membership
| Conversion - GPO Membership | Business
8 | Book of Business
| Conversion | Business
| OnGoing | Business
| Contract Conversion |  |  |  |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends:
9 | Contracts
| Conversion - Contract Header | Business
| Conversion - Products and Pricing | Business
| Commercial/Managed Care |  |  |  |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends:
10 | Direct Sales
| Conversion - SIT | SAP
| Conversion - Full | SAP
| Ongoing | SAP
12 | Chargebacks
| Conversion - SIT | Revitas
| Conversion - Full | Revitas
| Ongoing - EDI 844 | Gentran
13 | Utilization Data
| Ongoing | Business
14 | UOM Data Maps
| Conversion | Business |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
15 | Customer Data Maps
| Conversion | Business |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
16 | Market Baskets
| Conversion | Business
17 | National Market Share
| Conversion | Business
18 | EDI 845 - Bid Awards
| Ongoing | Model N
19 | EDI 849 - Chargeback Reconciliation
| Ongoing | Model N
20 | Credit/Debit Memo Request
| Ongoing | Model N
21 | Credit/Debit Memo Confirmation
| Ongoing | SAP
22 | Rebate Payment Request
| Ongoing | Model N
23 | Rebate Payment Confirmation
| Ongoing | SAP
24 | Estimated Rebate Payment Request
| Ongoing | Model N
25 | Estimated Rebate Payment Confirmation
| Ongoing | SAP
26 | Coverage Gap Payment Request
| Ongoing | Model N
27 | Accruals
| Ongoing | Model N
28 | Accrual Backout
| Ongoing | SAP
29 | Pricing
| Real Time | SAP
| Bid Award Extraction | SAP
| Regulatory |  |  |  |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends: |  | Starts: |  | Ends:
30 | Historical Rebate Payments
| Conversion | Revitas
31 | Time Series
| Conversion | Business
32 | Labeler Codes
| Conversion | Model N
33 | Medicaid Programs | Revitas Medicaid
Conversion
34 | Medicaid Price Lists | Revitas Medicaid
Conversion
35 | Medicaid Converted Claims | Revitas Medicaid
Conversion
36 | Government Price Lists | Revitas GP
Conversion
37 | Medicaid Check Request
| Ongoing | Model N
38 | Medicaid Check Confirmation
| Ongoing | Model N
Note on AC9: Bill: With Model N Support

## List (hidden)
1
0
-1

## Instructions
Purpose of Workbook | This workbook is meant to assist Project Managers in managing projects. It is built on a simplified version of many typical project workbooks. It is not meant to discourage use of individually preferred tools.
How to Use | Update this workbook daily/weekly, save into shared drive. You can add tabs as desired, however the Status, Overview and Milestones tabs need to be updated weekly in the Model N Format. Deliverable Tracker, RAID, Gantt and RACI are required for projects (not MPC projects), however, a PM can use a customer format or other format as desired. This workbook should be in addition to resource, stakeholder management matrix's and financial trackers.
Naming Convention | Save weekly on Google Site as [PROJECT][DATE MMDDYY][VERSION] - Example Amgen ICO 03152014
Instructions | Purpose of Tab
Overview | Use this to identify general project information that should not change week to week
Status | Use this to provide status on the 7 keys to project success
Milestones | Use this to track the key project milestones that should be monitored on a weekly basis
RAID | This is a modified version of a typical RAID log, use this to manage the project Risks, Actions, Issues and Decisions
Gantt | Use this to depict the high level project schedule
RACI | Use this to provide a clear view of who is responsible, Accountable, Consulted, and Informed for the project
Deliverable Tracker | Use this to manage key project deliverables in order to meet the project objectives & contractual commitments, including assumptions and dependencies
FDS Tracker | Use this to track Functional Design Spec Status
Test Scrtip Tracker | Use this to track Test Scrtip Status
Blank Tracker | Use this to create other unique trackers (e.g. Enviornments)
Workshop Gantt | Use this to show high level workshop plan
Integration Matrix | Use this to track integration and conversion progress
Product Backlog | Tracker for Stories when leveraging Agile Methodology
Logistics (Hidden) | Use this to manage project logistics
Communication (Hidden) | Use this tab to highlight the project communication plans (e.g. meetings, etc…)
CCR (Hidden) | Use this to manage the Change Requests / Change Orders of the project
Lessons Learned (Hidden) | Use this to highlight any best practices or lessons learned on the project - these should be logged throughout the project

## Logistics (hidden)
STATUS | WORKSTREAM | MEETING TOPIC / INTERFACE | MEETING FORMAT | MEETING LOCATION | START DATE | FINISH DATE | DURATION | START TIME | FINISH TIME | CUSTOMER ATTENDEES | MN ATTENDEES
Complete | Functional | Project Kick-Off Meeting | Face-to-Face & WebEx | BSC - MA | 2014-07-23 | 2014-07-23 | 2 hrs | 11:00 | 12:30 | John Adam, Sam Adams | Sally Smith, Tim Adams (Remote)

## Communiction (hidden)
MEETING | PURPOSE | WHEN | HOW | TIME | DURATION | ATTENDEES - CUSTOMER | ATTENDEES - MODEL N | INPUT | OUTPUT (Model N)
MODEL N - INTERNAL WEEKLY STATUS | Weekly review of project schedule, deliverables status, project risks/issues and action items as input into BSC meeting | Tuesdays | WEBEX / CONFERENCE CALL | 9:00 AM EST | 1 hour | N/A | John Smith, Todd Jones, Sally Sams | Project Status, Deliverable Tracker | Updated Project Status, Updated Deliverable Tracker

## CCR Summary (hidden)
CCR ID | Status | Description / Impact | Total Effort (Hrs) | Est. Cost | Approval Date

## Lessons Learned (hidden)
ID # | Date Rasied | Phase | Product Area | Methodology Type | Model N Version Number | Area - Process to Review | Identified by: | Describe Issue or Best Practice | Reccommneded Action
Model N Lessons Learned should be logged here