## Method Task Scope
Instructions:
1. Review and update the task scope for your project. Mark the 'In Scope' column as 'Yes' or 'No' to indicate the scope for the task.
2. Note: Column 'G' indicates if the task is estimated. All tasks that are estimated have been defaulted to 'In Scope'.
3. Other tasks that have been defaulted to 'In scope' and should be reviewed carefully before taking 'Out of Scope'.
4. The task information can be sorted and filtered by discipline and/or sub-discipline to help assign ownership.
5. Upon completing the 'Method Scope Template' the scope information needs to be transferred into the PEPS application for your estimate.
Phase ID | Discipline | Sub-Discipline | Task ID | WBS ID | Task Name | Estimated | In Scope
1 - Project Preparation | Project Management | Plan | 01000 | 1.PM.PL.01000 | Develop Project Charter | No | Yes
1 - Project Preparation | Project Management | Plan | 00001 | 1.PM.PL.00001 | Scheduling Milestones | No | No
1 - Project Preparation | Project Management | Plan | 01032 | 1.PM.PL.01032 | Establish Budget | No | Yes
1 - Project Preparation | Project Management | Plan | 01002 | 1.PM.PL.01002 | Develop Project Management Plan | No | Yes
1 - Project Preparation | Project Management | Plan | 01015 | 1.PM.PL.01015 | Develop Master Plan | No | Yes
1 - Project Preparation | Project Management | Plan | 01035 | 1.PM.PL.01035 | Develop Work Plan | No | Yes
1 - Project Preparation | Project Management | Plan | 01038 | 1.PM.PL.01038 | Complete Deliverables Log | No | Yes
1 - Project Preparation | Project Management | Plan | 02689 | 1.PM.PL.02689 | Develop Project Tools Strategy | No | Yes
1 - Project Preparation | Project Management | Plan | 01033 | 1.PM.PL.01033 | Install and Configure Tools | No | Yes
1 - Project Preparation | Project Management | Manage | 00003 | 1.PM.MG.00003 | Fixed Headcount | Yes | Yes
1 - Project Preparation | Project Management | Manage | 01084 | 1.PM.MG.01084 | Develop Project Team | No | Yes
1 - Project Preparation | Quality Management | Quality Planning | 01058 | 1.QM.QP.01058 | Develop Quality Management Plan | No | Yes
1 - Project Preparation | Quality Management | Quality Planning | 01062 | 1.QM.QP.01062 | Establish Project Document Management | No | Yes
1 - Project Preparation | Process and Application | Business Process Management | 01198 | 1.PP.BP.01198 | Develop Process Vision | No | No
1 - Project Preparation | Process and Application | Business Process Management | 01193 | 1.PP.BP.01193 | Develop Process Scope Statement | No | No
1 - Project Preparation | Process and Application | Package Configuration | 01233 | 1.PP.PK.01233 | Develop Package Functional Scope Statement | No | No
1 - Project Preparation | Process and Application | Package Configuration | 01232 | 1.PP.PK.01232 | Define ERP Project Applications Scope Statement | No | No
1 - Project Preparation | Process and Application | Business Process Controls | 01266 | 1.PP.PC.01266 | Assess Security and Controls Risk | No | No
1 - Project Preparation | Process and Application | Business Process Controls | 01263 | 1.PP.PC.01263 | Determine Security and Controls Strategy | No | No
1 - Project Preparation | Process and Application | Business Process Controls | 01267 | 1.PP.PC.01267 | Determine Security and Controls Tools | No | No
1 - Project Preparation | Process and Application | Business Process Controls | 01286 | 1.PP.PC.01286 | Develop Security and Controls Transition Approach | No | Yes
1 - Project Preparation | Organizational Change Management | Change Preparation | 02724 | 1.CM.CP.02724 | Develop Organizational Change Management Strategy | No | Yes
1 - Project Preparation | Organizational Change Management | Change Preparation | 02727 | 1.CM.CP.02727 | Conduct Stakeholder Assessment | No | Yes
1 - Project Preparation | Organizational Change Management | Communications | 02736 | 1.CM.CO.02736 | Conduct Communications Assessments | No | Yes
1 - Project Preparation | Information Management | Information Governance | 01377 | 1.IM.GO.01377 | Update Information Governance Organization Assessment | No | No
1 - Project Preparation | Information Management | Information Governance | 01378 | 1.IM.GO.01378 | Assess Information Governance Policies and Procedures | No | No
1 - Project Preparation | Information Management | Information Governance | 01380 | 1.IM.GO.01380 | Evaluate Information Governance Skill Set | No | No
1 - Project Preparation | Information Management | Information Governance | 01382 | 1.IM.GO.01382 | Define Information Governance Requirements | No | No
1 - Project Preparation | Information Management | Information Governance | 01383 | 1.IM.GO.01383 | Define Information Governance Organization Scope | No | No
1 - Project Preparation | Information Management | Information Governance | 01384 | 1.IM.GO.01384 | Define Information Governance Policies Scope | No | No
1 - Project Preparation | Information Management | Information Strategy & Architecture | 01404 | 1.IM.SA.01404 | Verify Client Business Intelligence Strategy | No | No
1 - Project Preparation | Information Management | Information Strategy & Architecture | 01412 | 1.IM.SA.01412 | Assess Enterprise Data Environment | No | No
1 - Project Preparation | Information Management | Information Strategy & Architecture | 01413 | 1.IM.SA.01413 | Define Enterprise Data Scope | No | No
1 - Project Preparation | Information Management | Information Strategy & Architecture | 01416 | 1.IM.SA.01416 | Define Enterprise Data Business Requirements | No | No
1 - Project Preparation | Information Management | Information Strategy & Architecture | 01435 | 1.IM.SA.01435 | Develop Enterprise Data Architecture | No | No
1 - Project Preparation | Information Management | Data Protection & Privacy | 01494 | 1.IM.PP.01494 | Develop Privacy and Data Protection Project Work Plan | No | No
1 - Project Preparation | Information Management | Data Protection & Privacy | 01379 | 1.IM.PP.01379 | Identify Enterprise Information Compliance Requirements | No | No
1 - Project Preparation | Information Management | Master Data Management | 01501 | 1.IM.MD.01501 | Assess Enterprise Data Objects | No | No
1 - Project Preparation | Information Management | Business Intelligence & Data Warehousing | 01566 | 1.IM.BI.01566 | Identify Business Intelligence Key Performance Indicators | No | No
1 - Project Preparation | Information Management | Business Intelligence & Data Warehousing | 01567 | 1.IM.BI.01567 | Identify Preliminary Business Intelligence Scope Components | No | No
1 - Project Preparation | Information Management | Business Intelligence & Data Warehousing | 01569 | 1.IM.BI.01569 | Assess Business Intelligence Applications Landscape | No | No
1 - Project Preparation | Information Management | Business Intelligence & Data Warehousing | 01570 | 1.IM.BI.01570 | Analyze Business Intelligence Front-End Tools | No | No
1 - Project Preparation | Information Management | Business Intelligence & Data Warehousing | 01572 | 1.IM.BI.01572 | Identify Business Intelligence Performance Targets | No | No
1 - Project Preparation | Information Management | Business Intelligence & Data Warehousing | 01573 | 1.IM.BI.01573 | Define Business Intelligence Critical Success Factors | No | No
1 - Project Preparation | Information Management | Information Quality | 01779 | 1.IM.IQ.01779 | Identify Critical Data Sources | No | No
1 - Project Preparation | Development | Application Development | 01811 | 1.DV.AD.01811 | Develop Data Conversion Scope and Strategy | No | No
1 - Project Preparation | Development | Application Landscape | 01993 | 1.DV.LN.01993 | Develop As-Is Applications Inventory | No | No
1 - Project Preparation | Development | Application Landscape | 01998 | 1.DV.LN.01998 | Document As-Is Application Landscape | No | No
1 - Project Preparation | Technology | Logical Infrastructure | 02014 | 1.TE.LI.02014 | Define Technical Infrastructure Scope and Strategy | No | No
1 - Project Preparation | Technology | Logical Infrastructure | 02020 | 1.TE.LI.02020 | Define To-Be High-Level Conceptual Landscape | No | No
1 - Project Preparation | Technology | Logical Infrastructure | 02034 | 1.TE.LI.02034 | Develop Technical Infrastructure Work Plan | No | No
1 - Project Preparation | Technology | Logical Infrastructure | 02044 | 1.TE.LI.02044 | Estimate Non-Production Hardware Sizing | No | No
1 - Project Preparation | Technology | Physical Infrastructure | 02060 | 1.TE.PI.02060 | Develop As-Is Integrations Inventory | No | No
1 - Project Preparation | Technology | Physical Infrastructure | 02062 | 1.TE.PI.02062 | Inventory As-Is Hardware Infrastructure | No | No
1 - Project Preparation | Technology | Physical Infrastructure | 02063 | 1.TE.PI.02063 | Inventory As-Is Network Infrastructure | No | No
1 - Project Preparation | Technology | Physical Infrastructure | 02064 | 1.TE.PI.02064 | Procure and Build Application Sandbox | No | No
1 - Project Preparation | Technology | Physical Infrastructure | 02067 | 1.TE.PI.02067 | Develop Third-Party Tools Request for Proposal and Request for Quote | No | No
1 - Project Preparation | Technology | Physical Infrastructure | 02068 | 1.TE.PI.02068 | Procure Third-Party Tools | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02108 | 1.TE.ID.02108 | Develop Identity and Access Management Vision Document | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02109 | 1.TE.ID.02109 | Assess Identity and Access Management Current Environment | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02110 | 1.TE.ID.02110 | Define Identity and Access Management Conceptual Architecture | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02111 | 1.TE.ID.02111 | Define Identity and Access Management Stakeholder Interactions | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02112 | 1.TE.ID.02112 | Develop Identity and Access Management Scope Statement | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02113 | 1.TE.ID.02113 | Develop Identity and Access Management Work Plan | No | No
1 - Project Preparation | Technology | Identity & Access Management | 02114 | 1.TE.ID.02114 | Develop User Data Clean-up Plan | No | No
1 - Project Preparation | Deployment | Business Deployment | 02294 | 1.DP.BD.02294 | Develop Geographic Scope Statement | No | No
1 - Project Preparation | Deployment | Business Deployment | 02295 | 1.DP.BD.02295 | Develop Organization Scope Statement | No | No
1 - Project Preparation | Deployment | Business Deployment | 02296 | 1.DP.BD.02296 | Define Deployment Strategy | No | No
1 - Project Preparation | Deployment | Business Deployment | 02297 | 1.DP.BD.02297 | Develop Deployment Plan | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02310 | 1.DP.SU.02310 | Define Support Scope | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02321 | 1.DP.SU.02321 | Determine Support Requirements | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02319 | 1.DP.SU.02319 | Define Support Approach | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02311 | 1.DP.SU.02311 | Analyze Support Organization | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02312 | 1.DP.SU.02312 | Assess Technical Governance and Support Service Level Agreements | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02313 | 1.DP.SU.02313 | Assess Support Organization Technology | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02316 | 1.DP.SU.02316 | Develop Support Organization Scope Statement | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02318 | 1.DP.SU.02318 | Develop Support Organization Plan | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02387 | 1.DP.SU.02387 | Identify Third-Party Support Resources | No | No
1 - Project Preparation | Deployment | Support Preparation & Stabilization | 02690 | 1.DP.SU.02690 | Prepare Strategy for Service Oriented Architecture | No | Yes
1 - Project Preparation | Tax | Tax | 02449 | 1.TX.TX.02449 | Define Tax Solution Scope Statement | No | No
1 - Project Preparation | Tax | Tax | 02450 | 1.TX.TX.02450 | Submit Tax Solution Information Request | No | No
1 - Project Preparation | Tax | Tax | 02451 | 1.TX.TX.02451 | Plan Tax Solution Kickoff | No | No
1 - Project Preparation | Tax | Tax | 02452 | 1.TX.TX.02452 | Schedule Tax Solution Workshops | No | No
1 - Project Preparation | Tax | Tax | 02453 | 1.TX.TX.02453 | Conduct Tax Solution Workshops | No | No
1 - Project Preparation | Tax | Tax | 02454 | 1.TX.TX.02454 | Identify Tax Solution Opportunities | No | No
1 - Project Preparation | Tax | Tax | 02455 | 1.TX.TX.02455 | Evaluate Tax Solution Software | No | No
1 - Project Preparation | Tax | Tax | 02456 | 1.TX.TX.02456 | Develop Tax Solution Work Plan | No | No
1 - Project Preparation | Tax | Tax | 02457 | 1.TX.TX.02457 | Develop Tax Solution Issues Log | No | No
1 - Project Preparation | Tax | Tax | 02458 | 1.TX.TX.02458 | Develop Tax Solution Status Report | No | No
1 - Project Preparation | Tax | Tax | 02459 | 1.TX.TX.02459 | Develop Tax Solution Learning Strategy | No | No
1 - Project Preparation | Tax | Tax | 02460 | 1.TX.TX.02460 | Develop Tax Solution Test Strategy | No | No
1 - Project Preparation | Value | Value | 02474 | 1.VL.VL.02474 | Understand Client's Industry Environment | No | No
1 - Project Preparation | Value | Value | 02475 | 1.VL.VL.02475 | Determine Client's Key Strategy Elements | No | No
1 - Project Preparation | Value | Value | 02476 | 1.VL.VL.02476 | Conduct Value Performance Benchmarking Analysis | No | No
1 - Project Preparation | Value | Value | 02477 | 1.VL.VL.02477 | Summarize Value Performance Benchmarking Analysis | No | No
1 - Project Preparation | Value | Value | 02478 | 1.VL.VL.02478 | Assess Client Position | No | No
1 - Project Preparation | Value | Value | 02480 | 1.VL.VL.02480 | Identify Performance Improvement Targets | No | No
1 - Project Preparation | Value | Value | 02481 | 1.VL.VL.02481 | Define Value Goals | No | No
1 - Project Preparation | Value | Value | 02482 | 1.VL.VL.02482 | Define Value Approach | No | No
1 - Project Preparation | Value | Value | 02483 | 1.VL.VL.02483 | Develop Value Assessment Plan | No | No
1 - Project Preparation | Value | Value | 02484 | 1.VL.VL.02484 | Conduct Value Opportunities Assessment | No | No
1 - Project Preparation | Value | Value | 02490 | 1.VL.VL.02490 | Summarize Value Opportunities Assessment | No | No
1 - Project Preparation | Value | Value | 02493 | 1.VL.VL.02493 | Develop Business Case Scope Statement | No | No
1 - Project Preparation | Value | Value | 02495 | 1.VL.VL.02495 | Develop Business Case Work Plan | No | No
1 - Project Preparation | Value | Value | 02497 | 1.VL.VL.02497 | Develop Total Cost of Ownership Estimate | No | No
1 - Project Preparation | Value | Value | 02499 | 1.VL.VL.02499 | Develop ValuePlan | No | No
1 - Project Preparation | Value | Value | 02498 | 1.VL.VL.02498 | Conduct Business Case Financial Analysis | No | No
1 - Project Preparation | Value | Value | 02500 | 1.VL.VL.02500 | Prepare Business Case | No | No
2 - Blueprint | Project Management | Plan | 00001 | 2.PM.PL.00001 | Scheduling Milestones | No | No
2 - Blueprint | Project Management | Plan | 01035 | 2.PM.PL.01035 | Develop Work Plan | No | Yes
2 - Blueprint | Project Management | Plan | 01038 | 2.PM.PL.01038 | Complete Deliverables Log | No | Yes
2 - Blueprint | Project Management | Plan | 01033 | 2.PM.PL.01033 | Install and Configure Tools | No | Yes
2 - Blueprint | Project Management | Manage | 00003 | 2.PM.MG.00003 | Fixed Headcount | Yes | Yes
2 - Blueprint | Project Management | Manage | 01084 | 2.PM.MG.01084 | Develop Project Team | No | Yes
2 - Blueprint | Process and Application | Business Process Management | 01199 | 2.PP.BP.01199 | Define Business Requirements | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01200 | 2.PP.BP.01200 | Analyze As-Is Processes | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01205 | 2.PP.BP.01205 | Design To-Be Process Groups (L1) | No | Yes
2 - Blueprint | Process and Application | Business Process Management | 01206 | 2.PP.BP.01206 | Identify Business Scenarios | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01214 | 2.PP.BP.01214 | Design To-Be Processes (L2) | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01215 | 2.PP.BP.01215 | Design To-Be SubProcesses (L3) | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01217 | 2.PP.BP.01217 | Define Business Roles | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01207 | 2.PP.BP.01207 | Develop To-Be Business Scenarios | No | No
2 - Blueprint | Process and Application | Business Process Management | 00037 | 2.PP.BP.00037 | Develop Time Design | Yes | Yes
2 - Blueprint | Process and Application | Business Process Management | 01221 | 2.PP.BP.01221 | Develop String Test Approach | No | No
2 - Blueprint | Process and Application | Package Configuration | 01239 | 2.PP.PK.01239 | Develop Enterprise Structure | Yes | Yes
2 - Blueprint | Process and Application | Package Configuration | 01238 | 2.PP.PK.01238 | Conduct Software Gap Analysis | Yes | Yes
2 - Blueprint | Process and Application | Package Configuration | 01245 | 2.PP.PK.01245 | Develop Software Control Values | Yes | Yes
2 - Blueprint | Process and Application | Package Configuration | 01252 | 2.PP.PK.01252 | Develop Configuration Unit Test Approach | No | No
2 - Blueprint | Process and Application | Package Configuration | 01244 | 2.PP.PK.01244 | Develop Software Configuration Design | Yes | Yes
2 - Blueprint | Process and Application | Package Configuration | 00162 | 2.PP.PK.00162 | Develop Payroll Design | Yes | Yes
2 - Blueprint | Process and Application | Package Configuration | 00163 | 2.PP.PK.00163 | Configure Sandbox | Yes | Yes
2 - Blueprint | Process and Application | Business Process Controls | 01276 | 2.PP.PC.01276 | Design Business Process Control Framework | Yes | Yes
2 - Blueprint | Process and Application | Business Process Controls | 01272 | 2.PP.PC.01272 | Develop Business Process Control Strategy | No | No
2 - Blueprint | Process and Application | Business Process Controls | 01277 | 2.PP.PC.01277 | Define Segregation of Duties and Critical Access | Yes | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02725 | 2.CM.CP.02725 | Develop Change Readiness Assessment Approach | No | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02706 | 2.CM.CP.02706 | Conduct Initial Change Readiness Assessment | Yes | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02726 | 2.CM.CP.02726 | Develop Stakeholder Engagement Approach | Yes | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02705 | 2.CM.CP.02705 | Conduct Leadership Interviews | No | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02728 | 2.CM.CP.02728 | Brief Leadership | No | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02718 | 2.CM.CP.02718 | Prepare Subject Matter Experts for Business Blueprint | Yes | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02713 | 2.CM.CP.02713 | Develop Change Network Approach | Yes | Yes
2 - Blueprint | Organizational Change Management | Change Preparation | 02714 | 2.CM.CP.02714 | Launch Change Network | Yes | Yes
2 - Blueprint | Organizational Change Management | Organizational Alignment | 02764 | 2.CM.OA.02764 | Develop Change Impact Assessment Approach | No | Yes
2 - Blueprint | Organizational Change Management | Organizational Alignment | 02761 | 2.CM.OA.02761 | Assess Initial Change Impacts | Yes | Yes
2 - Blueprint | Organizational Change Management | Organizational Alignment | 02767 | 2.CM.OA.02767 | Develop Role-to-Position Mapping Approach | Yes | Yes
2 - Blueprint | Organizational Change Management | Communications | 02733 | 2.CM.CO.02733 | Develop Communications Approach | No | Yes
2 - Blueprint | Organizational Change Management | Communications | 02734 | 2.CM.CO.02734 | Develop Communications Plan | No | Yes
2 - Blueprint | Organizational Change Management | Communications | 02735 | 2.CM.CO.02735 | Establish Communications Website | No | Yes
2 - Blueprint | Organizational Change Management | Communications | 02729 | 2.CM.CO.02729 | Develop and Deliver Communications for Business Blueprint | No | Yes
2 - Blueprint | Organizational Change Management | Capability Transfer | 02703 | 2.CM.CT.02703 | Develop Project Team Member Capability Transfer Plans | Yes | Yes
2 - Blueprint | Organizational Change Management | Capability Transfer | 02701 | 2.CM.CT.02701 | Initiate Project Team Capability Transfer | Yes | Yes
2 - Blueprint | Organizational Change Management | Capability Transfer | 02702 | 2.CM.CT.02702 | Develop Project Team Capability Transfer Approach | No | Yes
2 - Blueprint | Organizational Change Management | End-User Training | 02743 | 2.CM.TR.02743 | Develop End-User Training Curriculum | No | Yes
2 - Blueprint | Organizational Change Management | End-User Training | 02756 | 2.CM.TR.02756 | Conduct End-User Training Assessments | No | Yes
2 - Blueprint | Organizational Change Management | End-User Training | 02744 | 2.CM.TR.02744 | Develop End-User Training Approach | No | Yes
2 - Blueprint | Organizational Change Management | End-User Training | 02741 | 2.CM.TR.02741 | Define Courseware Development Standards | No | Yes
2 - Blueprint | Organizational Change Management | End-User Training | 02758 | 2.CM.TR.02758 | Develop Trainer Preparation Plan | No | Yes
2 - Blueprint | Information Management | Information Governance | 01389 | 2.IM.GO.01389 | Define Information Governance Organization Structure | No | No
2 - Blueprint | Information Management | Information Governance | 01390 | 2.IM.GO.01390 | Define Information Governance Organization Roles and Responsibilities | No | No
2 - Blueprint | Information Management | Information Governance | 01391 | 2.IM.GO.01391 | Assess Information Governance Organization Impact | No | No
2 - Blueprint | Information Management | Information Strategy & Architecture | 01442 | 2.IM.SA.01442 | Define Business Intelligence Data Modeling Standards and Guiding Principles | No | No
2 - Blueprint | Information Management | Information Strategy & Architecture | 01450 | 2.IM.SA.01450 | Develop Logical Data Model | No | No
2 - Blueprint | Information Management | Information Strategy & Architecture | 01438 | 2.IM.SA.01438 | Design Data Architecture | No | No
2 - Blueprint | Information Management | Information Strategy & Architecture | 01452 | 2.IM.SA.01452 | Develop Physical Data Model | No | No
2 - Blueprint | Information Management | Information Strategy & Architecture | 01439 | 2.IM.SA.01439 | Develop Data Sourcing Approach | No | No
2 - Blueprint | Information Management | Information Strategy & Architecture | 01441 | 2.IM.SA.01441 | Design Logical Data Flow | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01493 | 2.IM.PP.01493 | Identify Privacy and Data Protection Requirements | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01484 | 2.IM.PP.01484 | Populate Privacy and Data Protection Requirements Framework | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01483 | 2.IM.PP.01483 | Develop Privacy and Data Protection Rationalized Requirements | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01490 | 2.IM.PP.01490 | Review Privacy and Data Protection Requirements Framework | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01489 | 2.IM.PP.01489 | Approve Rationalized Privacy Requirements | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01491 | 2.IM.PP.01491 | Develop Privacy and Data Protection Requirements Analysis Framework | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01497 | 2.IM.PP.01497 | Prepare Privacy and Data Protection Requirements Analysis Questionnaire | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01487 | 2.IM.PP.01487 | Conduct Privacy and Data Protection Requirements Analysis Interview Sessions | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01473 | 2.IM.PP.01473 | Conduct Privacy and Data Protection Gap Analysis | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01476 | 2.IM.PP.01476 | Perform Privacy and Data Protection Data Flow Mapping | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01480 | 2.IM.PP.01480 | Identify Privacy and Data Protection Recommendations | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01492 | 2.IM.PP.01492 | Develop Privacy and Data Protection Gap Scoring | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01472 | 2.IM.PP.01472 | Score Privacy and Data Protection Gaps | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01471 | 2.IM.PP.01471 | Design Privacy and Data Protection Control Objectives | No | No
2 - Blueprint | Information Management | Data Protection & Privacy | 01486 | 2.IM.PP.01486 | Design Privacy and Data Protection Control Activities | No | No
2 - Blueprint | Information Management | Master Data Management | 01521 | 2.IM.MD.01521 | Develop To-Be Master Data Design | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 00010 | 2.IM.BI.00010 | Develop Dimensional Data Model | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01605 | 2.IM.BI.01605 | Develop Business Intelligence Conference Room Pilot Prototype | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01606 | 2.IM.BI.01606 | Conduct Business Intelligence Conference Room Pilot | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01537 | 2.IM.BI.01537 | Define Business Intelligence Vision and Guiding Principles | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01540 | 2.IM.BI.01540 | Define Business Intelligence Project Scope Statement | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 00168 | 2.IM.BI.00168 | High Level Architecture Design - By Complexity | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 00167 | 2.IM.BI.00167 | Logical Data Model Design - By Complexity | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01542 | 2.IM.BI.01542 | Define Business Intelligence Applications Landscape | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01545 | 2.IM.BI.01545 | Define Business Intelligence Legacy System Decommissioning Strategy | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01548 | 2.IM.BI.01548 | Plan Business Intelligence Front-End Tool Usage | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01552 | 2.IM.BI.01552 | Define High-Level Business Intelligence Security Strategy | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01586 | 2.IM.BI.01586 | Assess Scorecard and Dashboard Capabilities | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 00169 | 2.IM.BI.00169 | Define To-Be Requirements List | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01590 | 2.IM.BI.01590 | Assess Analytics Reporting Capabilities | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01592 | 2.IM.BI.01592 | Assess Operational Reporting Capabilities | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01595 | 2.IM.BI.01595 | Assess Management and External Reporting Capabilities | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01535 | 2.IM.BI.01535 | Assess Data Mining Capabilities | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01578 | 2.IM.BI.01578 | Define Scorecard and Dashboard Requirements | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01600 | 2.IM.BI.01600 | Define Analytics Reporting Requirements | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01582 | 2.IM.BI.01582 | Define Operational Reporting Requirements | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01583 | 2.IM.BI.01583 | Define Management and External Reporting Requirements | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01538 | 2.IM.BI.01538 | Define Data Mining Requirements | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01613 | 2.IM.BI.01613 | Define Data Extraction and Transformation Standards and Guiding Principles | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01615 | 2.IM.BI.01615 | Define Business Intelligence Master Data and Hierarchy Standards and Guiding Principles | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01618 | 2.IM.BI.01618 | Define Reporting Standards and Guiding Principles | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01621 | 2.IM.BI.01621 | Define InfoObject Standards | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01623 | 2.IM.BI.01623 | Define Business Intelligence Naming Standards and Conventions | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01609 | 2.IM.BI.01609 | Template and Report Functional Specifications | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 00056 | 2.IM.BI.00056 | Develop Scorecard and Dashboard Functional Specifications | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01612 | 2.IM.BI.01612 | Develop Analytics Reporting Functional Specifications | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01610 | 2.IM.BI.01610 | Develop Operational Reporting Functional Specifications | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01611 | 2.IM.BI.01611 | Develop Management and External Reporting Functional Specifications | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01547 | 2.IM.BI.01547 | Develop Data Mining Functional Specifications | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01625 | 2.IM.BI.01625 | Report Technical Specifications | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 00057 | 2.IM.BI.00057 | Develop Scorecard and Dashboard Development Standards | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01627 | 2.IM.BI.01627 | Develop Technical Specifications (Scorecard and Dashboard) | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01571 | 2.IM.BI.01571 | Develop Scorecard and Dashboard Unit Test Plan | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01601 | 2.IM.BI.01601 | Develop Scorecard and Dashboard Unit Test Cases | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01628 | 2.IM.BI.01628 | Develop Analytics Development Standards | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01629 | 2.IM.BI.01629 | Develop Analytics Solution Technical Design | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01574 | 2.IM.BI.01574 | Develop Analytics Unit Test Plan | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01602 | 2.IM.BI.01602 | Develop Analytics Unit Test Cases | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01630 | 2.IM.BI.01630 | Develop Operational Reporting Development Standards | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01632 | 2.IM.BI.01632 | Develop Operational Reporting Technical Design | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01576 | 2.IM.BI.01576 | Develop Operational Reporting Unit Test Plan | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01603 | 2.IM.BI.01603 | Develop Operational Reporting Unit Test Cases | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01634 | 2.IM.BI.01634 | Develop Management and External Reporting Development Standards | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01635 | 2.IM.BI.01635 | Develop Technical Specifications (Management and External Reporting) | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01563 | 2.IM.BI.01563 | Develop Management and External Reporting Unit Test Plan | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01579 | 2.IM.BI.01579 | Develop Management and External Reporting Unit Test Cases | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01557 | 2.IM.BI.01557 | Develop Data Mining Development Standards | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01559 | 2.IM.BI.01559 | Develop Technical Specifications (Data Mining) | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01568 | 2.IM.BI.01568 | Develop Data Mining Unit Test Plan | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01581 | 2.IM.BI.01581 | Develop Data Mining Unit Test Cases | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01555 | 2.IM.BI.01555 | Business Content Gap Analysis | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01558 | 2.IM.BI.01558 | Identify Business Intelligence Development Objects | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01587 | 2.IM.BI.01587 | Develop Data Extraction Functional Specifications | Yes | Yes
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01549 | 2.IM.BI.01549 | Develop Business Intelligence Data Conversion Specifications | No | No
2 - Blueprint | Information Management | Business Intelligence & Data Warehousing | 01550 | 2.IM.BI.01550 | Develop Business Intelligence Interface Specifications | No | No
2 - Blueprint | Information Management | Metadata Management | 01744 | 2.IM.ME.01744 | Define Business Intelligence Metadata Standards | No | No
2 - Blueprint | Information Management | Metadata Management | 01745 | 2.IM.ME.01745 | Develop Metadata Glossary | No | No
2 - Blueprint | Information Management | Information Quality | 01767 | 2.IM.IQ.01767 | Define Data and Content Quality Standards | No | No
2 - Blueprint | Information Management | Information Quality | 01768 | 2.IM.IQ.01768 | Develop Data and Content Quality Approach | No | No
2 - Blueprint | Information Management | Information Quality | 01769 | 2.IM.IQ.01769 | Define Data and Content Validation Requirements | No | No
2 - Blueprint | Information Management | Information Quality | 01771 | 2.IM.IQ.01771 | Evaluate Third-Party Data and Content Providers | No | No
2 - Blueprint | Information Management | Information Quality | 01789 | 2.IM.IQ.01789 | Perform Legacy Data Analysis | Yes | Yes
2 - Blueprint | Information Management | Information Quality | 01793 | 2.IM.IQ.01793 | Develop Data Cleanup Approach | No | No
2 - Blueprint | Information Management | Information Quality | 01795 | 2.IM.IQ.01795 | Develop Data Cleanup and Migration Work Plan | Yes | Yes
2 - Blueprint | Information Management | Information Quality | 01772 | 2.IM.IQ.01772 | Develop Data Cleansing Approach | Yes | Yes
2 - Blueprint | Development | Application Development | 01881 | 2.DV.AD.01881 | Define Software Development Standards and Guidelines | Yes | Yes
2 - Blueprint | Development | Application Development | 01812 | 2.DV.AD.01812 | Develop Software Development Scope | No | No
2 - Blueprint | Development | Application Development | 01877 | 2.DV.AD.01877 | Develop Software Development Strategy | No | No
2 - Blueprint | Development | Application Development | 01878 | 2.DV.AD.01878 | Define Software Development Approach | No | No
2 - Blueprint | Development | Application Development | 01875 | 2.DV.AD.01875 | Define Integration Component Test Procedures | No | No
2 - Blueprint | Development | Application Development | 01884 | 2.DV.AD.01884 | Define Integration Exception and Error-Handling Mechanism | No | No
2 - Blueprint | Development | Application Development | 01816 | 2.DV.AD.01816 | Develop Outbound Interface Requirements | No | No
2 - Blueprint | Development | Application Development | 01825 | 2.DV.AD.01825 | Develop Data Organization Approach | No | No
2 - Blueprint | Development | Application Development | 01826 | 2.DV.AD.01826 | Develop Functional Specifications (Enhancement) | Yes | Yes
2 - Blueprint | Development | Application Development | 00061 | 2.DV.AD.00061 | Develop Functional Specifications (Forms) | Yes | Yes
2 - Blueprint | Development | Application Development | 01827 | 2.DV.AD.01827 | Develop Functional Specifications (Workflow) | Yes | Yes
2 - Blueprint | Development | Application Development | 01822 | 2.DV.AD.01822 | Develop Functional Specifications (Report) | Yes | Yes
2 - Blueprint | Development | Application Development | 00063 | 2.DV.AD.00063 | Develop Functional Specifications (Point-to-Point Interface) | Yes | Yes
2 - Blueprint | Development | Application Development | 00062 | 2.DV.AD.00062 | Develop Functional Specifications (Middleware Interface) | Yes | Yes
2 - Blueprint | Development | Application Development | 00064 | 2.DV.AD.00064 | Develop Functional Specifications (EDI) | Yes | Yes
2 - Blueprint | Development | Application Development | 01824 | 2.DV.AD.01824 | Develop Functional Specifications (Conversion) | Yes | Yes
2 - Blueprint | Development | Application Development | 01829 | 2.DV.AD.01829 | Develop To-Be Data Field Map | No | No
2 - Blueprint | Development | Portal Development | 00008 | 2.DV.PO.00008 | Install Business Packages (out-of-the-box) | Yes | Yes
2 - Blueprint | Development | Portal Development | 00161 | 2.DV.PO.00161 | Define Service Level Objectives | Yes | Yes
2 - Blueprint | Development | Portal Development | 01937 | 2.DV.PO.01937 | Develop Portal Requirements | Yes | Yes
2 - Blueprint | Development | Portal Development | 01939 | 2.DV.PO.01939 | Develop Portal Strategy and Roadmap | Yes | Yes
2 - Blueprint | Development | Portal Development | 01942 | 2.DV.PO.01942 | Develop Portal Solution Technical Design | Yes | Yes
2 - Blueprint | Development | Portal Development | 00159 | 2.DV.PO.00159 | Develop Portal Infrastructure Design | Yes | Yes
2 - Blueprint | Development | Portal Development | 01943 | 2.DV.PO.01943 | Design Portal Business Package | Yes | Yes
2 - Blueprint | Development | Portal Development | 00156 | 2.DV.PO.00156 | Build Portal Sandbox | Yes | Yes
2 - Blueprint | Development | Portal Development | 01944 | 2.DV.PO.01944 | Develop Portal Content Design and Migration Plan | No | No
2 - Blueprint | Development | Portal Development | 01946 | 2.DV.PO.01946 | Design Portal User Experience | Yes | Yes
2 - Blueprint | Development | Legacy System Development | 00164 | 2.DV.LS.00164 | Identify Legacy System Modifications | Yes | Yes
2 - Blueprint | Development | Application Landscape | 02041 | 2.DV.LN.02041 | Finalize Application Landscape | No | No
2 - Blueprint | Development | Development Controls | 02005 | 2.DV.DC.02005 | Design Interface Control Framework | Yes | Yes
2 - Blueprint | Development | Development Controls | 02001 | 2.DV.DC.02001 | Develop Interface Control Strategy | Yes | Yes
2 - Blueprint | Development | Development Controls | 02006 | 2.DV.DC.02006 | Design Data Conversion Control Framework | Yes | Yes
2 - Blueprint | Development | Development Controls | 02008 | 2.DV.DC.02008 | Develop Data Conversion Control Strategy | Yes | Yes
2 - Blueprint | Technology | Logical Infrastructure | 02051 | 2.TE.LI.02051 | Estimate Production Hardware Sizing | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02025 | 2.TE.LI.02025 | Develop Instance and Landscape Strategy | Yes | Yes
2 - Blueprint | Technology | Logical Infrastructure | 02026 | 2.TE.LI.02026 | Develop Application Access Scope and Strategy | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02032 | 2.TE.LI.02032 | Develop SAP Infrastructure Strategy | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02027 | 2.TE.LI.02027 | Define Solution Manager Tool Decision Tree | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02016 | 2.TE.LI.02016 | Develop Technology Team Work Plan | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02029 | 2.TE.LI.02029 | Develop Transport Strategy and Approach | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02028 | 2.TE.LI.02028 | Develop SAP Infrastructure Documentation Templates | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02030 | 2.TE.LI.02030 | Define Infrastructure Management Procedures | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02031 | 2.TE.LI.02031 | Define Output Management Infrastructure Strategy | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02045 | 2.TE.LI.02045 | Design Non-Production Logical and Physical Architecture | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02049 | 2.TE.LI.02049 | Establish Production Application and Performance Volumetrics | No | No
2 - Blueprint | Technology | Logical Infrastructure | 02053 | 2.TE.LI.02053 | Design Production Logical Architecture | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02076 | 2.TE.PI.02076 | Build Non-Production Environments | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02069 | 2.TE.PI.02069 | Install Third-Party Tools | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02070 | 2.TE.PI.02070 | Configure Third-Party Tools | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02072 | 2.TE.PI.02072 | Develop Non-Production Hardware Request for Proposal and Request for Quote | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02073 | 2.TE.PI.02073 | Procure Non-Production Hardware | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02074 | 2.TE.PI.02074 | Procure Non-Production Database | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02075 | 2.TE.PI.02075 | Procure Non-Production Software | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02086 | 2.TE.PI.02086 | Develop Production Hardware Request for Proposal and Request for Quote | No | No
2 - Blueprint | Technology | Physical Infrastructure | 02089 | 2.TE.PI.02089 | Develop High-Availability Procedures and Test Strategy | No | No
2 - Blueprint | Technology | Technology Controls | 02099 | 2.TE.TC.02099 | Develop Information Technology Control Strategy | Yes | Yes
2 - Blueprint | Technology | Technology Controls | 02102 | 2.TE.TC.02102 | Design Information Technology Control Framework | Yes | Yes
2 - Blueprint | Technology | Identity & Access Management | 02117 | 2.TE.ID.02117 | Develop Identity and Access Management Solution Requirements Specification | No | No
2 - Blueprint | Technology | Identity & Access Management | 02118 | 2.TE.ID.02118 | Develop Identity and Access Management Solution Design Document | No | No
2 - Blueprint | Technology | Identity & Access Management | 02115 | 2.TE.ID.02115 | Configure Identity and Access Management Non-Production Environment | No | No
2 - Blueprint | Technology | Application Security | 02134 | 2.TE.SE.02134 | Define Non-Production Application Security Procedures | Yes | Yes
2 - Blueprint | Technology | Application Security | 02137 | 2.TE.SE.02137 | Define Non-Production Application Security and System Checklist | Yes | Yes
2 - Blueprint | Technology | Application Security | 02135 | 2.TE.SE.02135 | Configure Non-Production Application Security Environment | Yes | Yes
2 - Blueprint | Technology | Application Security | 02136 | 2.TE.SE.02136 | Design Non-Production Application Security Custom Objects | No | No
2 - Blueprint | Technology | Application Security | 02138 | 2.TE.SE.02138 | Support Non-Production Application Security Users and Roles | Yes | Yes
2 - Blueprint | Technology | Application Security | 02143 | 2.TE.SE.02143 | Develop Production Application Security Strategy | Yes | Yes
2 - Blueprint | Technology | Application Security | 02145 | 2.TE.SE.02145 | Define Production Application Security Architecture | Yes | Yes
2 - Blueprint | Technology | Application Security | 02169 | 2.TE.SE.02169 | Develop Production Application Security Test Approach | No | No
2 - Blueprint | Technology | Technology Operations | 02200 | 2.TE.OP.02200 | Establish Service Level Agreement | No | No
2 - Blueprint | Technology | Technology Operations | 02203 | 2.TE.OP.02203 | Define Backup and Restore Design Approach | No | No
2 - Blueprint | Technology | Technology Operations | 02206 | 2.TE.OP.02206 | Develop Patch Change Control Process | No | No
2 - Blueprint | Technology | Technology Operations | 02208 | 2.TE.OP.02208 | Develop Production Monitoring Procedures | No | No
2 - Blueprint | Technology | Infrastructure Testing | 02222 | 2.TE.TE.02222 | Define Backup and Restore Testing Approach | No | No
2 - Blueprint | Technology | Infrastructure Testing | 02230 | 2.TE.TE.02230 | Test Non-Production Environment Infrastructure | No | No
2 - Blueprint | Technology | Infrastructure Testing | 02231 | 2.TE.TE.02231 | Test Third-Party Tools | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02332 | 2.DP.SU.02332 | Identify System Topology | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02325 | 2.DP.SU.02325 | Define Support Logistics Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02324 | 2.DP.SU.02324 | Define Help Desk Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02326 | 2.DP.SU.02326 | Define Connectivity Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02327 | 2.DP.SU.02327 | Define Knowledge Landscape Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02328 | 2.DP.SU.02328 | Define Infrastructure Security Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02330 | 2.DP.SU.02330 | Define Telecommunications Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02333 | 2.DP.SU.02333 | Define Special Support Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02322 | 2.DP.SU.02322 | Define Support Organization Requirements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02334 | 2.DP.SU.02334 | Develop Support Organization Implementation Approach | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02375 | 2.DP.SU.02375 | Establish Vendor Management Process | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02336 | 2.DP.SU.02336 | Develop Technical Governance and Support Service Level Agreements Approach | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02317 | 2.DP.SU.02317 | Finalize Applications Scope and Solution | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02365 | 2.DP.SU.02365 | Document Applications Statement of Work | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02337 | 2.DP.SU.02337 | Develop Applications Delivery Model | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02360 | 2.DP.SU.02360 | Develop Applications Service Level Agreements | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02314 | 2.DP.SU.02314 | Conduct Applications Performance Gap Analysis | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02338 | 2.DP.SU.02338 | Develop Applications Staffing Model | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02367 | 2.DP.SU.02367 | Review Applications Solution | No | No
2 - Blueprint | Deployment | Support Preparation & Stabilization | 02319 | 2.DP.SU.02319 | Design Support Organization | Yes | Yes
2 - Blueprint | Deployment | Readiness Testing | 02408 | 2.DP.RE.02408 | Develop Test Management Plan | Yes | Yes
2 - Blueprint | Deployment | Readiness Testing | 02410 | 2.DP.RE.02410 | Develop Integration Test Approach | No | No
2 - Blueprint | Deployment | Readiness Testing | 02411 | 2.DP.RE.02411 | Develop User-Acceptance Test Approach | No | No
2 - Blueprint | Deployment | Readiness Testing | 02412 | 2.DP.RE.02412 | Develop Parallel Test Approach | No | No
2 - Blueprint | Deployment | Readiness Testing | 02443 | 2.DP.RE.02443 | Develop Regression Test Approach | No | No
2 - Blueprint | Tax | Tax | 02461 | 2.TX.TX.02461 | Define Tax Solution Business Requirements | No | No
2 - Blueprint | Tax | Tax | 02462 | 2.TX.TX.02462 | Define Tax Solution Functional Requirements | No | No
2 - Blueprint | Tax | Tax | 02463 | 2.TX.TX.02463 | Develop Functional Specifications (Tax Solution) | No | No
2 - Blueprint | Tax | Tax | 02464 | 2.TX.TX.02464 | Develop Tax Solution Business Processes and Procedures | No | No
2 - Blueprint | Tax | Tax | 02465 | 2.TX.TX.02465 | Plan Tax Solution Transition | No | No
2 - Blueprint | Tax | Tax | 02466 | 2.TX.TX.02466 | Develop Tax Solution Test Scenarios | No | No
2 - Blueprint | Tax | Tax | 02467 | 2.TX.TX.02467 | Refine Tax Solution Opportunities | No | No
2 - Blueprint | Value | Value | 00119 | 2.VL.VL.00119 | Update and Refresh Business Case | Yes | Yes
2 - Blueprint | Value | Value | 02510 | 2.VL.VL.02510 | Develop Value Delivery Approach | No | No
2 - Blueprint | Value | Value | 02511 | 2.VL.VL.02511 | Develop Value Delivery Goals by Organization | No | No
2 - Blueprint | Value | Value | 02515 | 2.VL.VL.02515 | Develop Value Tracking Plan | No | No
3a - Realization Build | Project Management | Plan | 00001 | 3a.PM.PL.00001 | Scheduling Milestones | No | No
3a - Realization Build | Project Management | Plan | 01035 | 3a.PM.PL.01035 | Develop Work Plan | No | Yes
3a - Realization Build | Project Management | Plan | 01038 | 3a.PM.PL.01038 | Complete Deliverables Log | No | Yes
3a - Realization Build | Project Management | Plan | 01033 | 3a.PM.PL.01033 | Install and Configure Tools | No | Yes
3a - Realization Build | Project Management | Manage | 00003 | 3a.PM.MG.00003 | Fixed Headcount | Yes | Yes
3a - Realization Build | Project Management | Manage | 01084 | 3a.PM.MG.01084 | Develop Project Team | No | Yes
3a - Realization Build | Process and Application | Business Process Management | 01203 | 3a.PP.BP.01203 | Identify Business Continuity Operation Team | No | No
3a - Realization Build | Process and Application | Business Process Management | 01201 | 3a.PP.BP.01201 | Identify Critical Business Functions and Processes | No | No
3a - Realization Build | Process and Application | Business Process Management | 01204 | 3a.PP.BP.01204 | Gather Business Continuity Requirements | No | No
3a - Realization Build | Process and Application | Business Process Management | 01202 | 3a.PP.BP.01202 | Determine Business Function Interruption Impacts | No | No
3a - Realization Build | Process and Application | Business Process Management | 01218 | 3a.PP.BP.01218 | Develop Business Function Interruption Response Plan | No | No
3a - Realization Build | Process and Application | Business Process Management | 01219 | 3a.PP.BP.01219 | Develop Business Function Restoration Plan | No | No
3a - Realization Build | Process and Application | Business Process Management | 01229 | 3a.PP.BP.01229 | Develop Business Process Procedures | Yes | Yes
3a - Realization Build | Process and Application | Business Process Management | 01223 | 3a.PP.BP.01223 | Develop String Test Plan | No | No
3a - Realization Build | Process and Application | Business Process Management | 01225 | 3a.PP.BP.01225 | Develop String Test Cases | Yes | Yes
3a - Realization Build | Process and Application | Business Process Management | 01227 | 3a.PP.BP.01227 | Prepare String Test Environment | No | No
3a - Realization Build | Process and Application | Business Process Management | 01228 | 3a.PP.BP.01228 | Prepare String Test Data | No | No
3a - Realization Build | Process and Application | Business Process Management | 01231 | 3a.PP.BP.01231 | Conduct String Test | Yes | Yes
3a - Realization Build | Process and Application | Business Process Management | 01216 | 3a.PP.BP.01216 | Develop Interim Business Procedures | Yes | Yes
3a - Realization Build | Process and Application | Package Configuration | 01254 | 3a.PP.PK.01254 | Develop Configuration Unit Test Plan | No | No
3a - Realization Build | Process and Application | Package Configuration | 01256 | 3a.PP.PK.01256 | Complete and Document Baseline Configuration | Yes | Yes
3a - Realization Build | Process and Application | Package Configuration | 01261 | 3a.PP.PK.01261 | Perform Final Configuration | Yes | Yes
3a - Realization Build | Process and Application | Package Configuration | 00039 | 3a.PP.PK.00039 | Perform Payroll Configuration | Yes | Yes
3a - Realization Build | Process and Application | Package Configuration | 00038 | 3a.PP.PK.00038 | Perform Time Configuration | Yes | Yes
3a - Realization Build | Process and Application | Package Configuration | 00040 | 3a.PP.PK.00040 | Perform HR Final Configuration | Yes | Yes
3a - Realization Build | Process and Application | Package Configuration | 01257 | 3a.PP.PK.01257 | Prepare and Conduct Configuration Unit Test | No | No
3a - Realization Build | Process and Application | Business Process Controls | 01279 | 3a.PP.PC.01279 | Develop Process Control Framework | Yes | Yes
3a - Realization Build | Process and Application | Business Process Controls | 00026 | 3a.PP.PC.00026 | Unit Test Process Control Activities | Yes | Yes
3a - Realization Build | Process and Application | Business Process Controls | 01280 | 3a.PP.PC.01280 | Develop Controls Test Trackers | Yes | Yes
3a - Realization Build | Organizational Change Management | Change Preparation | 02707 | 3a.CM.CP.02707 | Conduct Mid-Point Change Readiness Assessment | Yes | Yes
3a - Realization Build | Organizational Change Management | Change Preparation | 02710 | 3a.CM.CP.02710 | Develop Leadership Action Plans for Realization | No | Yes
3a - Realization Build | Organizational Change Management | Change Preparation | 02719 | 3a.CM.CP.02719 | Prepare Subject Matter Experts for Realization | Yes | Yes
3a - Realization Build | Organizational Change Management | Change Preparation | 02715 | 3a.CM.CP.02715 | Develop Change Network Action Plans | Yes | Yes
3a - Realization Build | Organizational Change Management | Organizational Alignment | 02762 | 3a.CM.OA.02762 | Assess Final Change Impacts | Yes | Yes
3a - Realization Build | Organizational Change Management | Organizational Alignment | 02768 | 3a.CM.OA.02768 | Perform Role-to-Position Mapping | Yes | Yes
3a - Realization Build | Organizational Change Management | Communications | 02730 | 3a.CM.CO.02730 | Develop and Deliver Communications for Realization | No | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02740 | 3a.CM.TR.02740 | Conduct Training Developer Onboarding | No | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02746 | 3a.CM.TR.02746 | Develop Web-Based Training Outlines | Yes | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02747 | 3a.CM.TR.02747 | Develop Web-Based Training Storyboards | Yes | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02748 | 3a.CM.TR.02748 | Develop Web-Based Training Courseware | Yes | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02745 | 3a.CM.TR.02745 | Develop Instructor-Led Training Course Outlines | Yes | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02749 | 3a.CM.TR.02749 | Develop Instructor-Led Training Courseware | Yes | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02755 | 3a.CM.TR.02755 | Develop Training Environment and Training Data Approach | No | Yes
3a - Realization Build | Organizational Change Management | End-User Training | 02752 | 3a.CM.TR.02752 | Develop End-User Training Delivery Schedule | No | Yes
3a - Realization Build | Information Management | Information Governance | 01395 | 3a.IM.GO.01395 | Develop Information Governance Policies | No | No
3a - Realization Build | Information Management | Information Governance | 01396 | 3a.IM.GO.01396 | Plan Information Governance Organization Transition | No | No
3a - Realization Build | Information Management | Information Strategy & Architecture | 01454 | 3a.IM.SA.01454 | Design Physical Data Model | No | No
3a - Realization Build | Information Management | Information Strategy & Architecture | 01411 | 3a.IM.SA.01411 | Configure Business Intelligence Data Architecture | Yes | Yes
3a - Realization Build | Information Management | Information Strategy & Architecture | 01414 | 3a.IM.SA.01414 | Configure Business Intelligence Physical Data Model | Yes | Yes
3a - Realization Build | Information Management | Data Protection & Privacy | 01474 | 3a.IM.PP.01474 | Develop Privacy and Data Protection Control Activity Framework | No | No
3a - Realization Build | Information Management | Data Protection & Privacy | 01485 | 3a.IM.PP.01485 | Develop Privacy and Data Protection Test Cases | No | No
3a - Realization Build | Information Management | Master Data Management | 00012 | 3a.IM.MD.00012 | Manage Data Clean-up | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01641 | 3a.IM.BI.01641 | Develop Analytics and Reporting Processes | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01631 | 3a.IM.BI.01631 | Develop Data Model Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01651 | 3a.IM.BI.01651 | Conduct Data Model Unit Tests | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00058 | 3a.IM.BI.00058 | Develop Scorecard and Dashboard Layouts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01614 | 3a.IM.BI.01614 | Develop Scorecard and Dashboard Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01643 | 3a.IM.BI.01643 | Conduct Scorecard and Dashboard Unit Testing | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01645 | 3a.IM.BI.01645 | Develop Analytics Capabilities | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01617 | 3a.IM.BI.01617 | Develop Analytics Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01646 | 3a.IM.BI.01646 | Conduct Analytics Unit Testing | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01647 | 3a.IM.BI.01647 | Develop Operational Report Layouts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01620 | 3a.IM.BI.01620 | Develop Operational Reporting Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01648 | 3a.IM.BI.01648 | Conduct Operational Reporting Unit Testing | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01644 | 3a.IM.BI.01644 | Develop Management and External Reporting Layouts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01622 | 3a.IM.BI.01622 | Develop Management and External Reporting Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01649 | 3a.IM.BI.01649 | Conduct Management and External Reporting Unit Testing | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01564 | 3a.IM.BI.01564 | Develop Data Mining Capabilities | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01626 | 3a.IM.BI.01626 | Develop Data Mining Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01650 | 3a.IM.BI.01650 | Conduct Data Mining Unit Testing | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00069 | 3a.IM.BI.00069 | Develop Technical Specifications (BI Enhancements) | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00075 | 3a.IM.BI.00075 | Develop Software Code (BI Enhancement) | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00084 | 3a.IM.BI.00084 | Conduct Functional Unit Test (BI Enhancement) | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00171 | 3a.IM.BI.00171 | Conduct Functional Unit Test (BI) | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00059 | 3a.IM.BI.00059 | Build and Unit Test Reporting Solution- By Complexity | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01597 | 3a.IM.BI.01597 | Design Business Intelligence Batch Process Execution Schedule | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01599 | 3a.IM.BI.01599 | Build Business Intelligence Batch Process Execution Schedule | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01593 | 3a.IM.BI.01593 | Develop Business Intelligence Batch Process Schedule Unit Test Scripts | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 01604 | 3a.IM.BI.01604 | Conduct Business Intelligence Batch Process Schedule Unit Test | No | No
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00055 | 3a.IM.BI.00055 | Develop Business Intelligence Batch Process Execution Schedule - By Complexity | Yes | Yes
3a - Realization Build | Information Management | Business Intelligence & Data Warehousing | 00011 | 3a.IM.BI.00011 | Develop BI BPPs | Yes | Yes
3a - Realization Build | Development | Application Development | 01847 | 3a.DV.AD.01847 | Develop Technical Specifications (Form) | Yes | Yes
3a - Realization Build | Development | Application Development | 01848 | 3a.DV.AD.01848 | Develop Technical Specifications (Report) | Yes | Yes
3a - Realization Build | Development | Application Development | 00066 | 3a.DV.AD.00066 | Develop Technical Specifications (Point-to-Point Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 00068 | 3a.DV.AD.00068 | Develop Technical Specifications (Middleware Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 01851 | 3a.DV.AD.01851 | Develop Technical Specifications (Enhancement) | Yes | Yes
3a - Realization Build | Development | Application Development | 01852 | 3a.DV.AD.01852 | Develop Technical Specifications (Workflow) | Yes | Yes
3a - Realization Build | Development | Application Development | 00065 | 3a.DV.AD.00065 | Develop Technical Specifications (EDI) | Yes | Yes
3a - Realization Build | Development | Application Development | 01885 | 3a.DV.AD.01885 | Develop Technical Specifications (Conversion) | Yes | Yes
3a - Realization Build | Development | Application Development | 00074 | 3a.DV.AD.00074 | Develop Software Code (Forms) | Yes | Yes
3a - Realization Build | Development | Application Development | 00080 | 3a.DV.AD.00080 | Develop Software Code (Report) | Yes | Yes
3a - Realization Build | Development | Application Development | 00079 | 3a.DV.AD.00079 | Develop Software Code (Point-to-Point Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 01897 | 3a.DV.AD.01897 | Review Software Code | No | No
3a - Realization Build | Development | Application Development | 00076 | 3a.DV.AD.00076 | Develop Software Code (Enhancement) | Yes | Yes
3a - Realization Build | Development | Application Development | 00072 | 3a.DV.AD.00072 | Develop Software Code (Workflow) | Yes | Yes
3a - Realization Build | Development | Application Development | 00070 | 3a.DV.AD.00070 | Develop Software Code (EDI) | Yes | Yes
3a - Realization Build | Development | Application Development | 00077 | 3a.DV.AD.00077 | Develop Software Code (Conversion) | Yes | Yes
3a - Realization Build | Development | Application Development | 00078 | 3a.DV.AD.00078 | Develop Software Code (Middleware Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 01873 | 3a.DV.AD.01873 | Install or Develop Integration Common Services | No | No
3a - Realization Build | Development | Application Development | 01904 | 3a.DV.AD.01904 | Prepare and Conduct Technical Unit Test (Form) | Yes | Yes
3a - Realization Build | Development | Application Development | 01905 | 3a.DV.AD.01905 | Prepare and Conduct Technical Unit Test (Report) | Yes | Yes
3a - Realization Build | Development | Application Development | 00092 | 3a.DV.AD.00092 | Prepare and Conduct Technical Unit Test (Point-to-Point Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 00091 | 3a.DV.AD.00091 | Prepare and Conduct Technical Unit Test (Middleware Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 01909 | 3a.DV.AD.01909 | Prepare and Conduct Technical Unit Test (Enhancement) | Yes | Yes
3a - Realization Build | Development | Application Development | 01910 | 3a.DV.AD.01910 | Prepare and Conduct Technical Unit Test (Workflow) | Yes | Yes
3a - Realization Build | Development | Application Development | 00172 | 3a.DV.AD.00172 | Prepare and Conduct Technical Unit Test (EDI) | Yes | Yes
3a - Realization Build | Development | Application Development | 01908 | 3a.DV.AD.01908 | Prepare and Conduct Technical Unit Test (Conversion) | Yes | Yes
3a - Realization Build | Development | Application Development | 01922 | 3a.DV.AD.01922 | Prepare and Conduct Functional Unit Test (Form) | Yes | Yes
3a - Realization Build | Development | Application Development | 01923 | 3a.DV.AD.01923 | Prepare and Conduct Functional Unit Test (Report) | Yes | Yes
3a - Realization Build | Development | Application Development | 00086 | 3a.DV.AD.00086 | Prepare and Conduct Functional Unit Test (Point-to-Point Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 00081 | 3a.DV.AD.00081 | Prepare and Conduct Functional Unit Test (Middleware Interface) | Yes | Yes
3a - Realization Build | Development | Application Development | 01926 | 3a.DV.AD.01926 | Prepare and Conduct Functional Unit Test (Enhancement) | Yes | Yes
3a - Realization Build | Development | Application Development | 01927 | 3a.DV.AD.01927 | Prepare and Conduct Functional Unit Test (Workflow) | Yes | Yes
3a - Realization Build | Development | Application Development | 00087 | 3a.DV.AD.00087 | Conduct Functional Unit Test (EDI) | Yes | Yes
3a - Realization Build | Development | Application Development | 01925 | 3a.DV.AD.01925 | Prepare and Conduct Functional Unit Test (Conversion) | Yes | Yes
3a - Realization Build | Development | Portal Development | 01945 | 3a.DV.PO.01945 | Develop Technical Specifications (Portal) | Yes | Yes
3a - Realization Build | Development | Portal Development | 01952 | 3a.DV.PO.01952 | Build Portal Technical Configuration | Yes | Yes
3a - Realization Build | Development | Portal Development | 01953 | 3a.DV.PO.01953 | Develop and Implement Portal Business Package Configuration | No | No
3a - Realization Build | Development | Portal Development | 01954 | 3a.DV.PO.01954 | Develop and Migrate Portal Content | Yes | Yes
3a - Realization Build | Development | Portal Development | 01955 | 3a.DV.PO.01955 | Build Federated Portal | Yes | Yes
3a - Realization Build | Development | Portal Development | 00071 | 3a.DV.PO.00071 | Develop Software Code (Portal) | Yes | Yes
3a - Realization Build | Development | Portal Development | 01957 | 3a.DV.PO.01957 | Prepare and Conduct Technical Unit Test (Portal) | No | No
3a - Realization Build | Development | Portal Development | 01959 | 3a.DV.PO.01959 | Prepare and Conduct Functional Unit Test (Portal) | No | No
3a - Realization Build | Development | Legacy System Development | 00067 | 3a.DV.LS.00067 | Develop Technical Specifications (Legacy System) | Yes | Yes
3a - Realization Build | Development | Legacy System Development | 00073 | 3a.DV.LS.00073 | Develop Software Code (Legacy) | Yes | Yes
3a - Realization Build | Development | Legacy System Development | 00089 | 3a.DV.LS.00089 | Perform Functional Unit Test (Legacy System) | Yes | Yes
3a - Realization Build | Development | Development Controls | 02009 | 3a.DV.DC.02009 | Develop Interface Control Framework | Yes | Yes
3a - Realization Build | Development | Development Controls | 02010 | 3a.DV.DC.02010 | Develop Data Conversion Control Framework | Yes | Yes
3a - Realization Build | Development | Development Controls | 00094 | 3a.DV.DC.00094 | Unit Test Interface Control Activities | Yes | Yes
3a - Realization Build | Development | Development Controls | 00095 | 3a.DV.DC.00095 | Unit Test Data Conversion Control Activities | Yes | Yes
3a - Realization Build | Technology | Logical Infrastructure | 02047 | 3a.TE.LI.02047 | Conduct Non-Production Transports | No | No
3a - Realization Build | Technology | Physical Infrastructure | 02088 | 3a.TE.PI.02088 | Procure Production Hardware | No | No
3a - Realization Build | Technology | Physical Infrastructure | 02098 | 3a.TE.PI.02098 | Install Output Management Infrastructure | No | No
3a - Realization Build | Technology | Technology Controls | 02103 | 3a.TE.TC.02103 | Develop Information Technology Control Framework | Yes | Yes
3a - Realization Build | Technology | Technology Controls | 00097 | 3a.TE.TC.00097 | Unit Test Information Technology Control Activities | Yes | Yes
3a - Realization Build | Technology | Identity & Access Management | 02116 | 3a.TE.ID.02116 | Install Identity and Access Management Solution Components | No | No
3a - Realization Build | Technology | Identity & Access Management | 02119 | 3a.TE.ID.02119 | Perform Identity and Access Management Solution Configuration | No | No
3a - Realization Build | Technology | Identity & Access Management | 02120 | 3a.TE.ID.02120 | Integrate Managed Systems | No | No
3a - Realization Build | Technology | Identity & Access Management | 02121 | 3a.TE.ID.02121 | Document Identity and Access Management Solution Build Process | No | No
3a - Realization Build | Technology | Identity & Access Management | 02122 | 3a.TE.ID.02122 | Cleanse User Data | No | No
3a - Realization Build | Technology | Identity & Access Management | 02123 | 3a.TE.ID.02123 | Configure Identity and Access Management Non-Production Testing Environment | No | No
3a - Realization Build | Technology | Identity & Access Management | 02124 | 3a.TE.ID.02124 | Document Identity and Access Management Non-Production Environment Build Process | No | No
3a - Realization Build | Technology | Identity & Access Management | 02125 | 3a.TE.ID.02125 | Develop Identity and Access Management Test Cases | No | No
3a - Realization Build | Technology | Application Security | 02177 | 3a.TE.SE.02177 | Configure Additional Non-Production Application Security Environments (Security Test Environment) | Yes | Yes
3a - Realization Build | Technology | Application Security | 02180 | 3a.TE.SE.02180 | Support Additional Non-Production Application Security Users and Roles (Support Project Team) | Yes | Yes
3a - Realization Build | Technology | Application Security | 02186 | 3a.TE.SE.02186 | Analyze Role Segregation of Duties | Yes | Yes
3a - Realization Build | Technology | Application Security | 02149 | 3a.TE.SE.02149 | Develop Production Application Specialty Integration Strategies | Yes | Yes
3a - Realization Build | Technology | Application Security | 02151 | 3a.TE.SE.02151 | Prepare Production Application Security Design Workshop | No | No
3a - Realization Build | Technology | Application Security | 00099 | 3a.TE.SE.00099 | Conduct Production Application Security Design Workshop (Design Master Roles) | Yes | Yes
3a - Realization Build | Technology | Application Security | 00098 | 3a.TE.SE.00098 | Conduct Production Application Security Design Workshop (Derived Roles) | Yes | Yes
3a - Realization Build | Technology | Application Security | 02155 | 3a.TE.SE.02155 | Design Production Application Security Business Roles | Yes | Yes
3a - Realization Build | Technology | Application Security | 02162 | 3a.TE.SE.02162 | Configure Production Application Security Business Roles | Yes | Yes
3a - Realization Build | Technology | Application Security | 02165 | 3a.TE.SE.02165 | Configure Production Application Security (Configure Master Roles) | Yes | Yes
3a - Realization Build | Technology | Application Security | 02166 | 3a.TE.SE.02166 | Configure Production Application Security Derived Roles | Yes | Yes
3a - Realization Build | Technology | Application Security | 02167 | 3a.TE.SE.02167 | Configure Production Application Security Batch and Spool Management | Yes | Yes
3a - Realization Build | Technology | Infrastructure Testing | 02229 | 3a.TE.TE.02229 | Define Performance and Stress Testing Requirements | No | No
3a - Realization Build | Technology | Infrastructure Testing | 02232 | 3a.TE.TE.02232 | Test Output Management Infrastructure | No | No
3a - Realization Build | Technology | Infrastructure Testing | 02233 | 3a.TE.TE.02233 | Develop Disaster Recovery Test Approach | No | No
3a - Realization Build | Deployment | System Deployment | 02256 | 3a.DP.SD.02256 | Develop Cutover Strategy | No | No
3a - Realization Build | Deployment | System Deployment | 02259 | 3a.DP.SD.02259 | Develop Cutover Plan | Yes | Yes
3a - Realization Build | Deployment | System Deployment | 02260 | 3a.DP.SD.02260 | Develop Go-Live Contingency Approach | No | No
3a - Realization Build | Deployment | Business Deployment | 02301 | 3a.DP.BD.02301 | Define Release Go/No-Go Criteria | No | No
3a - Realization Build | Deployment | Business Deployment | 02298 | 3a.DP.BD.02298 | Develop Business Freeze Approach | No | No
3a - Realization Build | Deployment | Business Deployment | 02300 | 3a.DP.BD.02300 | Develop Business Restart Procedures | No | No
3a - Realization Build | Deployment | Business Deployment | 02299 | 3a.DP.BD.02299 | Develop Business Outage Procedures | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02335 | 3a.DP.SU.02335 | Identify ERP System Stabilization Metrics | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02323 | 3a.DP.SU.02323 | Establish Baseline ERP System Stabilization Metrics | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02374 | 3a.DP.SU.02374 | Develop Support Organization Procedures | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02691 | 3a.DP.SU.02691 | Design Root Cause Analysis Process and Tools | Yes | Yes
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02380 | 3a.DP.SU.02380 | Develop Support Organization Technology Environment | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02329 | 3a.DP.SU.02329 | Develop Upgrade and Patch Implementation Strategy | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02692 | 3a.DP.SU.02692 | Establish Remote Supportability | Yes | Yes
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02388 | 3a.DP.SU.02388 | Develop Technical Support Infrastructure Test Plan | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02389 | 3a.DP.SU.02389 | Develop Technical Support System Infrastructure Test Plan | No | No
3a - Realization Build | Deployment | Support Preparation & Stabilization | 02391 | 3a.DP.SU.02391 | Develop Support Landscape Test Approach | No | No
3a - Realization Build | Deployment | Readiness Testing | 02418 | 3a.DP.RE.02418 | Develop Integration Test Plan | No | No
3a - Realization Build | Deployment | Readiness Testing | 02427 | 3a.DP.RE.02427 | Develop User-Acceptance Test Plan | No | No
3a - Realization Build | Deployment | Readiness Testing | 02414 | 3a.DP.RE.02414 | Develop Integration Test Cases | Yes | Yes
3a - Realization Build | Deployment | Readiness Testing | 02416 | 3a.DP.RE.02416 | Prepare Integration Test Environment | No | No
3a - Realization Build | Deployment | Readiness Testing | 02419 | 3a.DP.RE.02419 | Prepare Integration Test Data | No | No
3a - Realization Build | Deployment | Readiness Testing | 02421 | 3a.DP.RE.02421 | Develop Test Traceability Matrix | No | No
3a - Realization Build | Deployment | Readiness Testing | 02435 | 3a.DP.RE.02435 | Perform Defect Management | No | No
3a - Realization Build | Tax | Tax | 02468 | 3a.TX.TX.02468 | Develop Tax Solution Configuration Specifications | No | No
3a - Realization Build | Tax | Tax | 02469 | 3a.TX.TX.02469 | Configure Tax Solution Elements | No | No
3a - Realization Build | Tax | Tax | 02470 | 3a.TX.TX.02470 | Conduct Tax Solution Unit Test | No | No
3a - Realization Build | Value | Value | 00119 | 3a.VL.VL.00119 | Update and Refresh Business Case | Yes | Yes
3a - Realization Build | Value | Value | 02489 | 3a.VL.VL.02489 | Implement Value Delivery Approach | No | No
3a - Realization Build | Value | Value | 02492 | 3a.VL.VL.02492 | Implement Value Delivery Goals by Organization | No | No
3a - Realization Build | Value | Value | 02496 | 3a.VL.VL.02496 | Implement Value Tracking Plan | No | No
3a - Realization Build | Value | Value | 02494 | 3a.VL.VL.02494 | Conduct Value Delivery Gap Analysis | No | No
3b - Realization Test | Project Management | Plan | 00001 | 3b.PM.PL.00001 | Scheduling Milestones | No | No
3b - Realization Test | Project Management | Plan | 01035 | 3b.PM.PL.01035 | Develop Work Plan | No | Yes
3b - Realization Test | Project Management | Plan | 01038 | 3b.PM.PL.01038 | Complete Deliverables Log | No | Yes
3b - Realization Test | Project Management | Plan | 01033 | 3b.PM.PL.01033 | Install and Configure Tools | No | Yes
3b - Realization Test | Project Management | Manage | 00003 | 3b.PM.MG.00003 | Fixed Headcount | Yes | Yes
3b - Realization Test | Project Management | Manage | 01084 | 3b.PM.MG.01084 | Develop Project Team | No | Yes
3b - Realization Test | Process and Application | Package Configuration | 01248 | 3b.PP.PK.01248 | Define Batch Schedule | No | No
3b - Realization Test | Process and Application | Package Configuration | 00135 | 3b.PP.PK.00135 | Perform Break-fix | Yes | Yes
3b - Realization Test | Process and Application | Business Process Controls | 01279 | 3b.PP.PC.01279 | Develop Process Control Framework | Yes | Yes
3b - Realization Test | Process and Application | Business Process Controls | 00026 | 3b.PP.PC.00026 | Unit Test Process Control Activities | Yes | Yes
3b - Realization Test | Process and Application | Business Process Controls | 01281 | 3b.PP.PC.01281 | Support Integration Controls Testing | No | No
3b - Realization Test | Organizational Change Management | Change Preparation | 02720 | 3b.CM.CP.02720 | Launch Super User Program | Yes | Yes
3b - Realization Test | Organizational Change Management | Change Preparation | 02721 | 3b.CM.CP.02721 | Build Super User Skills | Yes | Yes
3b - Realization Test | Organizational Change Management | Organizational Alignment | 02766 | 3b.CM.OA.02766 | Conduct Go-Live Transition Assessment | No | Yes
3b - Realization Test | Organizational Change Management | Organizational Alignment | 02765 | 3b.CM.OA.02765 | Develop Go-Live Transition Guides | Yes | Yes
3b - Realization Test | Organizational Change Management | Communications | 02730 | 3b.CM.CO.02730 | Develop and Deliver Communications for Realization | No | Yes
3b - Realization Test | Organizational Change Management | Capability Transfer | 02704 | 3b.CM.CT.02704 | Assess Project Team Capability Transfer | Yes | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02748 | 3b.CM.TR.02748 | Develop Web-Based Training Courseware | Yes | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02749 | 3b.CM.TR.02749 | Develop Instructor-Led Training Courseware | Yes | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02757 | 3b.CM.TR.02757 | Build Training Environment and Training Data | Yes | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02759 | 3b.CM.TR.02759 | Prepare Train-the-Trainer Materials | No | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02760 | 3b.CM.TR.02760 | Conduct Train-the-Trainer Program | Yes | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02750 | 3b.CM.TR.02750 | Translate and Localize End-User Courseware | Yes | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02751 | 3b.CM.TR.02751 | Produce and Distribute Courseware | No | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02753 | 3b.CM.TR.02753 | Set Up Training Facilities | No | Yes
3b - Realization Test | Organizational Change Management | End-User Training | 02737 | 3b.CM.TR.02737 | Enroll End Users | No | Yes
3b - Realization Test | Information Management | Data Protection & Privacy | 01475 | 3b.IM.PP.01475 | Conduct Privacy and Data Protection Controls Unit Test | No | No
3b - Realization Test | Information Management | Data Protection & Privacy | 01481 | 3b.IM.PP.01481 | Conduct Privacy and Data Protection Controls Integration Test | No | No
3b - Realization Test | Information Management | Master Data Management | 00012 | 3b.IM.MD.00012 | Manage Data Clean-up | Yes | Yes
3b - Realization Test | Information Management | Business Intelligence & Data Warehousing | 00009 | 3b.IM.BI.00009 | Conduct Performance and Stress Tests - By Complexity | Yes | Yes
3b - Realization Test | Information Management | Business Intelligence & Data Warehousing | 00013 | 3b.IM.BI.00013 | Online Performance Test Materials - By Complexity | Yes | Yes
3b - Realization Test | Development | Application Development | 01870 | 3b.DV.AD.01870 | Install or Develop Reusable Integration Components | No | No
3b - Realization Test | Development | Application Development | 01887 | 3b.DV.AD.01887 | Build Integration Components | No | No
3b - Realization Test | Development | Portal Development | 00158 | 3b.DV.PO.00158 | Conduct Portal Performance Test | Yes | Yes
3b - Realization Test | Development | Portal Development | 00157 | 3b.DV.PO.00157 | Conduct Portal Disaster Recovery Test | Yes | Yes
3b - Realization Test | Development | Development Controls | 02009 | 3b.DV.DC.02009 | Develop Interface Control Framework | Yes | Yes
3b - Realization Test | Development | Development Controls | 02010 | 3b.DV.DC.02010 | Develop Data Conversion Control Framework | Yes | Yes
3b - Realization Test | Development | Development Controls | 00094 | 3b.DV.DC.00094 | Unit Test Interface Control Activities | Yes | Yes
3b - Realization Test | Development | Development Controls | 00095 | 3b.DV.DC.00095 | Unit Test Data Conversion Control Activities | Yes | Yes
3b - Realization Test | Technology | Technology Controls | 02103 | 3b.TE.TC.02103 | Develop Information Technology Control Framework | Yes | Yes
3b - Realization Test | Technology | Technology Controls | 00097 | 3b.TE.TC.00097 | Unit Test Information Technology Control Activities | Yes | Yes
3b - Realization Test | Technology | Identity & Access Management | 02126 | 3b.TE.ID.02126 | Conduct Identity and Access Management Solution Test | No | No
3b - Realization Test | Technology | Application Security | 02177 | 3b.TE.SE.02177 | Configure Additional Non-Production Application Security Environments (Security Test Environment) | Yes | Yes
3b - Realization Test | Technology | Application Security | 02180 | 3b.TE.SE.02180 | Support Additional Non-Production Application Security Users and Roles (Support Project Team) | Yes | Yes
3b - Realization Test | Technology | Application Security | 02186 | 3b.TE.SE.02186 | Analyze Role Segregation of Duties | Yes | Yes
3b - Realization Test | Technology | Application Security | 02162 | 3b.TE.SE.02162 | Configure Production Application Security Business Roles | Yes | Yes
3b - Realization Test | Technology | Application Security | 02166 | 3b.TE.SE.02166 | Configure Production Application Security Derived Roles | Yes | Yes
3b - Realization Test | Technology | Application Security | 02167 | 3b.TE.SE.02167 | Configure Production Application Security Batch and Spool Management | Yes | Yes
3b - Realization Test | Technology | Application Security | 02187 | 3b.TE.SE.02187 | Configure Production Application Support Security | Yes | Yes
3b - Realization Test | Technology | Application Security | 02189 | 3b.TE.SE.02189 | Identify Production Users (Review Role to Position Mapping doc [PCL]) | No | Yes
3b - Realization Test | Technology | Application Security | 02171 | 3b.TE.SE.02171 | Develop Production Application Security Unit Test Scripts | Yes | Yes
3b - Realization Test | Technology | Application Security | 00101 | 3b.TE.SE.00101 | Conduct Production Application Security Unit Testing (Business Roles) | Yes | Yes
3b - Realization Test | Technology | Application Security | 00100 | 3b.TE.SE.00100 | Conduct Production Application Security Unit Testing (Master Roles / Responsibilities) | Yes | Yes
3b - Realization Test | Technology | Application Security | 02183 | 3b.TE.SE.02183 | Develop Production Application Security Test Tracker | Yes | Yes
3b - Realization Test | Technology | Application Security | 02185 | 3b.TE.SE.02185 | Support Production Application Security Integration Testing | No | No
3b - Realization Test | Technology | Technology Operations | 02212 | 3b.TE.OP.02212 | Develop Batch Schedule Strategy | Yes | Yes
3b - Realization Test | Technology | Technology Operations | 02213 | 3b.TE.OP.02213 | Develop Batch Job Schedule | Yes | Yes
3b - Realization Test | Technology | Infrastructure Testing | 00103 | 3b.TE.TE.00103 | Define Performance and Stress Test Scope | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02242 | 3b.TE.TE.02242 | Conduct Disaster Recovery Test | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02243 | 3b.TE.TE.02243 | Develop Batch Schedule Test Work Plan | Yes | Yes
3b - Realization Test | Technology | Infrastructure Testing | 01259 | 3b.TE.TE.01259 | Conduct Batch Schedule Test | Yes | Yes
3b - Realization Test | Technology | Infrastructure Testing | 00102 | 3b.TE.TE.00102 | Develop Performance and Stress Test Approach | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02228 | 3b.TE.TE.02228 | Develop Performance and Stress Testing Work Plan | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02241 | 3b.TE.TE.02241 | Develop Performance and Stress Test Scripts | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02244 | 3b.TE.TE.02244 | Prepare and Conduct Database Tier Performance and Stress Testing | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02245 | 3b.TE.TE.02245 | Prepare and Conduct Middleware Tier Performance and Stress Testing | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02246 | 3b.TE.TE.02246 | Prepare and Conduct Application Tier Performance and Stress Testing | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02247 | 3b.TE.TE.02247 | Prepare and Conduct Web Tier Performance and Stress Testing | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02248 | 3b.TE.TE.02248 | Prepare and Conduct Batch Tier Performance and Stress Testing | No | No
3b - Realization Test | Technology | Infrastructure Testing | 02255 | 3b.TE.TE.02255 | Develop Performance and Stress Testing Report | No | No
3b - Realization Test | Deployment | System Deployment | 02278 | 3b.DP.SD.02278 | Implement Batch Job Schedule | No | No
3b - Realization Test | Deployment | Business Deployment | 02302 | 3b.DP.BD.02302 | Develop Site Readiness Checklist | No | No
3b - Realization Test | Deployment | Readiness Testing | 00117 | 3b.DP.RE.00117 | Support Integration Test (Report) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00118 | 3b.DP.RE.00118 | Support Integration Test (Form) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00113 | 3b.DP.RE.00113 | Support Integration Test (Portal) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00111 | 3b.DP.RE.00111 | Support Integration Test (P2P Interface) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00114 | 3b.DP.RE.00114 | Support Integration Test (Middleware Interface) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00115 | 3b.DP.RE.00115 | Support Integration Test (Business Package) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00108 | 3b.DP.RE.00108 | Support Integration Test (Conversion) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00109 | 3b.DP.RE.00109 | Support Integration Test (Enhancement) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00110 | 3b.DP.RE.00110 | Support Integration Test (Workflow) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00107 | 3b.DP.RE.00107 | Support Integration Test (Legacy System) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00112 | 3b.DP.RE.00112 | Support Integration Test (EDI) | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 02431 | 3b.DP.RE.02431 | Conduct Integration Test | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 00116 | 3b.DP.RE.00116 | Conduct BI Integration Tests - By Complexity | Yes | Yes
3b - Realization Test | Deployment | Readiness Testing | 02434 | 3b.DP.RE.02434 | Update Test Traceability Matrix | No | No
3b - Realization Test | Deployment | Readiness Testing | 02447 | 3b.DP.RE.02447 | Develop Regression Test Plan | No | No
3b - Realization Test | Deployment | Readiness Testing | 02446 | 3b.DP.RE.02446 | Prepare Regression Test Environment | No | No
3b - Realization Test | Deployment | Readiness Testing | 02444 | 3b.DP.RE.02444 | Develop Regression Test Cases | No | No
3b - Realization Test | Deployment | Readiness Testing | 02445 | 3b.DP.RE.02445 | Develop Regression Test Data | No | No
3b - Realization Test | Deployment | Readiness Testing | 02448 | 3b.DP.RE.02448 | Conduct Regression Test | No | No
3b - Realization Test | Deployment | Readiness Testing | 02436 | 3b.DP.RE.02436 | Develop Parallel Test Plan | No | No
3b - Realization Test | Deployment | Readiness Testing | 02437 | 3b.DP.RE.02437 | Prepare Parallel Test Environment | No | No
3b - Realization Test | Deployment | Readiness Testing | 02439 | 3b.DP.RE.02439 | Develop Parallel Test Cases | No | No
3b - Realization Test | Deployment | Readiness Testing | 02438 | 3b.DP.RE.02438 | Prepare Parallel Test Data | No | No
3b - Realization Test | Deployment | Readiness Testing | 02440 | 3b.DP.RE.02440 | Conduct Parallel Test | No | No
3b - Realization Test | Value | Value | 02489 | 3b.VL.VL.02489 | Update and Refresh Business Case | Yes | Yes
3b - Realization Test | Value | Value | 02492 | 3b.VL.VL.02492 | Implement Value Delivery Goals by Organization | No | No
3b - Realization Test | Value | Value | 02496 | 3b.VL.VL.02496 | Implement Value Tracking Plan | No | No
4 - Final Preparation | Project Management | Plan | 00001 | 4.PM.PL.00001 | Scheduling Milestones | No | No
4 - Final Preparation | Project Management | Plan | 01035 | 4.PM.PL.01035 | Develop Work Plan | No | Yes
4 - Final Preparation | Project Management | Plan | 01038 | 4.PM.PL.01038 | Complete Deliverables Log | No | Yes
4 - Final Preparation | Project Management | Plan | 01033 | 4.PM.PL.01033 | Install and Configure Tools | No | Yes
4 - Final Preparation | Project Management | Manage | 00003 | 4.PM.MG.00003 | Fixed Headcount | Yes | Yes
4 - Final Preparation | Project Management | Manage | 01084 | 4.PM.MG.01084 | Develop Project Team | No | Yes
4 - Final Preparation | Process and Application | Business Process Controls | 01288 | 4.PP.PC.01288 | Update Security and Controls Transition Approach | Yes | Yes
4 - Final Preparation | Process and Application | Business Process Controls | 01291 | 4.PP.PC.01291 | Develop Controls Post-Implementation Plan | Yes | Yes
4 - Final Preparation | Process and Application | Business Process Controls | 01283 | 4.PP.PC.01283 | Verify Process Control Framework | Yes | Yes
4 - Final Preparation | Process and Application | Business Process Controls | 01284 | 4.PP.PC.01284 | Verify Process Control Training | Yes | Yes
4 - Final Preparation | Process and Application | Business Process Controls | 01285 | 4.PP.PC.01285 | Verify Process Control Segregation of Duties | Yes | Yes
4 - Final Preparation | Organizational Change Management | Change Preparation | 02708 | 4.CM.CP.02708 | Conduct Final Change Readiness Assessment | Yes | Yes
4 - Final Preparation | Organizational Change Management | Change Preparation | 02711 | 4.CM.CP.02711 | Develop Leadership Action Plans for Final Preparation | No | Yes
4 - Final Preparation | Organizational Change Management | Change Preparation | 02722 | 4.CM.CP.02722 | Prepare Super Users for Go-Live | Yes | Yes
4 - Final Preparation | Organizational Change Management | Change Preparation | 02716 | 4.CM.CP.02716 | Monitor Change Network Go-Live Action Plans | Yes | Yes
4 - Final Preparation | Organizational Change Management | Organizational Alignment | 02763 | 4.CM.OA.02763 | Conduct Go-Live Transition Workshops | Yes | Yes
4 - Final Preparation | Organizational Change Management | Communications | 02731 | 4.CM.CO.02731 | Develop and Deliver Communications for Final Preparation | No | Yes
4 - Final Preparation | Organizational Change Management | Capability Transfer | 02700 | 4.CM.CT.02700 | Complete Project Team Capability Transfer | No | Yes
4 - Final Preparation | Organizational Change Management | End-User Training | 02742 | 4.CM.TR.02742 | Develop End-User Training Program Maintenance Plan | No | Yes
4 - Final Preparation | Organizational Change Management | End-User Training | 02738 | 4.CM.TR.02738 | Conduct Pre Go-Live End-User Training | Yes | Yes
4 - Final Preparation | Information Management | Information Governance | 01399 | 4.IM.GO.01399 | Develop Information Governance Charter | No | No
4 - Final Preparation | Information Management | Information Governance | 01401 | 4.IM.GO.01401 | Implement Information Governance Organization Transition Plan | No | No
4 - Final Preparation | Information Management | Data Protection & Privacy | 01479 | 4.IM.PP.01479 | Verify Privacy and Data Protection Control Activities | No | No
4 - Final Preparation | Information Management | Data Protection & Privacy | 01488 | 4.IM.PP.01488 | Develop Privacy and Data Protection Controls Post-Implementation Plan | No | No
4 - Final Preparation | Information Management | Master Data Management | 00166 | 4.IM.MD.00166 | Perform Data Conversion Validation | Yes | Yes
4 - Final Preparation | Information Management | Master Data Management | 00165 | 4.IM.MD.00165 | Perform Manual Conversions | Yes | Yes
4 - Final Preparation | Development | Portal Development | 00160 | 4.DV.PO.00160 | Develop Portal Production Support Procedures | Yes | Yes
4 - Final Preparation | Development | Development Controls | 02011 | 4.DV.DC.02011 | Verify Interface Control Framework | Yes | Yes
4 - Final Preparation | Development | Development Controls | 02012 | 4.DV.DC.02012 | Verify Data Conversion Control Framework | Yes | Yes
4 - Final Preparation | Technology | Physical Infrastructure | 02094 | 4.TE.PI.02094 | Build Production Application and Database | No | No
4 - Final Preparation | Technology | Physical Infrastructure | 02091 | 4.TE.PI.02091 | Establish Production Network Connectivity | No | No
4 - Final Preparation | Technology | Technology Controls | 02105 | 4.TE.TC.02105 | Verify Information Technology Control Framework | Yes | Yes
4 - Final Preparation | Technology | Identity & Access Management | 02127 | 4.TE.ID.02127 | Develop Identity and Access Management Solution Deployment Plan | No | No
4 - Final Preparation | Technology | Identity & Access Management | 02130 | 4.TE.ID.02130 | Configure Identity and Access Management Production Environment | No | No
4 - Final Preparation | Technology | Identity & Access Management | 02128 | 4.TE.ID.02128 | Develop Identity and Access Management Operations Guide | No | No
4 - Final Preparation | Technology | Identity & Access Management | 02129 | 4.TE.ID.02129 | Assess Identity and Access Management Solution Release Readiness | No | No
4 - Final Preparation | Technology | Identity & Access Management | 02131 | 4.TE.ID.02131 | Release Identity and Access Management Solution | No | No
4 - Final Preparation | Technology | Application Security | 02191 | 4.TE.SE.02191 | Configure Security Production Environment | Yes | Yes
4 - Final Preparation | Technology | Application Security | 02192 | 4.TE.SE.02192 | Load Security Production End-User Accounts (Establish User ID's) | Yes | Yes
4 - Final Preparation | Technology | Application Security | 02133 | 4.TE.SE.02133 | Analyze User Segregation of Duties | Yes | Yes
4 - Final Preparation | Technology | Application Security | 02193 | 4.TE.SE.02193 | Develop Security Administration Procedures | Yes | Yes
4 - Final Preparation | Technology | Infrastructure Testing | 02250 | 4.TE.TE.02250 | Test Production Environment Infrastructure | No | No
4 - Final Preparation | Technology | Infrastructure Testing | 02251 | 4.TE.TE.02251 | Test Production Backup and Recovery Mechanisms | No | No
4 - Final Preparation | Technology | Infrastructure Testing | 02694 | 4.TE.TE.02694 | Test Application Stability | Yes | Yes
4 - Final Preparation | Technology | Infrastructure Testing | 02226 | 4.TE.TE.02226 | Develop Disaster Recovery Test Cases | No | No
4 - Final Preparation | Technology | Infrastructure Testing | 02252 | 4.TE.TE.02252 | Test High-Availability Failover Scenarios | No | No
4 - Final Preparation | Technology | Infrastructure Testing | 02253 | 4.TE.TE.02253 | Test Site Readiness | No | No
4 - Final Preparation | Deployment | System Deployment | 02279 | 4.DP.SD.02279 | Perform Production Application Security Cutover | Yes | Yes
4 - Final Preparation | Deployment | System Deployment | 02266 | 4.DP.SD.02266 | Develop Tax Solution Cutover Plan | No | No
4 - Final Preparation | Deployment | System Deployment | 02271 | 4.DP.SD.02271 | Develop Production Application Security Cutover | Yes | Yes
4 - Final Preparation | Deployment | System Deployment | 02269 | 4.DP.SD.02269 | Plan Production Application Security Cutover | No | No
4 - Final Preparation | Deployment | System Deployment | 02270 | 4.DP.SD.02270 | Conduct Production Application Security Cutover Rehearsal Plan | No | No
4 - Final Preparation | Deployment | System Deployment | 02276 | 4.DP.SD.02276 | Conduct Tax Solution Cutover | No | No
4 - Final Preparation | Deployment | System Deployment | 00105 | 4.DP.SD.00105 | Perform Data Conversion | Yes | Yes
4 - Final Preparation | Deployment | System Deployment | 00104 | 4.DP.SD.00104 | Execute Cutover | Yes | Yes
4 - Final Preparation | Deployment | System Deployment | 02274 | 4.DP.SD.02274 | Perform Legacy System Decommissioning | Yes | Yes
4 - Final Preparation | Deployment | Business Deployment | 02307 | 4.DP.BD.02307 | Conduct Go/No-Go Evaluations | No | No
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 02382 | 4.DP.SU.02382 | Implement Support Organization Technology Environment | No | No
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 02392 | 4.DP.SU.02392 | Test Help Desk | No | No
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 02393 | 4.DP.SU.02393 | Test Knowledge Landscape and Tools | No | No
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 02384 | 4.DP.SU.02384 | Establish Support Organization | Yes | Yes
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 02394 | 4.DP.SU.02394 | Test Connectivity | No | No
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 02339 | 4.DP.SU.02339 | Develop Tax Solution Support Plan | No | No
4 - Final Preparation | Deployment | Support Preparation & Stabilization | 00106 | 4.DP.SU.00106 | Deploy Support Organization | Yes | Yes
4 - Final Preparation | Deployment | Readiness Testing | 02429 | 4.DP.RE.02429 | Execute Cutover Dress Rehearsal | No | No
4 - Final Preparation | Deployment | Readiness Testing | 02423 | 4.DP.RE.02423 | Develop User-Acceptance Test Cases | No | No
4 - Final Preparation | Deployment | Readiness Testing | 02425 | 4.DP.RE.02425 | Prepare User-Acceptance Test Environment | No | No
4 - Final Preparation | Deployment | Readiness Testing | 02441 | 4.DP.RE.02441 | Conduct User-Acceptance Test | Yes | Yes
4 - Final Preparation | Deployment | Readiness Testing | 02428 | 4.DP.RE.02428 | Prepare User-Acceptance Test Data | No | No
4 - Final Preparation | Tax | Tax | 02471 | 4.TX.TX.02471 | Develop Tax Solution User Guide | No | No
4 - Final Preparation | Value | Value | 00119 | 4.VL.VL.00119 | Update and Refresh Business Case | Yes | Yes
4 - Final Preparation | Value | Value | 02489 | 4.VL.VL.02489 | Implement Value Delivery Approach | No | No
4 - Final Preparation | Value | Value | 02492 | 4.VL.VL.02492 | Implement Value Delivery Goals by Organization | No | No
4 - Final Preparation | Value | Value | 02494 | 4.VL.VL.02494 | Conduct Value Delivery Gap Analysis | No | No
4 - Final Preparation | Value | Value | 02496 | 4.VL.VL.02496 | Implement Value Tracking Plan | No | No
5 - Go Live & Support | Project Management | Plan | 00001 | 5.PM.PL.00001 | Scheduling Milestones | No | No
5 - Go Live & Support | Project Management | Plan | 01035 | 5.PM.PL.01035 | Develop Work Plan | No | Yes
5 - Go Live & Support | Project Management | Plan | 01038 | 5.PM.PL.01038 | Complete Deliverables Log | No | Yes
5 - Go Live & Support | Project Management | Plan | 01033 | 5.PM.PL.01033 | Install and Configure Tools | No | Yes
5 - Go Live & Support | Project Management | Manage | 00003 | 5.PM.MG.00003 | Fixed Headcount | Yes | Yes
5 - Go Live & Support | Project Management | Manage | 01084 | 5.PM.MG.01084 | Develop Project Team | No | Yes
5 - Go Live & Support | Project Management | Close | 01127 | 5.PM.CL.01127 | Close Project | No | Yes
5 - Go Live & Support | Process and Application | Business Process Controls | 01292 | 5.PP.PC.01292 | Conduct Post-Implementation Review | No | No
5 - Go Live & Support | Process and Application | Business Process Controls | 01282 | 5.PP.PC.01282 | Update Control Frameworks | No | No
5 - Go Live & Support | Process and Application | Business Process Controls | 01289 | 5.PP.PC.01289 | Conduct Controls Documentation Transition | No | No
5 - Go Live & Support | Organizational Change Management | Change Preparation | 02709 | 5.CM.CP.02709 | Conduct Post Go-Live User Readiness Assessment | No | Yes
5 - Go Live & Support | Organizational Change Management | Change Preparation | 02712 | 5.CM.CP.02712 | Develop Leadership Action Plans for Go-Live & Support | No | Yes
5 - Go Live & Support | Organizational Change Management | Change Preparation | 02723 | 5.CM.CP.02723 | Conduct Super User Briefings | No | Yes
5 - Go Live & Support | Organizational Change Management | Change Preparation | 02717 | 5.CM.CP.02717 | Conduct Change Network Briefings | No | Yes
5 - Go Live & Support | Organizational Change Management | Communications | 02732 | 5.CM.CO.02732 | Develop and Deliver Communications for Go-Live & Support | No | Yes
5 - Go Live & Support | Organizational Change Management | End-User Training | 02739 | 5.CM.TR.02739 | Conduct Post Go-Live End-User Training | No | Yes
5 - Go Live & Support | Information Management | Data Protection & Privacy | 01498 | 5.IM.PP.01498 | Conduct Post-Implementation Privacy and Data Protection Control Review | No | No
5 - Go Live & Support | Information Management | Data Protection & Privacy | 01495 | 5.IM.PP.01495 | Update Privacy and Data Protection Control Activities | No | No
5 - Go Live & Support | Technology | Identity & Access Management | 02132 | 5.TE.ID.02132 | Provide Post-Go-Live Support | No | No
5 - Go Live & Support | Technology | Application Security | 02195 | 5.TE.SE.02195 | Administer Production Application Security | No | No
5 - Go Live & Support | Technology | Application Security | 02196 | 5.TE.SE.02196 | Conduct Production Application Security Operations | No | No
5 - Go Live & Support | Technology | Technology Operations | 02209 | 5.TE.OP.02209 | Define Production Environment Patch Procedures | No | No
5 - Go Live & Support | Technology | Technology Operations | 02217 | 5.TE.OP.02217 | Implement Operational Support Technology Environment | No | No
5 - Go Live & Support | Technology | Technology Operations | 02218 | 5.TE.OP.02218 | Monitor Application Technical Issues | No | No
5 - Go Live & Support | Technology | Technology Operations | 02219 | 5.TE.OP.02219 | Monitor Integrations | No | No
5 - Go Live & Support | Technology | Technology Operations | 02220 | 5.TE.OP.02220 | Monitor Network | No | No
5 - Go Live & Support | Technology | Technology Operations | 02221 | 5.TE.OP.02221 | Monitor Application Performance and Stability | No | No
5 - Go Live & Support | Deployment | System Deployment | 02290 | 5.DP.SD.02290 | Transfer Application Service Responsibilities | No | No
5 - Go Live & Support | Deployment | System Deployment | 02274 | 5.DP.SD.02274 | Shut Down Legacy Environment | No | No
5 - Go Live & Support | Deployment | Business Deployment | 02305 | 5.DP.BD.02305 | Establish Activities for Business Continuity Culture | No | No
5 - Go Live & Support | Deployment | Business Deployment | 02303 | 5.DP.BD.02303 | Develop Business Continuity Maintenance Approach | No | No
5 - Go Live & Support | Deployment | Business Deployment | 02306 | 5.DP.BD.02306 | Develop Business Continuity Audit Approach | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02403 | 5.DP.SU.02403 | Conduct Root Cause Analysis | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02404 | 5.DP.SU.02404 | Conduct Preventive Maintenance | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02399 | 5.DP.SU.02399 | Install New-User Base | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02398 | 5.DP.SU.02398 | Conduct Software Upgrades and Patches | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02406 | 5.DP.SU.02406 | Develop New Applications | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02396 | 5.DP.SU.02396 | Maintain Applications | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02397 | 5.DP.SU.02397 | Meet Service Level Agreements | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02400 | 5.DP.SU.02400 | Manage Applications Delivery Performance | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02695 | 5.DP.SU.02695 | Transition Solution Documentation to Support Organization | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02405 | 5.DP.SU.02405 | Monitor Support Scope | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02343 | 5.DP.SU.02343 | Develop Applications Transition Plan | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02331 | 5.DP.SU.02331 | Confirm Hardware, Software, and Connectivity Requirements | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02395 | 5.DP.SU.02395 | Conduct Functional and Technical Post-Implementation Review | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02385 | 5.DP.SU.02385 | Conduct Applications Knowledge Transfer | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02368 | 5.DP.SU.02368 | Establish Applications Operating Processes and Procedures | No | No
5 - Go Live & Support | Deployment | Support Preparation & Stabilization | 02386 | 5.DP.SU.02386 | Conduct Applications Training | No | No
5 - Go Live & Support | Tax | Tax | 02472 | 5.TX.TX.02472 | Develop Tax Solution Satisfaction Survey | No | No
5 - Go Live & Support | Tax | Tax | 02473 | 5.TX.TX.02473 | Develop Tax Solution Project Case Study | No | No
5 - Go Live & Support | Value | Value | 02489 | 5.VL.VL.02489 | Implement Value Delivery Approach | No | No
5 - Go Live & Support | Value | Value | 02492 | 5.VL.VL.02492 | Implement Value Delivery Goals by Organization | No | No
5 - Go Live & Support | Value | Value | 02496 | 5.VL.VL.02496 | Implement Value Tracking Plan | No | No
5 - Go Live & Support | Value | Value | 02494 | 5.VL.VL.02494 | Conduct Value Delivery Gap Analysis | No | No
5 - Go Live & Support | Value | Value | 02512 | 5.VL.VL.02512 | Define Continuous Improvement Metrics | No | No
5 - Go Live & Support | Value | Value | 02491 | 5.VL.VL.02491 | Determine Continuous Improvement Opportunities | No | No
5 - Go Live & Support | Value | Value | 02514 | 5.VL.VL.02514 | Track and Assess Performance | No | No
5 - Go Live & Support | Value | Value | 02513 | 5.VL.VL.02513 | Develop Continuous Improvement Baseline and Targets | No | No
| Project Management | Plan | 00002 | 99.PM.PL.00002 | Business Milestones | No | Yes
| Project Management | Plan | 01083 | 99.PM.PL.01083 | Acquire Project Team | No | Yes
| Project Management | Manage | 00003 | 99.PM.MG.00003 | Fixed Headcount | Yes | Yes
| Project Management | Manage | 01040 | 99.PM.MG.01040 | Manage Work Plan | No | Yes
| Project Management | Manage | 01068 | 99.PM.MG.01068 | Manage Issues | No | Yes
| Project Management | Manage | 01042 | 99.PM.MG.01042 | Manage Risks | No | Yes
| Project Management | Manage | 01073 | 99.PM.MG.01073 | Manage Action Items | No | Yes
| Project Management | Manage | 01070 | 99.PM.MG.01070 | Manage Decisions | No | Yes
| Project Management | Manage | 01044 | 99.PM.MG.01044 | Manage Change Requests | No | Yes
| Project Management | Manage | 01046 | 99.PM.MG.01046 | Manage Project Status | No | Yes
| Project Management | Manage | 01048 | 99.PM.MG.01048 | Manage Non-Labor Resources | No | Yes
| Project Management | Manage | 01050 | 99.PM.MG.01050 | Manage Budget | No | Yes
| Project Management | Manage | 01089 | 99.PM.MG.01089 | Perform Deliverable Acceptance | No | Yes
| Project Management | Close | 01052 | 99.PM.CL.01052 | Close Work Plan | No | Yes
| Quality Management | Quality Control | 01090 | 99.QM.QC.01090 | Manage Deliverable Reviews and Sign-offs | No | Yes
| Quality Management | Quality Control | 01092 | 99.QM.QC.01092 | Produce Metrics | No | Yes
| Quality Management | Quality Support | 01098 | 99.QM.QS.01098 | Perform Project Reviews | No | Yes
| Quality Management | Quality Support | 01081 | 99.QM.QS.01081 | Perform Method Coaching | No | No
| Quality Management | Quality Support | 01082 | 99.QM.QS.01082 | Perform Specialist Support | No | Yes