## Metric Input for Release
Instructions:
1. Review all the metrics and update the 'Metric Quantity' column with the total number for the given metric. Complete the first tab for the 'Release' and then the second tab for the 'Rollout'.
2. Some metrics are further broken out by 'Complexity'. Use the column 'Complexity Level' to see these metrics and update 'Metric Quantities' by complexity.
3. The 'Rule of Thumb Formula' can be used to help estimate the 'Metric Quantity' if a value is unknown. It's also a good starting point.
4. The 'Notes' column can be used to update any information when gathering the 'Metric Quantities'.
5. Use the 'Formula Usage' column to understand how the metric is used to calculate other metrics.
6. Use the 'Task Usage' column to understand what tasks use the metric as an estimation input.
Note: If a value exists in the 'Metric Quantity' it's the default value. This number can be changed, but is used as a starting point.
Note: This sheet only includes the 'User Input' metrics. The calculated metrics will need to be reviewed after updating these metrics in the PEPS application.
Note: The input sheet here reflects a single release. For multiple release projects a 'Metric Quantity' needs to be defined for each release. All the metrics can be copied and a release ID can be added.
Release ID | Discipline | Sub-Discipline Name | Metric ID | Metric Name | Metric Description | Complexity Level | Metric Quantity | Rule of Thumb Formula | Notes | Formula Usage | Task Usage
R1 | Process and Application | Business Process Management | MT2101 | Process Groups (L1) | The number of in-scope process groups. It refers to the level 1 objects in the IndustryPrint hierarchy. A set of processes covering a single business area. Usually under the ownership of one business process owner and correlates to one module e.g. HR. | NA |  |  |  |  | Task Usage for Process Groups (L1): 2.CM.CP.02718 - Prepare Subject Matter Experts for Business Blueprint 2.PP.BP.01205 - Design To-Be Process Groups (L1) 3a.CM.CP.02719 - Prepare Subject Matter Experts for Realization 3b.CM.CP.02720 - Launch Super User Program
R1 | Process and Application | Business Process Management | MT2102 | Processes (L2) | The number of in-scope processes. It refers to the level 2 object in the IndustryPrint hierarchy. A process is a collection of subprocesses that meets a specific business objective e.g. HR-020 Manage Recruitment | NA |  |  |  | Formula Usage for Processes (L2): . MT2103 - SubProcesses (L3)(Rule of Thumb Formula = Processes (L2)*5, Rule of Thumb Calculation = 0) . MT2106 - # of As-Is Unique Processes(Rule of Thumb Formula = (Processes (L2)*% of Processes Unique to LOBs/100*(# of Lines of Business (LOB)-1))+Processes (L2), Rule of Thumb Calculation = 0) . MT2109 - Business Process Scenarios(Rule of Thumb Formula = Processes (L2)*3, Rule of Thumb Calculation = 0) . MT4113 - # of Financially Significant Processes(Rule of Thumb Formula = % of Financially Significant Processes*Processes (L2)/100, Rule of Thumb Calculation = 0) . MT4410 - Master Security Roles(Rule of Thumb Formula = Processes (L2)*Master Security Roles per Process, Rule of Thumb Calculation = 0) . MT6216 - Instructor-Led Training: Course Duration (Total)(Rule of Thumb Formula = Processes (L2)*6, Rule of Thumb Calculation = 0) | Task Usage for Processes (L2): 2.CM.OA.02761 - Assess Initial Change Impacts 2.PP.BP.01214 - Design To-Be Processes (L2) 2.VL.VL.00119 - Update and Refresh Business Case 3a.CM.OA.02762 - Assess Final Change Impacts 3a.CM.TR.02745 - Develop Instructor-Led Training Course Outlines 3a.VL.VL.00119 - Update and Refresh Business Case 3b.VL.VL.02489 - Update and Refresh Business Case
R1 | Process and Application | Business Process Management | MT2103 | SubProcesses (L3) | The number of in-scope subprocesses. It refers to the level 3 objects in IndustryPrint hierarchy. A subprocess is a grouping of related tasks that create an output within the larger objective of the subprocess e.g. HR-020-040: Manage requisitions | NA |  | Processes (L2)*5 |  | Formula Usage for SubProcesses (L3): . MT2104 - Tasks (L4)(Rule of Thumb Formula = SubProcesses (L3)*10, Rule of Thumb Calculation = 0) . MT2118 - Business Roles(Rule of Thumb Formula = SubProcesses (L3), Rule of Thumb Calculation = 0) . MT2401 - String Test Objects(Rule of Thumb Formula = SubProcesses (L3), Rule of Thumb Calculation = 0) | Task Usage for SubProcesses (L3): 2.PP.BP.01215 - Design To-Be SubProcesses (L3)
R1 | Process and Application | Business Process Management | MT2109 | Business Process Scenarios | Different variants of a business event. For example, an event could be "report of power off" and the scenarios could be "power disruption", "non-payment of bill", and "planned outage." | NA |  | Processes (L2)*3 |  | Formula Usage for Business Process Scenarios: . MT2403 - Integration Test Objects(Rule of Thumb Formula = Business Process Scenarios, Rule of Thumb Calculation = 0) | Task Usage for Business Process Scenarios: 2.PP.BP.01206 - Identify Business Scenarios
R1 | Process and Application | Business Process Management | MT2118 | Business Roles | Distinct from an official job title. A business role is a set of related work steps that are performed based on a level of authority. Business roles are mapped to jobs at the end of Realization Build (P3A) phase. | NA |  | SubProcesses (L3) |  |  | Task Usage for Business Roles: 2.PP.BP.01217 - Define Business Roles 3a.TE.SE.02155 - Design Production Application Security Business Roles 3a.TE.SE.02162 - Configure Production Application Security Business Roles 3b.TE.SE.00101 - Conduct Production Application Security Unit Testing (Business Roles) 3b.TE.SE.02162 - Configure Production Application Security Business Roles
R1 | Process and Application | Business Process Management | MT2107 | Interim Business Procedures | This is the number of to-be tasks that are temporary and will be replaced when end-state design is implemented. | NA |  |  |  |  | Task Usage for Interim Business Procedures: 3a.PP.BP.01216 - Develop Interim Business Procedures
R1 | Process and Application | Business Process Management | MT2111 | % of Processes Unique to LOBs | % of Processes Unique to LOBs | NA | 20 |  |  | Formula Usage for % of Processes Unique to LOBs: . MT2106 - # of As-Is Unique Processes(Rule of Thumb Formula = (Processes (L2)*% of Processes Unique to LOBs/100*(# of Lines of Business (LOB)-1))+Processes (L2), Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Management | MT2106 | # of As-Is Unique Processes | In many organizations the as-is processes are different in various locations and/or business units. If the to-be objective is to go to common processes, it is important that the unique as-is variants be understood and inventoried. This parameter drives the estimated effort to identify the legacy systems, roles, and reports against the IndustryPrint model. Initially set to the number of processes multiplied by the number of business units but this number can be reduced when common processes already exist. | NA |  | (Processes (L2)*% of Processes Unique to LOBs/100*(# of Lines of Business (LOB)-1))+Processes (L2) |  |  | Task Usage for # of As-Is Unique Processes: 2.PP.BP.01199 - Define Business Requirements 2.PP.BP.01200 - Analyze As-Is Processes
R1 | Process and Application | Business Process Management | MT2401 | String Test Objects | A test object is the subject of a test and for the functional string test it will normally equal the number of activities . | NA |  | SubProcesses (L3) |  | Formula Usage for String Test Objects: . MT2407 - String Test Cases(Rule of Thumb Formula = String Test Objects*1.5, Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Management | MT2407 | String Test Cases | Situation or scenario of a test object. | NA |  | String Test Objects*1.5 |  |  | Task Usage for String Test Cases: 3a.PP.BP.01225 - Develop String Test Cases 3a.PP.BP.01231 - Conduct String Test
R1 | Process and Application | Package Configuration | MT2202 | Package Functions (SAP Modules, Oracle Solution Sets) | The number of major system components being implemented e.g. Finance, Procurement, Inventory, Sales. SAP - FI, CO, MM, SD, etc. | NA |  |  |  |  | Task Usage for Package Functions (SAP Modules, Oracle Solution Sets): 2.PP.PK.01239 - Develop Enterprise Structure 2.PP.PK.01245 - Develop Software Control Values
R1 | Process and Application | Package Configuration | MT2203 | Package Subfunctions (SAP Submodules, Oracle Modules) | Second level of the package functional decomposition (i.e. Finance-General Ledger, Finance-Accounts Payable, Finance-Costing) | NA |  |  |  | Formula Usage for Package Subfunctions (SAP Submodules, Oracle Modules): . MT2211 - Package Transactions(Rule of Thumb Formula = Package Subfunctions (SAP Submodules, Oracle Modules)*10, Rule of Thumb Calculation = 0) . MT4424 - # of Application Modules for all System Environments/Instances(Rule of Thumb Formula = # of System Instances / Environments*Package Subfunctions (SAP Submodules, Oracle Modules), Rule of Thumb Calculation = 0) | Task Usage for Package Subfunctions (SAP Submodules, Oracle Modules): 2.PP.PK.00163 - Configure Sandbox 2.PP.PK.01238 - Conduct Software Gap Analysis 2.PP.PK.01244 - Develop Software Configuration Design 3a.PP.PK.01256 - Complete and Document Baseline Configuration 3a.PP.PK.01261 - Perform Final Configuration 3b.PP.PK.00135 - Perform Break-fix
R1 | Process and Application | Package Configuration | MT2211 | Package Transactions | Number of transaction codes across all packages used. | NA |  | Package Subfunctions (SAP Submodules, Oracle Modules)*10 |  | Formula Usage for Package Transactions: . MT2212 - Business Process Procedures (BPPs)(Rule of Thumb Formula = Package Transactions+HR Infotypes, Rule of Thumb Calculation = 0)
R1 | Process and Application | Package Configuration | MT2212 | Business Process Procedures (BPPs) | Business Process Procedures are step-by-step procedures outlining post go-live operating, maintenance and update procedures for the production system. They serve as inputs for any user training instructional material development and client specific standard operating procedure (SOP), if required. | NA |  | Package Transactions+HR Infotypes |  | Formula Usage for Business Process Procedures (BPPs): . MT6205 - # of BPP Translations - Test Phase(Rule of Thumb Formula = Additional Languages*Business Process Procedures (BPPs)*(1-(% of Training Development Effort to be Completed during Build Phase/100)), Rule of Thumb Calculation = 0) . MT6206 - # of BPP Translations - Build Phase(Rule of Thumb Formula = Additional Languages*Business Process Procedures (BPPs)*% of Training Development Effort to be Completed during Build Phase/100, Rule of Thumb Calculation = 0) | Task Usage for Business Process Procedures (BPPs): 3a.PP.BP.01229 - Develop Business Process Procedures
R1 | Process and Application | Package Configuration | MT2205 | HR Infotypes | SAP only concept where three mega-transactions in HR (PA20, PA30, PA40) are divided into many smaller transactions known as InfoTypes. | NA |  |  |  | Formula Usage for HR Infotypes: . MT2212 - Business Process Procedures (BPPs)(Rule of Thumb Formula = Package Transactions+HR Infotypes, Rule of Thumb Calculation = 0) | Task Usage for HR Infotypes: 3a.PP.PK.00040 - Perform HR Final Configuration
R1 | Process and Application | Package Configuration | MT2207 | Payroll Wage Types | Payroll Wage Types | NA |  |  |  |  | Task Usage for Payroll Wage Types: 2.PP.PK.00162 - Develop Payroll Design 3a.PP.PK.00039 - Perform Payroll Configuration
R1 | Process and Application | Package Configuration | MT2208 | Time Work Schedules | If the project has a heavy number of union employees that are paid hourly, 50+ work schedules could be required. If most workers are salaried and non-union, 10 is reasonable estimate. Document the assumption. | NA |  |  |  |  | Task Usage for Time Work Schedules: 2.PP.BP.00037 - Develop Time Design 3a.PP.PK.00038 - Perform Time Configuration
R1 | Process and Application | Business Process Controls | MT4111 | % of Financially Significant Processes | % of total number of processes that are financially significant and for which controls needs to be designed | NA | 25 |  |  | Formula Usage for % of Financially Significant Processes: . MT4113 - # of Financially Significant Processes(Rule of Thumb Formula = % of Financially Significant Processes*Processes (L2)/100, Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Controls | MT4104 | Financial Controls (1 = Yes, 0 = No) | Financial Controls are designed to ensure the fairness, accuracy, and reliability of financial data. | NA | 0 |  |  | Formula Usage for Financial Controls (1 = Yes, 0 = No): . MT4102 - # of Business Process Controls(Rule of Thumb Formula = # of Financially Significant Processes*((Financial Controls (1 = Yes, 0 = No)*Financial Controls per Business Process)+(Operational Controls (1 = Yes, 0 = No)*Operational Controls per Business Process)+(Compliance / Regulatory Controls (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process)), Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Controls | MT4107 | Financial Controls per Business Process | Financial Controls are designed to ensure the fairness, accuracy, and reliability of financial data. | NA | 5 |  |  | Formula Usage for Financial Controls per Business Process: . MT4102 - # of Business Process Controls(Rule of Thumb Formula = # of Financially Significant Processes*((Financial Controls (1 = Yes, 0 = No)*Financial Controls per Business Process)+(Operational Controls (1 = Yes, 0 = No)*Operational Controls per Business Process)+(Compliance / Regulatory Controls (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process)), Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Controls | MT4105 | Operational Controls (1 = Yes, 0 = No) | Operational Controls are designed to evaluate an area, department or functional operation. May typically be a client resource. | NA | 0 |  |  | Formula Usage for Operational Controls (1 = Yes, 0 = No): . MT4102 - # of Business Process Controls(Rule of Thumb Formula = # of Financially Significant Processes*((Financial Controls (1 = Yes, 0 = No)*Financial Controls per Business Process)+(Operational Controls (1 = Yes, 0 = No)*Operational Controls per Business Process)+(Compliance / Regulatory Controls (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process)), Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Controls | MT4109 | Operational Controls per Business Process | Operational Controls are designed to evaluate an area, department or functional operation. May typically be a client resource. | NA | 8 |  |  | Formula Usage for Operational Controls per Business Process: . MT4102 - # of Business Process Controls(Rule of Thumb Formula = # of Financially Significant Processes*((Financial Controls (1 = Yes, 0 = No)*Financial Controls per Business Process)+(Operational Controls (1 = Yes, 0 = No)*Operational Controls per Business Process)+(Compliance / Regulatory Controls (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process)), Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Controls | MT4106 | Compliance / Regulatory Controls (1 = Yes, 0 = No) | Compliance and Regulatory Controls are designed to address the specific department's adherence to laws and regulations, policies and procedures, federal and provincial requirements, and restrictions imposed on endowments and grants. May typically be a client resource. | NA | 0 |  |  | Formula Usage for Compliance / Regulatory Controls (1 = Yes, 0 = No): . MT4102 - # of Business Process Controls(Rule of Thumb Formula = # of Financially Significant Processes*((Financial Controls (1 = Yes, 0 = No)*Financial Controls per Business Process)+(Operational Controls (1 = Yes, 0 = No)*Operational Controls per Business Process)+(Compliance / Regulatory Controls (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process)), Rule of Thumb Calculation = 0)
R1 | Process and Application | Business Process Controls | MT4110 | Compliance / Regulatory Controls per Business Process | Compliance and Regulatory Controls are designed to address the specific department's adherence to laws and regulations, policies and procedures, federal and provincial requirements, and restrictions imposed on endowments and grants. May typically be a client resource. | NA | 2 |  |  | Formula Usage for Compliance / Regulatory Controls per Business Process: . MT4102 - # of Business Process Controls(Rule of Thumb Formula = # of Financially Significant Processes*((Financial Controls (1 = Yes, 0 = No)*Financial Controls per Business Process)+(Operational Controls (1 = Yes, 0 = No)*Operational Controls per Business Process)+(Compliance / Regulatory Controls (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process)), Rule of Thumb Calculation = 0)
R1 | Organizational Change Management | Organizational Alignment | MT5303 | Additional Languages | Used to calculate effort to translate material beyond 1 language. Enter Additional languages above and beyond 1. For example, Release 1 has three languages: English, Spanish, and French and Release 2 has two additional languages: Chinese and French. User would enter 2 for Release 1 and 2 for Release 2. | NA |  |  |  | Formula Usage for Additional Languages: . MT6205 - # of BPP Translations - Test Phase(Rule of Thumb Formula = Additional Languages*Business Process Procedures (BPPs)*(1-(% of Training Development Effort to be Completed during Build Phase/100)), Rule of Thumb Calculation = 0) . MT6206 - # of BPP Translations - Build Phase(Rule of Thumb Formula = Additional Languages*Business Process Procedures (BPPs)*% of Training Development Effort to be Completed during Build Phase/100, Rule of Thumb Calculation = 0) . MT6218 - Instructor-Led and Web-Based: Course Hours to be Translated (Total)(Rule of Thumb Formula = Additional Languages*(Instructor-Led Training: Course Duration (Total)+Web-Based Training: Course Duration (ALL COMPLEXITIES)), Rule of Thumb Calculation = 0) . MT6224 - Instructor-Led Training: Course Hours to be Translated(Rule of Thumb Formula = Additional Languages*Instructor-Led Training: Course Duration (Total), Rule of Thumb Calculation = 0)
R1 | Organizational Change Management | Organizational Alignment | MT5301 | Geographic Locations | Number of geographic locations where end-users will work. Used in calculating the Change Network activities. | NA |  |  |  | Formula Usage for Geographic Locations: . MT5403 - # of LOB in all geographic units(Rule of Thumb Formula = # of Lines of Business (LOB)*Geographic Locations, Rule of Thumb Calculation = 0) | Task Usage for Geographic Locations: 2.CM.CP.02714 - Launch Change Network
R1 | Organizational Change Management | Organizational Alignment | MT5302 | # of Lines of Business (LOB) | To be defined as the major lines of business of an organization that will have unique processes in certain areas. For ex: Energy Industry: Distribution, Generation; Hi-Tech Industry: Product, Services. This is not the organizational structure such as, AP, AR, Sales, etc. | NA |  |  |  | Formula Usage for # of Lines of Business (LOB): . MT2106 - # of As-Is Unique Processes(Rule of Thumb Formula = (Processes (L2)*% of Processes Unique to LOBs/100*(# of Lines of Business (LOB)-1))+Processes (L2), Rule of Thumb Calculation = 0) . MT5403 - # of LOB in all geographic units(Rule of Thumb Formula = # of Lines of Business (LOB)*Geographic Locations, Rule of Thumb Calculation = 0) | Task Usage for # of Lines of Business (LOB): 3b.CM.OA.02765 - Develop Go-Live Transition Guides
R1 | Organizational Change Management | Organizational Alignment | MT5307 | Named End Users | This is the number of people who will be actively using the ERP system and will need security and role-mapping. Include users who perform data input, systems maintenance, and other primary tasks. Active users may also be known as super users, reporting users, and regular users. May also need to include external users, such as Suppliers. Do not include passive or occasional users such as self-service, payroll counts or time recording users. | NA |  |  |  |  | Task Usage for Named End Users: 3a.CM.OA.02768 - Perform Role-to-Position Mapping 3b.TE.SE.02189 - Identify Production Users (Review Role to Position Mapping doc [PCL])
R1 | Organizational Change Management | Capability Transfer | MT5101 | Peak Team Size (Client) | This metric is used to estimate capability transfer tasks needed to be performed for client members. Make certain this number includes an estimate of both the fixed client resources and the variable client resources. The metric can be determined based on client FTEs in the FTE report once all resources and metrics have been entered. | NA |  |  |  | Formula Usage for Peak Team Size (Client): . MT4405 - Peak Team Size (Client & Deloitte)(Rule of Thumb Formula = Peak Team Size (Client)+Peak Team Size (Deloitte), Rule of Thumb Calculation = 0) | Task Usage for Peak Team Size (Client): 2.CM.CT.02703 - Develop Project Team Member Capability Transfer Plans 2.CM.CT.02701 - Initiate Project Team Capability Transfer 3b.CM.CT.02704 - Assess Project Team Capability Transfer
R1 | Organizational Change Management | Capability Transfer | MT5102 | Peak Team Size (Deloitte) | This metric is used to estimate the Non-Production Application Security Users and Roles for Deloitte. Make certain this number includes an estimate of both the fixed Deloitte resources and the variable Deloitte resources. The metric can be determined based on Deloitte FTEs in the FTE report once all resources and metrics have been entered. | NA |  |  |  | Formula Usage for Peak Team Size (Deloitte): . MT4405 - Peak Team Size (Client & Deloitte)(Rule of Thumb Formula = Peak Team Size (Client)+Peak Team Size (Deloitte), Rule of Thumb Calculation = 0)
R1 | Organizational Change Management | End-User Training | MT6212 | % of Training Development Effort to be Completed during Build Phase | Determines how to spilt the training development effort between the Build and Test phase. | NA | 50 |  |  | Formula Usage for % of Training Development Effort to be Completed during Build Phase: . MT6201 - Instructor-Led Training: Course Duration (Build Phase)(Rule of Thumb Formula = % of Training Development Effort to be Completed during Build Phase*Instructor-Led Training: Course Duration (Total)/100, Rule of Thumb Calculation = 0) . MT6205 - # of BPP Translations - Test Phase(Rule of Thumb Formula = Additional Languages*Business Process Procedures (BPPs)*(1-(% of Training Development Effort to be Completed during Build Phase/100)), Rule of Thumb Calculation = 0) . MT6206 - # of BPP Translations - Build Phase(Rule of Thumb Formula = Additional Languages*Business Process Procedures (BPPs)*% of Training Development Effort to be Completed during Build Phase/100, Rule of Thumb Calculation = 0) . MT6213 - Instructor-Led Training: Course Duration (Test Phase)(Rule of Thumb Formula = Instructor-Led Training: Course Duration (Total)*(1-(% of Training Development Effort to be Completed during Build Phase/100)), Rule of Thumb Calculation = 0)
R1 | Organizational Change Management | End-User Training | MT6216 | Instructor-Led Training: Course Duration (Total) | The total estimated duration of all Instructor-Led Training courses. | NA |  | Processes (L2)*6 |  | Formula Usage for Instructor-Led Training: Course Duration (Total): . MT6201 - Instructor-Led Training: Course Duration (Build Phase)(Rule of Thumb Formula = % of Training Development Effort to be Completed during Build Phase*Instructor-Led Training: Course Duration (Total)/100, Rule of Thumb Calculation = 0) . MT6213 - Instructor-Led Training: Course Duration (Test Phase)(Rule of Thumb Formula = Instructor-Led Training: Course Duration (Total)*(1-(% of Training Development Effort to be Completed during Build Phase/100)), Rule of Thumb Calculation = 0) . MT6218 - Instructor-Led and Web-Based: Course Hours to be Translated (Total)(Rule of Thumb Formula = Additional Languages*(Instructor-Led Training: Course Duration (Total)+Web-Based Training: Course Duration (ALL COMPLEXITIES)), Rule of Thumb Calculation = 0) . MT6224 - Instructor-Led Training: Course Hours to be Translated(Rule of Thumb Formula = Additional Languages*Instructor-Led Training: Course Duration (Total), Rule of Thumb Calculation = 0) | Task Usage for Instructor-Led Training: Course Duration (Total): 3a.CM.TR.02749 - Develop Instructor-Led Training Courseware 3b.CM.TR.02749 - Develop Instructor-Led Training Courseware 3b.CM.TR.02757 - Build Training Environment and Training Data 3b.CM.TR.02760 - Conduct Train-the-Trainer Program
R1 | Organizational Change Management | End-User Training | MT6217 | Web-Based Training: Course Duration (by complexity) | The total number of hours of web-based end-user courses to be developed. Consider web based training for SAP Navigation and Business Process Overviews. Default to 5 course hours | Simple
R1 | Organizational Change Management | End-User Training | MT6217 | Web-Based Training: Course Duration (by complexity) | The total number of hours of web-based end-user courses to be developed. Consider web based training for SAP Navigation and Business Process Overviews. Default to 5 course hours | Medium
R1 | Organizational Change Management | End-User Training | MT6217 | Web-Based Training: Course Duration (by complexity) | The total number of hours of web-based end-user courses to be developed. Consider web based training for SAP Navigation and Business Process Overviews. Default to 5 course hours | Complex
R1 | Organizational Change Management | End-User Training | MT6217 | Web-Based Training: Course Duration (by complexity) | The total number of hours of web-based end-user courses to be developed. Consider web based training for SAP Navigation and Business Process Overviews. Default to 5 course hours | Very Complex
R1 | Information Management | Master Data Management | MT3204 | Legacy Master Data Objects | Defines the number of different master data versions within the organization (i.e. the number of unique material files or unique customer files) that need to be reconciled during the project. User must first determines the in-scope Master Data objects. Refer to the Input Template -->PP-Master Data tab for assistance in deriving the Master Data objects. Then estimate the number of sources for each Master Data object. Input the total number of sources for all Master Data objects. Example: If I have multiple business units , 3, then would have to look in each one of those 3 in order to reconcile and convert. Input 3 | NA |  |  |  | Formula Usage for Legacy Master Data Objects: . MT3231 - # of Legacy Master Data Files Requiring Cleanup(Rule of Thumb Formula = Legacy Master Data Objects*% of Legacy Master Data Files Requiring Cleanup/100, Rule of Thumb Calculation = 0) | Task Usage for Legacy Master Data Objects: 2.IM.IQ.01772 - Develop Data Cleansing Approach 2.IM.IQ.01789 - Perform Legacy Data Analysis
R1 | Information Management | Master Data Management | MT3230 | % of Legacy Master Data Files Requiring Cleanup | % of Legacy Master Data Files Requiring Cleanup | NA |  |  |  | Formula Usage for % of Legacy Master Data Files Requiring Cleanup: . MT3231 - # of Legacy Master Data Files Requiring Cleanup(Rule of Thumb Formula = Legacy Master Data Objects*% of Legacy Master Data Files Requiring Cleanup/100, Rule of Thumb Calculation = 0)
R1 | Information Management | Master Data Management | MT2301 | Package Data Objects (To-Be) | Use to estimate the effort to design and configure the master data objects (i.e. customer, employee, vendor) of the package(s). Count customer table as 1 and vendor table as 1. | NA |  |  |  |  | Task Usage for Package Data Objects (To-Be): 2.IM.MD.01521 - Develop To-Be Master Data Design
R1 | Information Management | Business Intelligence & Data Warehousing | MT2501 | Information Requirements | Operational or analytical data that is required by any level of users in an organization regardless of reporting medium or tool (i.e. Excel reports, Legacy reports , Print-out Reports, HTML views) | NA |  |  |  |  | Task Usage for Information Requirements: 2.IM.BI.00169 - Define To-Be Requirements List
R1 | Information Management | Business Intelligence & Data Warehousing | MT2505 | Info Providers by complexity | Multiple linked tables that structure and store data (facts and characteristics) in BI. Zero to Minimal configuration effort is needed. Enter the number of standard un-modified Info Providers planned to be used on the project. | Simple
R1 | Information Management | Business Intelligence & Data Warehousing | MT2505 | Info Providers by complexity | Multiple linked tables that structure and store data (facts and characteristics) in BI. Zero to Minimal configuration effort is needed. Enter the number of standard un-modified Info Providers planned to be used on the project. | Medium
R1 | Information Management | Business Intelligence & Data Warehousing | MT2505 | Info Providers by complexity | Multiple linked tables that structure and store data (facts and characteristics) in BI. Zero to Minimal configuration effort is needed. Enter the number of standard un-modified Info Providers planned to be used on the project. | Complex
R1 | Information Management | Business Intelligence & Data Warehousing | MT2505 | Info Providers by complexity | Multiple linked tables that structure and store data (facts and characteristics) in BI. Zero to Minimal configuration effort is needed. Enter the number of standard un-modified Info Providers planned to be used on the project. | Very Complex
R1 | Information Management | Business Intelligence & Data Warehousing | MT2502 | BI Reports by complexity | A report created to allow a multitude of analytical uses. Users will leverage template to satisfy many combinations of analytical reporting needs. The report template provides a constant set of data and the default layout structure. | Simple
R1 | Information Management | Business Intelligence & Data Warehousing | MT2502 | BI Reports by complexity | A report created to allow a multitude of analytical uses. Users will leverage template to satisfy many combinations of analytical reporting needs. The report template provides a constant set of data and the default layout structure. | Medium
R1 | Information Management | Business Intelligence & Data Warehousing | MT2502 | BI Reports by complexity | A report created to allow a multitude of analytical uses. Users will leverage template to satisfy many combinations of analytical reporting needs. The report template provides a constant set of data and the default layout structure. | Complex
R1 | Information Management | Business Intelligence & Data Warehousing | MT2502 | BI Reports by complexity | A report created to allow a multitude of analytical uses. Users will leverage template to satisfy many combinations of analytical reporting needs. The report template provides a constant set of data and the default layout structure. | Very Complex
R1 | Development | Application Development | MT3205 | Programming Languages | Used to determine the number of programming standards to be developed. Enter ADDITIONAL languages in each subsequent release if relevant. | NA |  |  |  |  | Task Usage for Programming Languages: 2.DV.AD.01881 - Define Software Development Standards and Guidelines
R1 | Development | Application Development | MT3229 | Reports (non-BI): By Complexity | The number of custom reports. It will not be produced in the Business Intelligence tool (i.e. BEx , Cognos). For Oracle it needs to include the number of formatted "documents". | Simple
R1 | Development | Application Development | MT3229 | Reports (non-BI): By Complexity | The number of custom reports. It will not be produced in the Business Intelligence tool (i.e. BEx , Cognos). For Oracle it needs to include the number of formatted "documents". | Medium
R1 | Development | Application Development | MT3229 | Reports (non-BI): By Complexity | The number of custom reports. It will not be produced in the Business Intelligence tool (i.e. BEx , Cognos). For Oracle it needs to include the number of formatted "documents". | Complex
R1 | Development | Application Development | MT3229 | Reports (non-BI): By Complexity | The number of custom reports. It will not be produced in the Business Intelligence tool (i.e. BEx , Cognos). For Oracle it needs to include the number of formatted "documents". | Very Complex
R1 | Development | Application Development | MT3233 | Point-to-Point Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. Note: Excludes interfaces between 2 SAP or Oracle applications. | Simple
R1 | Development | Application Development | MT3233 | Point-to-Point Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. Note: Excludes interfaces between 2 SAP or Oracle applications. | Medium
R1 | Development | Application Development | MT3233 | Point-to-Point Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. Note: Excludes interfaces between 2 SAP or Oracle applications. | Complex
R1 | Development | Application Development | MT3233 | Point-to-Point Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. Note: Excludes interfaces between 2 SAP or Oracle applications. | Very Complex
R1 | Development | Application Development | MT3237 | Middleware Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. This metric pertains to interface units of work related to middleware. | Simple
R1 | Development | Application Development | MT3237 | Middleware Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. This metric pertains to interface units of work related to middleware. | Medium
R1 | Development | Application Development | MT3237 | Middleware Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. This metric pertains to interface units of work related to middleware. | Complex
R1 | Development | Application Development | MT3237 | Middleware Interfaces: By Complexity | An interface unit of work is defined as a uni-directional passing of data from one system to another. This metric pertains to interface units of work related to middleware. | Very Complex
R1 | Development | Application Development | MT3241 | Automated Conversions: By Complexity | A conversion is defined as a single legacy system file to a single to-be file. | Simple
R1 | Development | Application Development | MT3241 | Automated Conversions: By Complexity | A conversion is defined as a single legacy system file to a single to-be file. | Medium
R1 | Development | Application Development | MT3241 | Automated Conversions: By Complexity | A conversion is defined as a single legacy system file to a single to-be file. | Complex
R1 | Development | Application Development | MT3241 | Automated Conversions: By Complexity | A conversion is defined as a single legacy system file to a single to-be file. | Very Complex
R1 | Development | Application Development | MT3245 | Enhancements: By Complexity | Enhancements to the package that modifies existing functionality. May include new transactions, programs, tables, user exits, etc. Do not count custom reports or forms since these are counted separately. | Simple
R1 | Development | Application Development | MT3245 | Enhancements: By Complexity | Enhancements to the package that modifies existing functionality. May include new transactions, programs, tables, user exits, etc. Do not count custom reports or forms since these are counted separately. | Medium
R1 | Development | Application Development | MT3245 | Enhancements: By Complexity | Enhancements to the package that modifies existing functionality. May include new transactions, programs, tables, user exits, etc. Do not count custom reports or forms since these are counted separately. | Complex
R1 | Development | Application Development | MT3245 | Enhancements: By Complexity | Enhancements to the package that modifies existing functionality. May include new transactions, programs, tables, user exits, etc. Do not count custom reports or forms since these are counted separately. | Very Complex
R1 | Development | Application Development | MT3295 | Hardcopy Forms: By Complexity | SAP definition of a hard-copy report onto a specific form. On other packages such as Oracle, do not confuse this item with screen forms. Examples of forms include Sales Orders, Purchase Orders, etc. | Simple
R1 | Development | Application Development | MT3295 | Hardcopy Forms: By Complexity | SAP definition of a hard-copy report onto a specific form. On other packages such as Oracle, do not confuse this item with screen forms. Examples of forms include Sales Orders, Purchase Orders, etc. | Medium
R1 | Development | Application Development | MT3295 | Hardcopy Forms: By Complexity | SAP definition of a hard-copy report onto a specific form. On other packages such as Oracle, do not confuse this item with screen forms. Examples of forms include Sales Orders, Purchase Orders, etc. | Complex
R1 | Development | Application Development | MT3295 | Hardcopy Forms: By Complexity | SAP definition of a hard-copy report onto a specific form. On other packages such as Oracle, do not confuse this item with screen forms. Examples of forms include Sales Orders, Purchase Orders, etc. | Very Complex
R1 | Development | Application Development | MT3249 | Workflows: By Complexity | Workflow involves the automatic routing of a document via email to support business processes e.g. approval e-mail as part of a purchase approval process. Provide the number of workflows to be configured. | Simple
R1 | Development | Application Development | MT3249 | Workflows: By Complexity | Workflow involves the automatic routing of a document via email to support business processes e.g. approval e-mail as part of a purchase approval process. Provide the number of workflows to be configured. | Medium
R1 | Development | Application Development | MT3249 | Workflows: By Complexity | Workflow involves the automatic routing of a document via email to support business processes e.g. approval e-mail as part of a purchase approval process. Provide the number of workflows to be configured. | Complex
R1 | Development | Application Development | MT3249 | Workflows: By Complexity | Workflow involves the automatic routing of a document via email to support business processes e.g. approval e-mail as part of a purchase approval process. Provide the number of workflows to be configured. | Very Complex
R1 | Development | Application Development | MT3214 | EDI Transactions Types | Electronic Data Interchange (EDI) refers to a method of exchanging data among different companies. Enter the types of documents that are planned to be exchanged automatically with third-parties. | NA |  |  |  | Formula Usage for EDI Transactions Types: . MT3224 - EDI Transactions: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*EDI Transactions Types, Rule of Thumb Calculation = 0) | Task Usage for EDI Transactions Types: 2.DV.AD.00064 - Develop Functional Specifications (EDI) 3a.DV.AD.00065 - Develop Technical Specifications (EDI) 3a.DV.AD.00070 - Develop Software Code (EDI) 3a.DV.AD.00087 - Conduct Functional Unit Test (EDI) 3a.DV.AD.00172 - Prepare and Conduct Technical Unit Test (EDI)
R1 | Development | Portal Development | MT3317 | Portal Complexity Level | Translates the Portal Complexity Level to a value which is used for a majority of IT Portal Activities (P2-P3a) | Simple
R1 | Development | Portal Development | MT3317 | Portal Complexity Level | Translates the Portal Complexity Level to a value which is used for a majority of IT Portal Activities (P2-P3a) | Medium
R1 | Development | Portal Development | MT3317 | Portal Complexity Level | Translates the Portal Complexity Level to a value which is used for a majority of IT Portal Activities (P2-P3a) | Complex
R1 | Development | Portal Development | MT3317 | Portal Complexity Level | Translates the Portal Complexity Level to a value which is used for a majority of IT Portal Activities (P2-P3a) | Very Complex
R1 | Development | Portal Development | MT3312 | SAP and non-SAP Systems to Connect to Portal | Number of SAP and non-SAP that portal connects to for transaction interface | NA |  |  |  |  | Task Usage for SAP and non-SAP Systems to Connect to Portal: 3a.DV.PO.01955 - Build Federated Portal
R1 | Development | Portal Development | MT3302 | Standard iViews | An iView is a program that calls up data from any information source, and outputs this data in the content area of the SAP portal. Simple iViews based on SAP-provided out of the box templates (e.g. KM, URL, Web GUI Transaction, BSP iViews) requiring low effort. Estimate depends on the number of portal "tabs" and amount of content iViews/pages to be developed and/or migrated. Typical estimates: 50-100 iViews for small site, 100-500 for a medium sized site, 500-5000 for a large or externally facing portal. In this tool, the content web pages are treated synonymous with standard iViews. | NA |  |  |  |  | Task Usage for Standard iViews: 3a.DV.PO.01954 - Develop and Migrate Portal Content
R1 | Development | Portal Development | MT3307 | Business Packages | Business packages are SAP provided pre-packaged, role-based GUI’s for completing SAP business transactional tasks and workflows in Portal | NA |  |  |  |  | Task Usage for Business Packages: 2.DV.PO.01943 - Design Portal Business Package 2.DV.PO.00008 - Install Business Packages (out-of-the-box)
R1 | Development | Portal Development | MT3310 | Business Package iViews | iViews based on SAP-provided Business Packages in "Content Provided by SAP" folder (e.g. ESS, MSS, SRM iViews) Involve medium-very high design & configuration iterations. Not all iViews may be implemented. ESS has ~70 iViews, MSS has ~125 iViews, SRM has ~180 iViews. | NA |  |  |  | Formula Usage for Business Package iViews: . MT3405 - Business Package iViews Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Business Package iViews, Rule of Thumb Calculation = 0)
R1 | Development | Portal Development | MT3303 | Custom iViews: Web DynPro | Custom enhancements (E in RICEFW) developed in one of the portal programming frameworks - Web DynPro Java or PDK. Typically medium-high effort. The number of custom components depends on the level of customization involved. Typically 20-40 Web DynPro iViews for Employee HCM Portal, 20-60 for External Portal. | NA |  |  |  | Formula Usage for Custom iViews: Web DynPro: . MT3306 - Custom iViews: Total(Rule of Thumb Formula = Custom iViews: Web DynPro+Custom iViews: Visual Composer+Custom iViews: Interactive Forms+Custom iViews: Knowledge Management, Rule of Thumb Calculation = 0) . MT3313 - Custom iViews: Web DynPro Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Web DynPro, Rule of Thumb Calculation = 0)
R1 | Development | Portal Development | MT3304 | Custom iViews: Visual Composer | Custom enhancements (E in RICEFW) developed in Visual Composer portal programming frameworks. Typically medium-low effort. The number of custom components depends on the level of customization involved. Typically 10-20 Web DynPro iViews for Employee HCM Portal, 10-30 for BI Portal. | NA |  |  |  | Formula Usage for Custom iViews: Visual Composer: . MT3306 - Custom iViews: Total(Rule of Thumb Formula = Custom iViews: Web DynPro+Custom iViews: Visual Composer+Custom iViews: Interactive Forms+Custom iViews: Knowledge Management, Rule of Thumb Calculation = 0) . MT3314 - Custom iViews: Visual Composer Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Visual Composer, Rule of Thumb Calculation = 0)
R1 | Development | Portal Development | MT3305 | Custom iViews: Interactive Forms | Custom enhancements (E in RICEFW) developed using Adobe Interactive Forms programming framework. Typically medium-high effort. The number of custom components depends on the level of customization involved. Typically 5-10 for small sites, 10-20 for medium sites and more than 50 for large web sites. | NA |  |  |  | Formula Usage for Custom iViews: Interactive Forms: . MT3306 - Custom iViews: Total(Rule of Thumb Formula = Custom iViews: Web DynPro+Custom iViews: Visual Composer+Custom iViews: Interactive Forms+Custom iViews: Knowledge Management, Rule of Thumb Calculation = 0) . MT3315 - Custom iViews: Interactive Forms Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Interactive Forms, Rule of Thumb Calculation = 0)
R1 | Development | Portal Development | MT3402 | Custom iViews: Knowledge Management | Custom enhancements (E in RICEFW) developed using Knowledge Management framework. Typically medium-high effort. The number of custom components depends on the level of customization involved. | NA |  |  |  | Formula Usage for Custom iViews: Knowledge Management: . MT3306 - Custom iViews: Total(Rule of Thumb Formula = Custom iViews: Web DynPro+Custom iViews: Visual Composer+Custom iViews: Interactive Forms+Custom iViews: Knowledge Management, Rule of Thumb Calculation = 0) . MT3404 - Custom iViews: KM Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Knowledge Management, Rule of Thumb Calculation = 0)
R1 | Development | Legacy System Development | MT3201 | Legacy Systems to Be Replaced | The number of legacy systems to be replaced. | NA |  |  |  | Formula Usage for Legacy Systems to Be Replaced: . MT3216 - Legacy Systems to Be Interfaced or Replaced(Rule of Thumb Formula = Legacy Systems to Be Replaced+Legacy Systems to Be Interfaced, Rule of Thumb Calculation = 0) . MT4301 - Legacy Requiring Data Controls(Rule of Thumb Formula = Legacy Systems to Be Replaced+Legacy Systems to Be Interfaced, Rule of Thumb Calculation = 0)
R1 | Development | Legacy System Development | MT3202 | Legacy Systems to Be Interfaced | The number of legacy systems to interface to. This value is also used for guidance on a default number of DBAs in the resources section -- guidance is 1.5 DBA for every 4 environments. You may increase this default as needed for larger projects. | NA |  |  |  | Formula Usage for Legacy Systems to Be Interfaced: . MT3216 - Legacy Systems to Be Interfaced or Replaced(Rule of Thumb Formula = Legacy Systems to Be Replaced+Legacy Systems to Be Interfaced, Rule of Thumb Calculation = 0) . MT4301 - Legacy Requiring Data Controls(Rule of Thumb Formula = Legacy Systems to Be Replaced+Legacy Systems to Be Interfaced, Rule of Thumb Calculation = 0) | Task Usage for Legacy Systems to Be Interfaced: 2.DV.DC.02005 - Design Interface Control Framework
R1 | Development | Legacy System Development | MT3203 | Legacy Systems to Be Modified | The number of legacy systems that require changes before conversion or interfaces are turned on. | NA |  |  |  | Formula Usage for Legacy Systems to Be Modified: . MT3225 - Legacy Systems to Be Modified Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Legacy Systems to Be Modified, Rule of Thumb Calculation = 0) | Task Usage for Legacy Systems to Be Modified: 2.DV.LS.00164 - Identify Legacy System Modifications 3a.DV.LS.00067 - Develop Technical Specifications (Legacy System) 3a.DV.LS.00073 - Develop Software Code (Legacy) 3a.DV.LS.00089 - Perform Functional Unit Test (Legacy System)
R1 | Development | Development Controls | MT4306 | % of Financially Significant Data Conversion Controls | % of Data conversion controls that are financially significant. | NA | 25 |  |  | Formula Usage for % of Financially Significant Data Conversion Controls: . MT4307 - # of Financially Significant Data Conversion Controls(Rule of Thumb Formula = % of Financially Significant Data Conversion Controls*Automated Conversions: Total/100, Rule of Thumb Calculation = 0)
R1 | Technology | Logical Infrastructure | MT4422 | % of System Instances requiring Non Prod App Support |  | NA | 50 |  |  | Formula Usage for % of System Instances requiring Non Prod App Support: . MT4423 - # of Project Team Members for System Instances requiring Non Prod App Support(Rule of Thumb Formula = % of System Instances requiring Non Prod App Support*# of Project Team Members for all System Instances/100, Rule of Thumb Calculation = 0)
R1 | Technology | Logical Infrastructure | MT3101 | # of System Instances / Environments | The number of concurrent environments to be maintained by a database administrator (could include development, testing, QA, production, training, etc.). A typical default value would be six environments. The environments are assumed to be configured "from the ground up." This value is also used for guidance on a default number of DBAs in the resources section -- guidance is 1.5 DBA for every 4 environments. You may increase this default as needed for larger projects. | NA | 1 |  |  | Formula Usage for # of System Instances / Environments: . MT4421 - # of Project Team Members for all System Instances(Rule of Thumb Formula = # of System Instances / Environments*Peak Team Size (Client & Deloitte), Rule of Thumb Calculation = 0) . MT4424 - # of Application Modules for all System Environments/Instances(Rule of Thumb Formula = # of System Instances / Environments*Package Subfunctions (SAP Submodules, Oracle Modules), Rule of Thumb Calculation = 0)
R1 | Technology | Technology Controls | MT4201 | IT Controls per Technical Process | Assumption (based on best practices) for the number of IT Controls needed per technical process. | NA | 3 |  |  | Formula Usage for IT Controls per Technical Process: . MT4202 - IT Controls(Rule of Thumb Formula = Technical Processes*IT Controls per Technical Process, Rule of Thumb Calculation = 0)
R1 | Technology | Technology Controls | MT4203 | Technical Processes | Number of technical processes (e.g. System and Data backup, Data archiving, System administration). The IT Controls are determine based on the number of Technical Processes (Technical Processes * IT Controls per Technical Process). The Metric Quantity will eventually affect the effort for the Design & Develop Information Technology Control Framework, and Unit Test Information Technology Control Activities. Please refer to the "Other" tab in the Detailed End Product screen for a complete list of the technical processes. From this tab, technical processes can be selected as in scope. | NA |  |  |  | Formula Usage for Technical Processes: . MT4202 - IT Controls(Rule of Thumb Formula = Technical Processes*IT Controls per Technical Process, Rule of Thumb Calculation = 0)
R1 | Technology | Application Security | MT4401 | Master Security Roles per Process | Multiplier used to calculate the number of master roles. Default value is 3 but allows user to configure it to a different value as needed. | NA | 3 |  |  | Formula Usage for Master Security Roles per Process: . MT4410 - Master Security Roles(Rule of Thumb Formula = Processes (L2)*Master Security Roles per Process, Rule of Thumb Calculation = 0)
R1 | Technology | Application Security | MT4410 | Master Security Roles | Master (security) roles are collections of transactions which are defined by and within each Business Process. Master roles are templates and usually not assigned to users unless there is no derived role restriction requirements. All master roles are designed to be free from segregation of duty conflicts. Example: Buyer | NA |  | Processes (L2)*Master Security Roles per Process |  |  | Task Usage for Master Security Roles: 3a.TE.SE.00099 - Conduct Production Application Security Design Workshop (Design Master Roles) 3a.TE.SE.02165 - Configure Production Application Security (Configure Master Roles) 3b.TE.SE.00100 - Conduct Production Application Security Unit Testing (Master Roles / Responsibilities) 3b.TE.SE.02171 - Develop Production Application Security Unit Test Scripts 3b.TE.SE.02183 - Develop Production Application Security Test Tracker
R1 | Technology | Application Security | MT4404 | Derived Roles | Typically , there are a minimum of 10 derived roles per master and a max of 30 derived per master. Derived roles inherit characteristics from their master role, such as transactions, menu structures, field values, and other pieces of authorization information. They will have the identical set of transactions to the master role it was derived from but have restrictions for organizational unit values (plants, company codes, etc.) or functional values (order type, etc.) Example: Buyer for Purchasing Organization 912, Buyer for Purchasing Organization 790 Cope of the master role with the organization or functional restriction. Organizational would be plant or company code. Functional would be order type, purchasing document. | NA |  |  |  |  | Task Usage for Derived Roles: 3a.TE.SE.00098 - Conduct Production Application Security Design Workshop (Derived Roles) 3a.TE.SE.02166 - Configure Production Application Security Derived Roles 3b.TE.SE.02166 - Configure Production Application Security Derived Roles
R1 | Technology | Application Security | MT4416 | # of Production Support Security Staff | number of production security support team members | NA |  |  |  |  | Task Usage for # of Production Support Security Staff: 3b.TE.SE.02187 - Configure Production Application Support Security
R1 | Deployment | Readiness Testing | MT2403 | Integration Test Objects | The number of integration test objects should equal the number of event scenarios however each project may choose to refine this number directly. | NA |  | Business Process Scenarios |  | Formula Usage for Integration Test Objects: . MT2413 - Integration Test Cases(Rule of Thumb Formula = Integration Test Objects*8, Rule of Thumb Calculation = 0) . MT2418 - Integration Test Cases by Rollout(Rule of Thumb Formula = Integration Test Objects*8, Rule of Thumb Calculation = 0)
R1 | Deployment | Readiness Testing | MT2413 | Integration Test Cases | The number of integration test cases is the number of test objects times 8 | NA |  | Integration Test Objects*8 |  | Formula Usage for Integration Test Cases: . MT2414 - Integration Test Executions(Rule of Thumb Formula = Integration Test Cases*Integration Test Cycles, Rule of Thumb Calculation = 0) . MT2426 - User Acceptance Test Cases(Rule of Thumb Formula = Integration Test Cases*% of Integration Test Cases Executed in User Acceptance Test/100, Rule of Thumb Calculation = 0) | Task Usage for Integration Test Cases: 3a.DP.RE.02414 - Develop Integration Test Cases
R1 | Deployment | Readiness Testing | MT2405 | Integration Test Cycles | An integration test cycle is defined as an execution of all test cases and generally includes the execution of the Cutover plan. Enter the number of test cycles that are planned. | NA | 3 |  |  | Formula Usage for Integration Test Cycles: . MT2414 - Integration Test Executions(Rule of Thumb Formula = Integration Test Cases*Integration Test Cycles, Rule of Thumb Calculation = 0) . MT3313 - Custom iViews: Web DynPro Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Web DynPro, Rule of Thumb Calculation = 0) . MT3314 - Custom iViews: Visual Composer Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Visual Composer, Rule of Thumb Calculation = 0) . MT3315 - Custom iViews: Interactive Forms Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Interactive Forms, Rule of Thumb Calculation = 0) . MT3404 - Custom iViews: KM Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Custom iViews: Knowledge Management, Rule of Thumb Calculation = 0) . MT3405 - Business Package iViews Integration Test Executions(Rule of Thumb Formula = Integration Test Cycles*Business Package iViews, Rule of Thumb Calculation = 0)
R1 | Deployment | Readiness Testing | MT3215 | FRICEW Test Support Multiplier | This metric is the average number of times each FRICEW object will be tested over the course of all Integration Test cycles. It is used to determine the number of Integration Test Executions to be performed on each FRICEW object type. In the calculation, this metric is multiplied by the number of FRICEW objects (e.g. Automated Conversions: Total Integration Test Executions = FRICEW Test Support Multiplier * Automated Conversions: Total). The metric for Total Integration Test Executions then drives the effort for the 'Support Integration Test' tasks (e.g. Support Integration Test (Conversion)). | NA | 3 |  |  | Formula Usage for FRICEW Test Support Multiplier: . MT3217 - Hardcopy Forms: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Hardcopy Forms: Total, Rule of Thumb Calculation = 0) . MT3218 - Reports (non-BI): Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Reports (non-BI): Total, Rule of Thumb Calculation = 0) . MT3219 - Point-to-Point Interfaces: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Point-to-Point Interfaces: Total, Rule of Thumb Calculation = 0) . MT3220 - Middleware Interfaces: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Middleware Interfaces: Total, Rule of Thumb Calculation = 0) . MT3221 - Automated Conversions: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Automated Conversions: Total, Rule of Thumb Calculation = 0) . MT3222 - Enhancements: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Enhancements: Total, Rule of Thumb Calculation = 0) . MT3223 - Workflows: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Workflows: Total, Rule of Thumb Calculation = 0) . MT3224 - EDI Transactions: Total Integration Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*EDI Transactions Types, Rule of Thumb Calculation = 0) . MT3225 - Legacy Systems to Be Modified Test Executions(Rule of Thumb Formula = FRICEW Test Support Multiplier*Legacy Systems to Be Modified, Rule of Thumb Calculation = 0)
R1 | Deployment | Readiness Testing | MT2408 | % of Integration Test Cases Executed in User Acceptance Test | User acceptance or Day in the Life testing involves execution of key transactions. Please enter the % of integration test cases expected to be executed in this phase of testing. | NA | 10 |  |  | Formula Usage for % of Integration Test Cases Executed in User Acceptance Test: . MT2426 - User Acceptance Test Cases(Rule of Thumb Formula = Integration Test Cases*% of Integration Test Cases Executed in User Acceptance Test/100, Rule of Thumb Calculation = 0)

## Metric Input for Rollout
Instructions:
1. The following metrics are specific to a 'Rollout' or the 'Final Preparation' phase of a project. Complete the 'Metric Quantizes' as you did for the release metrics on the first tab.
Note: For a single release and a single rollout many of these metrics will be the same from the first tab. Update the 'Metric Quantity' with the same information from the first tab for duplicates.
Note: The sheet is setup for a single release and single rollout. If you have additional rollouts then the metrics need to be copied and for the additional rollouts. The metric quantities should then be broken out by the specific rollout.
Release ID | Rollout ID | Discipline | Sub-Discipline Name | Metric ID | Metric Name | Metric Description | Complexity Level | Metric Quantity | Formula | Notes | Formula Usage | Task Usage
R1 | RO1 | Process and Application | Business Process Management | MT2198 | Processes by Rollout (L2) | The number of in-scope processes for the rollout. It refers to the level 2 object in the IndustryPrint hierarchy. A process is a collection of subprocesses that meets a specific business objective e.g. HR-020 Manage Recruitment | NA |  |  |  | Formula Usage for Processes by Rollout (L2): . MT4114 - # of Financially Significant Processes by Rollout(Rule of Thumb Formula = % of Financially Significant Processes by Rollout*Processes by Rollout (L2)/100, Rule of Thumb Calculation = 0) | Task Usage for Processes by Rollout (L2): 4.VL.VL.00119 - Update and Refresh Business Case
R1 | RO1 | Process and Application | Package Configuration | MT2209 | Package Functions by Rollout | The number of major system components being implemented by rollout e.g. Finance, Procurement, Inventory, Sales. SAP - FI, CO, MM, SD, etc. | NA |  |  |  |  | Task Usage for Package Functions by Rollout: 4.TE.SE.02191 - Configure Security Production Environment
R1 | RO1 | Process and Application | Business Process Controls | MT4112 | % of Financially Significant Processes by Rollout | % of total number of processes that are financially significant for a rollout and for which controls needs to be designed | NA | 25 |  |  | Formula Usage for % of Financially Significant Processes by Rollout: . MT4114 - # of Financially Significant Processes by Rollout(Rule of Thumb Formula = % of Financially Significant Processes by Rollout*Processes by Rollout (L2)/100, Rule of Thumb Calculation = 0)
R1 | RO1 | Process and Application | Business Process Controls | MT4119 | Financial Controls by Rollout (1 = Yes, 0 = No) | Financial Controls are designed to ensure the fairness, accuracy, and reliability of financial data. | NA | 0 |  |  | Formula Usage for Financial Controls by Rollout (1 = Yes, 0 = No): . MT4118 - # of Business Process Controls by Rollout(Rule of Thumb Formula = # of Financially Significant Processes by Rollout*((Financial Controls by Rollout (1 = Yes, 0 = No)*Financial Controls per Business Process by Rollout)+(Operational Controls by Rollout (1 = Yes, 0 = No)*Operational Controls per Business Process by Rollout)+(Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process by Rollout)), Rule of Thumb Calculation = 0)
R1 | RO1 | Process and Application | Business Process Controls | MT4122 | Financial Controls per Business Process by Rollout | Financial Controls are designed to ensure the fairness, accuracy, and reliability of financial data. | NA | 5 |  |  | Formula Usage for Financial Controls per Business Process by Rollout: . MT4118 - # of Business Process Controls by Rollout(Rule of Thumb Formula = # of Financially Significant Processes by Rollout*((Financial Controls by Rollout (1 = Yes, 0 = No)*Financial Controls per Business Process by Rollout)+(Operational Controls by Rollout (1 = Yes, 0 = No)*Operational Controls per Business Process by Rollout)+(Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process by Rollout)), Rule of Thumb Calculation = 0)
R1 | RO1 | Process and Application | Business Process Controls | MT4120 | Operational Controls by Rollout (1 = Yes, 0 = No) | Operational Controls are designed to evaluate an area, department or functional operation. May typically be a client resource. | NA | 0 |  |  | Formula Usage for Operational Controls by Rollout (1 = Yes, 0 = No): . MT4118 - # of Business Process Controls by Rollout(Rule of Thumb Formula = # of Financially Significant Processes by Rollout*((Financial Controls by Rollout (1 = Yes, 0 = No)*Financial Controls per Business Process by Rollout)+(Operational Controls by Rollout (1 = Yes, 0 = No)*Operational Controls per Business Process by Rollout)+(Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process by Rollout)), Rule of Thumb Calculation = 0)
R1 | RO1 | Process and Application | Business Process Controls | MT4123 | Operational Controls per Business Process by Rollout | Operational Controls are designed to evaluate an area, department or functional operation. May typically be a client resource. | NA | 8 |  |  | Formula Usage for Operational Controls per Business Process by Rollout: . MT4118 - # of Business Process Controls by Rollout(Rule of Thumb Formula = # of Financially Significant Processes by Rollout*((Financial Controls by Rollout (1 = Yes, 0 = No)*Financial Controls per Business Process by Rollout)+(Operational Controls by Rollout (1 = Yes, 0 = No)*Operational Controls per Business Process by Rollout)+(Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process by Rollout)), Rule of Thumb Calculation = 0)
R1 | RO1 | Process and Application | Business Process Controls | MT4121 | Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No) | Compliance and Regulatory Controls are designed to address the specific department's adherence to laws and regulations, policies and procedures, federal and provincial requirements, and restrictions imposed on endowments and grants. May typically be a client resource. | NA | 0 |  |  | Formula Usage for Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No): . MT4118 - # of Business Process Controls by Rollout(Rule of Thumb Formula = # of Financially Significant Processes by Rollout*((Financial Controls by Rollout (1 = Yes, 0 = No)*Financial Controls per Business Process by Rollout)+(Operational Controls by Rollout (1 = Yes, 0 = No)*Operational Controls per Business Process by Rollout)+(Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process by Rollout)), Rule of Thumb Calculation = 0)
R1 | RO1 | Process and Application | Business Process Controls | MT4124 | Compliance / Regulatory Controls per Business Process by Rollout | Compliance and Regulatory Controls are designed to address the specific department's adherence to laws and regulations, policies and procedures, federal and provincial requirements, and restrictions imposed on endowments and grants. May typically be a client resource. | NA | 2 |  |  | Formula Usage for Compliance / Regulatory Controls per Business Process by Rollout: . MT4118 - # of Business Process Controls by Rollout(Rule of Thumb Formula = # of Financially Significant Processes by Rollout*((Financial Controls by Rollout (1 = Yes, 0 = No)*Financial Controls per Business Process by Rollout)+(Operational Controls by Rollout (1 = Yes, 0 = No)*Operational Controls per Business Process by Rollout)+(Compliance / Regulatory Controls by Rollout (1 = Yes, 0 = No)*Compliance / Regulatory Controls per Business Process by Rollout)), Rule of Thumb Calculation = 0)
R1 | RO1 | Organizational Change Management | Organizational Alignment | MT5316 | Geographic Locations by Rollout | Number of geographic locations where end-users will work. Used in calculating the Change Network activities. | NA |  |  |  | Formula Usage for Geographic Locations by Rollout: . MT5318 - LOB by Location by rollout(Rule of Thumb Formula = Geographic Locations by Rollout*# of Lines of Business (LOB) by Rollout, Rule of Thumb Calculation = 0) . MT5414 - # of LOB in all geographic units by Rollout(Rule of Thumb Formula = # of Lines of Business (LOB) by Rollout*Geographic Locations by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Organizational Change Management | Organizational Alignment | MT5317 | # of Lines of Business (LOB) by Rollout | To be defined as the major lines of business of an organization that will have unique processes in certain areas. For ex: Energy Industry: Distribution, Generation; Hi-Tech Industry: Product, Services. This is not the organizational structure such as, AP, AR, Sales, etc. | NA |  |  |  | Formula Usage for # of Lines of Business (LOB) by Rollout: . MT5318 - LOB by Location by rollout(Rule of Thumb Formula = Geographic Locations by Rollout*# of Lines of Business (LOB) by Rollout, Rule of Thumb Calculation = 0) . MT5414 - # of LOB in all geographic units by Rollout(Rule of Thumb Formula = # of Lines of Business (LOB) by Rollout*Geographic Locations by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Organizational Change Management | Organizational Alignment | MT5370 | Named End Users by Rollout | This is the number of people who will be actively using the ERP system and will need security and role-mapping. Include users who perform data input, systems maintenance, and other primary tasks. Active users may also be known as super users, reporting users, and regular users. May also need to include external users, such as Suppliers. Do not include passive or occasional users such as self-service, payroll counts or time recording users. | NA |  |  |  | Formula Usage for Named End Users by Rollout: . MT6292 - Instructor-Led Training: Total Student Days by Rollout(Rule of Thumb Formula = Named End Users by Rollout*Instructor-Led Training: Average Training Days per End-User by Rollout, Rule of Thumb Calculation = 0) | Task Usage for Named End Users by Rollout: 4.TE.SE.02133 - Analyze User Segregation of Duties 4.TE.SE.02192 - Load Security Production End-User Accounts (Establish User ID's)
R1 | RO1 | Organizational Change Management | End-User Training | MT6203 | Instructor-Led Training: Average Training Days per End-User by Rollout | The average number of training days for each end user. For ERP training, it is generally 3-5 days. Note: This is also used to calculate end-user training cost in the Business case module (not developed yet) | NA |  |  |  | Formula Usage for Instructor-Led Training: Average Training Days per End-User by Rollout: . MT6292 - Instructor-Led Training: Total Student Days by Rollout(Rule of Thumb Formula = Named End Users by Rollout*Instructor-Led Training: Average Training Days per End-User by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Organizational Change Management | End-User Training | MT6202 | Instructor-Led Training: Average Training Class or Session Size by Rollout | The average number of students in a class. It is use to calculate the number of training days. | NA |  |  |  | Formula Usage for Instructor-Led Training: Average Training Class or Session Size by Rollout: . MT6293 - Instructor-Led Training: Classroom Days by Rollout(Rule of Thumb Formula = Instructor-Led Training: Total Student Days by Rollout/Instructor-Led Training: Average Training Class or Session Size by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Development | Application Development | MT3289 | Point-to-Point Interfaces: Total by Rollout | Total number of point-to-point interfaces by rollout. | NA | 0 |  |  |  | Task Usage for Point-to-Point Interfaces: Total by Rollout: 4.DV.DC.02011 - Verify Interface Control Framework
R1 | RO1 | Development | Application Development | MT3286 | Automated Conversions: Total by Rollout | Total number of automated conversions by rollout. | NA | 0 |  |  | Formula Usage for Automated Conversions: Total by Rollout: . MT2340 - Automated Conversion Executions by Rollout(Rule of Thumb Formula = Cutover dress Rehearsals by Rollout*Automated Conversions: Total by Rollout, Rule of Thumb Calculation = 0) . MT4310 - # of Financially Significant Data Conversion Controls by Rollout(Rule of Thumb Formula = % of Financially Significant Data Conversion Controls by Rollout*Automated Conversions: Total by Rollout/100, Rule of Thumb Calculation = 0)
R1 | RO1 | Development | Legacy System Development | MT3287 | Legacy Systems to Be Replaced by Rollout | The number of legacy systems to be replaced. | NA |  |  |  | Formula Usage for Legacy Systems to Be Replaced by Rollout: . MT4320 - Legacy Requiring Data Controls by Rollout(Rule of Thumb Formula = Legacy Systems to Be Replaced by Rollout+Legacy Systems to Be Interfaced by Rollout, Rule of Thumb Calculation = 0) | Task Usage for Legacy Systems to Be Replaced by Rollout: 4.DP.SD.02274 - Perform Legacy System Decommissioning
R1 | RO1 | Development | Legacy System Development | MT3291 | Legacy Systems to Be Interfaced by Rollout | The number of legacy systems to be interfaced. Each interface should be uni-directional. If bi-directional count as 2 interfaces. | NA |  |  |  | Formula Usage for Legacy Systems to Be Interfaced by Rollout: . MT4320 - Legacy Requiring Data Controls by Rollout(Rule of Thumb Formula = Legacy Systems to Be Replaced by Rollout+Legacy Systems to Be Interfaced by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Development | Development Controls | MT4309 | % of Financially Significant Data Conversion Controls by Rollout | % of Data conversion controls that are financially significant. | NA | 25 |  |  | Formula Usage for % of Financially Significant Data Conversion Controls by Rollout: . MT4310 - # of Financially Significant Data Conversion Controls by Rollout(Rule of Thumb Formula = % of Financially Significant Data Conversion Controls by Rollout*Automated Conversions: Total by Rollout/100, Rule of Thumb Calculation = 0)
R1 | RO1 | Technology | Technology Controls | MT4206 | IT Controls per Technical Process by Rollout | Assumption (based on best practices) for the number of IT Controls needed per technical process. | NA | 3 |  |  | Formula Usage for IT Controls per Technical Process by Rollout: . MT4219 - IT Controls by Rollout(Rule of Thumb Formula = Technical Processes per Rollout*IT Controls per Technical Process by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Technology | Technology Controls | MT4205 | Technical Processes per Rollout | Number of technical processes (per Rollout) e.g. System and Data backup, Data archiving, System administration, for which IT controls are in scope. | NA |  |  |  | Formula Usage for Technical Processes per Rollout: . MT4219 - IT Controls by Rollout(Rule of Thumb Formula = Technical Processes per Rollout*IT Controls per Technical Process by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Deployment | Support Preparation & Stabilization | MT2330 | Cutover dress Rehearsals by Rollout | Number of dress rehearsals or dry runs to be executed prior to final cutover. | NA | 3 |  |  | Formula Usage for Cutover dress Rehearsals by Rollout: . MT2340 - Automated Conversion Executions by Rollout(Rule of Thumb Formula = Cutover dress Rehearsals by Rollout*Automated Conversions: Total by Rollout, Rule of Thumb Calculation = 0)
R1 | RO1 | Deployment | Support Preparation & Stabilization | MT2350 | Manual Conversion Executions by Rollout | Product of manual conversion per rollout and cutover dress rehearsals. | NA |  |  |  |  | Task Usage for Manual Conversion Executions by Rollout: 4.IM.MD.00165 - Perform Manual Conversions
R1 | RO1 | Deployment | Readiness Testing | MT2418 | Integration Test Cases by Rollout | The number of integration test cases is the number of test objects times 8 | NA |  | Integration Test Objects*8 |  | Formula Usage for Integration Test Cases by Rollout: . MT2428 - User Acceptance Test Cases by Rollout(Rule of Thumb Formula = Integration Test Cases by Rollout*% of Integration Test Cases Executed in User Acceptance Test by Rollout/100, Rule of Thumb Calculation = 0)
R1 | RO1 | Deployment | Readiness Testing | MT2419 | % of Integration Test Cases Executed in User Acceptance Test by Rollout | User acceptance or Day in the Life testing involves execution of key transactions. Please enter the % of integration test cases expected to be executed in this phase of testing. | NA | 10 |  |  | Formula Usage for % of Integration Test Cases Executed in User Acceptance Test by Rollout: . MT2428 - User Acceptance Test Cases by Rollout(Rule of Thumb Formula = Integration Test Cases by Rollout*% of Integration Test Cases Executed in User Acceptance Test by Rollout/100, Rule of Thumb Calculation = 0)
R1 | RO1 | Deployment | Readiness Testing | MT2420 | User Acceptance Test Cycles by Rollout | User acceptance or Day in the life test cycle is defined as the number of times the Day in the life test cases are executed. Enter the number of test cycles that are planned. | NA | 1 |  |  | Formula Usage for User Acceptance Test Cycles by Rollout: . MT2425 - User Acceptance Test Executions by Rollout(Rule of Thumb Formula = User Acceptance Test Cases by Rollout*User Acceptance Test Cycles by Rollout, Rule of Thumb Calculation = 0)